## Report1
JobCostReportDetail
Group By 1 = Property
Group By 2 = Job
Group By 3 = Category
Property = .emr
Category Tree = ysi_JobCost
Period = Jan 1900 - Jan 2100 | [13 empty] | ADD | CASH PAID TO DATE | (REVISED BUDGET - CASH PAID TO DATE)
Property | Description | Job | Job Description | Category Code | Category | Approved Budget | Revised Budget | Contracts CO 's | AP JE & JCA | Purchase Orders | Total Committed | Uncommitted Balance | Current Period Cost | Pending Contract Amount | Total Cost To Date | Undisbursed Budget Balance | Undisbursed Committed Cost | % Complete
100690 | Estrella North LLC | 100690-bi-0001 | Welcome Center Upgrades | 20-02-21-60-15 | Parking Lot | 0 | 37982 | 37982 | 0 | 0 | 37982 | 0 | 37982 |  | 37982 | 0 | 0 | 100
|  |  |  | 25-02-56-40-31 | Marketing Miscellaneous | 0 | 167459 | 0 | 167459 | 0 | 167459 | 0 | 167459 |  | 167459 | 0 | 0 | 100
|  | Total 100690-bi-0001 |  |  |  | 0 | 205441 | 37982 | 167459 | 0 | 205441 | 0 | 205441 |  | 205441 | 0 | 0 | 100
|  | 100690-ldam-0081 | Community 9 Parcel 23 Park | 20-02-12-20-01 | Land Planning | 0 | 0 | 17500 | 89 | 0 | 17589 | -17589 | 8531 |  | 8531 | -8531 | 9058 | 0
|  |  |  | 20-02-12-20-06 | Engineering-General | 139995 | 139995 | 32500 | 0 | 0 | 32500 | 107495 | 0 |  | 0 | 139995 | 32500 | 0
|  |  |  | 20-02-21-50-04 | Environmental Cleanup | 11311 | 11311 | 0 | 0 | 0 | 0 | 11311 | 0 |  | 0 | 11311 | 0 | 0
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 2799900 | 3799900 | 11310 | 0 | 0 | 11310 | 3788590 | 11310 |  | 11310 | 3788590 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 279990 | 279990 | 0 | 0 | 0 | 0 | 279990 | 0 |  | 0 | 279990 | 0 | 0
|  | Total 100690-ldam-0081 |  |  |  | 3231196 | 4231196 | 61310 | 89 | 0 | 61399 | 4169797 | 19841 |  | 19841 | 4211355 | 41558 | 0
|  | 100690-ldam-0603 | Ladera Park | 20-02-12-10-05 | Geotechnical Studies | 1100 | 7900 | 7900 | 0 | 0 | 7900 | 0 | 7900 |  | 7900 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 5000 | 11000 | 11000 | 0 | 0 | 11000 | 0 | 11000 |  | 11000 | 0 | 0 | 100
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 137 | 137 | 0 | 137 | 0 | 137 | 0 | 137 |  | 137 | 0 | 0 | 100
|  |  |  | 20-02-12-20-01 | Land Planning | 15910 | 18220 | 18060 | 0 | 0 | 18060 | 160 | 18220 |  | 18220 | 0 | -160 | 100
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 95 | 0 | 95 | 0 | 95 | 0 | 95 |  | 95 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 2577 | 2577 | 0 | 2577 | 0 | 2577 | 0 | 2577 |  | 2577 | 0 | 0 | 100
|  |  |  | 20-02-21-40-02 | Inspection Fees | 1184 | 1184 | 0 | 1184 | 0 | 1184 | 0 | 1184 |  | 1184 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 0 | 5695 | 0 | 5695 | 0 | 5695 | 0 | 5695 |  | 5695 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 3675 | 1900 | 1900 | 0 | 0 | 1900 | 0 | 1900 |  | 1900 | 0 | 0 | 100
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 0 | 781 | 0 | 781 | 0 | 781 | 0 | 781 |  | 781 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 2986 | 17498 | 0 | 13397 | 0 | 13397 | 4101 | 13397 |  | 13397 | 4101 | 0 | 77
|  |  |  | 20-02-22-60-07 | Outdoor Furnishings | 39082 | 39082 | 38850 | 232 | 0 | 39082 | 0 | 39082 |  | 39082 | 0 | 0 | 100
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 984088 | 976073 | 976073 | 0 | 0 | 976073 | 0 | 976073 |  | 976073 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 12000 | 11400 | 11400 | 0 | 0 | 11400 | 0 | 11400 |  | 11400 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldam-0603 |  |  |  | 1092739 | 1093542 | 1065183 | 24098 | 0 | 1089281 | 4261 | 1089441 |  | 1089441 | 4101 | -160 | 100
|  | 100690-ldam-0604 | Community 9 Parcel 10 Park | 20-02-12-10-07 | Engineering Studies | 67500 | 67500 | 2450 | 0 | 0 | 2450 | 65050 | 902 |  | 902 | 66598 | 1548 | 1
|  |  |  | 20-02-12-10-15 | Drainage/ 404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 1090800 | 1090800 | 0 | 0 | 0 | 0 | 1090800 | 0 |  | 0 | 1090800 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 109080 | 109080 | 0 | 0 | 0 | 0 | 109080 | 0 |  | 0 | 109080 | 0 | 0
|  | Total 100690-ldam-0604 |  |  |  | 1267380 | 1267380 | 2450 | 0 | 0 | 2450 | 1264930 | 902 |  | 902 | 1266478 | 1548 | 0
|  | 100690-ldcc-0001 | Cotton Lane | 20-02-12-20-06 | Engineering-General | 2839231 | 2839231 | 0 | 0 | 0 | 0 | 2839231 | 0 |  | 0 | 2839231 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 48266934 | 48266934 | 0 | 0 | 0 | 0 | 48266934 | 0 |  | 0 | 48266934 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 5678463 | 5678463 | 0 | 0 | 0 | 0 | 5678463 | 0 |  | 0 | 5678463 | 0 | 0
|  | Total 100690-ldcc-0001 |  |  |  | 56784628 | 56784628 | 0 | 0 | 0 | 0 | 56784628 | 0 |  | 0 | 56784628 | 0 | 0
|  | 100690-ldcc-0002 | General Traffic Signals | 20-02-12-20-06 | Engineering-General | 120750 | 120750 | 0 | 0 | 0 | 0 | 120750 | 0 |  | 0 | 120750 | 0 | 0
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 2052750 | 2052750 | 0 | 0 | 0 | 0 | 2052750 | 0 |  | 0 | 2052750 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 241500 | 241500 | 0 | 0 | 0 | 0 | 241500 | 0 |  | 0 | 241500 | 0 | 0
|  | Total 100690-ldcc-0002 |  |  |  | 2415000 | 2415000 | 0 | 0 | 0 | 0 | 2415000 | 0 |  | 0 | 2415000 | 0 | 0
|  | 100690-ldcc-0003 | Willis Road | 20-02-12-20-06 | Engineering-General | 25668 | 25668 | 0 | 0 | 0 | 0 | 25668 | 0 |  | 0 | 25668 | 0 | 0
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 436356 | 436356 | 0 | 0 | 0 | 0 | 436356 | 0 |  | 0 | 436356 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 10000 | 0 | 1320 | 0 | 1320 | 8680 | 1320 |  | 1320 | 8680 | 0 | 13
|  |  |  | 25-02-59-91-03 | Contingency - Development | 51336 | 41336 | 0 | 0 | 0 | 0 | 41336 | 0 |  | 0 | 41336 | 0 | 0
|  | Total 100690-ldcc-0003 |  |  |  | 513360 | 513360 | 0 | 1320 | 0 | 1320 | 512040 | 1320 |  | 1320 | 512040 | 0 | 0
|  | 100690-ldcc-0004 | Zone 2 Water | 20-02-12-20-06 | Engineering-General | 255769 | 255769 | 0 | 0 | 0 | 0 | 255769 | 0 |  | 0 | 255769 | 0 | 0
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 2050488 | 2050488 | 0 | 0 | 0 | 0 | 2050488 | 0 |  | 0 | 2050488 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 227832 | 227832 | 0 | 0 | 0 | 0 | 227832 | 0 |  | 0 | 227832 | 0 | 0
|  | Total 100690-ldcc-0004 |  |  |  | 2534089 | 2534089 | 0 | 0 | 0 | 0 | 2534089 | 0 |  | 0 | 2534089 | 0 | 0
|  | 100690-ldcc-0005 | General R&M - Legacy Parcels | 20-02-21-40-01 | Municipality Fees | 0 | 90000 | 0 | 1098 | 0 | 1098 | 88902 | 1098 |  | 1098 | 88902 | 0 | 1
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 0 | 10000 | 0 | 21897 | 0 | 21897 | -11897 | 21897 |  | 21897 | -11897 | 0 | 219
|  |  |  | 25-02-56-50-04 | Cap OH-R&M-Landscape | 0 | 50000 | 29798 | 7050 | 0 | 36848 | 13152 | 7050 |  | 7050 | 42950 | 29798 | 14
|  | Total 100690-ldcc-0005 |  |  |  | 0 | 150000 | 29798 | 30045 | 0 | 59843 | 90157 | 30045 |  | 30045 | 119955 | 29798 | 20
|  | 100690-ldcc-0006 | Canta Mia Lift Station | 20-02-21-90-03 | Reclaimed Water Pump Station | 0 | 200000 | 31600 | 0 | 0 | 31600 | 168400 | 0 |  | 0 | 200000 | 31600 | 0
|  | Total 100690-ldcc-0006 |  |  |  | 0 | 200000 | 31600 | 0 | 0 | 31600 | 168400 | 0 |  | 0 | 200000 | 31600 | 0
|  | 100690-ldcc-0007 | Non-Potable System | 20-02-21-90-01 | Reclaimed Non-Potable Water | 0 | 200000 | 173990 | 0 | 0 | 173990 | 26010 | 0 |  | 0 | 200000 | 173990 | 0
|  | Total 100690-ldcc-0007 |  |  |  | 0 | 200000 | 173990 | 0 | 0 | 173990 | 26010 | 0 |  | 0 | 200000 | 173990 | 0
|  | 100690-ldcc-0093 | Resmark Warranty Work | 20-02-21-40-01 | Municipality Fees | 0 | 1195786 | 0 | 0 | 0 | 0 | 1195786 | 0 |  | 0 | 1195786 | 0 | 0
|  |  |  | 20-02-21-45-04 | Performance Bonds | 0 | 0 | 0 | -4214 | 0 | -4214 | 4214 | -4214 |  | -4214 | 4214 | 0 | 0
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 400000 | 1224845 | 1186065 | 45384 | 0 | 1231448 | -6603 | 1211207 |  | 1211207 | 13638 | 20241 | 99
|  |  |  | 20-02-21-70-05 | Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldcc-0093 |  |  |  | 400000 | 2420631 | 1186065 | 41170 | 0 | 1227234 | 1193397 | 1206993 |  | 1206993 | 1213638 | 20241 | 50
|  | 100690-ldcc-0094 | Community Wide Warranty | 20-02-21-60-14 | Warranty / Punch List | 1980000 | 1980000 | 0 | 0 | 0 | 0 | 1980000 | 0 |  | 0 | 1980000 | 0 | 0
|  | Total 100690-ldcc-0094 |  |  |  | 1980000 | 1980000 | 0 | 0 | 0 | 0 | 1980000 | 0 |  | 0 | 1980000 | 0 | 0
|  | 100690-ldcc-0352 | Community 14 Infrastructure | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 62387148 | 62387148 | 0 | 0 | 0 | 0 | 62387148 | 0 |  | 0 | 62387148 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 6931905 | 6931905 | 0 | 0 | 0 | 0 | 6931905 | 0 |  | 0 | 6931905 | 0 | 0
|  | Total 100690-ldcc-0352 |  |  |  | 69319053 | 69319053 | 0 | 0 | 0 | 0 | 69319053 | 0 |  | 0 | 69319053 | 0 | 0
|  | 100690-ldcc-0358 | Community 15 Infrastructure | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 36690300 | 36690300 | 0 | 0 | 0 | 0 | 36690300 | 0 |  | 0 | 36690300 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 4076700 | 4076700 | 0 | 0 | 0 | 0 | 4076700 | 0 |  | 0 | 4076700 | 0 | 0
|  | Total 100690-ldcc-0358 |  |  |  | 40767000 | 40767000 | 0 | 0 | 0 | 0 | 40767000 | 0 |  | 0 | 40767000 | 0 | 0
|  | 100690-ldcc-0403 | Calistoga Drive & WMV Rd- Dev | 20-02-23-00-02 | General Contractor-Onsite Development | 13304503 | 13304503 | 66886 | 0 | 0 | 66886 | 13237617 | 66885 |  | 66885 | 13237618 | 1 | 1
|  |  |  | 25-02-59-91-03 | Contingency - Development | 1478278 | 1478278 | 0 | 0 | 0 | 0 | 1478278 | 0 |  | 0 | 1478278 | 0 | 0
|  | Total 100690-ldcc-0403 |  |  |  | 14782781 | 14782781 | 66886 | 0 | 0 | 66886 | 14715895 | 66885 |  | 66885 | 14715896 | 1 | 0
|  | 100690-ldcc-0404 | RVWRF Expansion | 20-02-12-10-07 | Engineering Studies | 1195000 | 1195000 | 972 | 0 | 0 | 972 | 1194028 | 972 |  | 972 | 1194028 | 0 | 0
|  |  |  | 20-02-12-20-01 | Land Planning | 600000 | 570000 | 0 | 24976 | 0 | 24976 | 545024 | 24976 |  | 24976 | 545024 | 0 | 4
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 5000 | 5000 | 0 | 68 | 0 | 68 | 4932 | 68 |  | 68 | 4932 | 0 | 1
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 360000 | 360000 | 0 | 103828 | 0 | 103828 | 256172 | 103828 |  | 103828 | 256172 | 0 | 29
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 23040000 | 29224271 | 0 | 0 | 0 | 0 | 29224271 | 0 |  | 0 | 29224271 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 30000 | 30000 | 0 | 0 | 30000 | 0 | 0 |  | 0 | 30000 | 30000 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 2800000 | 2800000 | 0 | 0 | 0 | 0 | 2800000 | 0 |  | 0 | 2800000 | 0 | 0
|  | Total 100690-ldcc-0404 |  |  |  | 28000000 | 34184271 | 30972 | 128872 | 0 | 159844 | 34024427 | 129844 |  | 129844 | 34054427 | 30000 | 0
|  | 100690-ldcc-0406 | CAP Phase 2 (24" Water Line) | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 24570000 | 24570000 | 0 | 0 | 0 | 0 | 24570000 | 0 |  | 0 | 24570000 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 2730000 | 2730000 | 0 | 0 | 0 | 0 | 2730000 | 0 |  | 0 | 2730000 | 0 | 0
|  | Total 100690-ldcc-0406 |  |  |  | 27300000 | 27300000 | 0 | 0 | 0 | 0 | 27300000 | 0 |  | 0 | 27300000 | 0 | 0
|  | 100690-ldcc-0407 | CAP Phase 1 (30" Water Line) | 20-02-12-10-07 | Engineering Studies | 33603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-10-13 | Other Studies-Consultants | 430853 | 347617 | 364757 | -17140 | 0 | 347617 | 0 | 347617 |  | 347617 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 700 | 700 | 0 | 700 | 0 | 700 | 0 | 700 |  | 700 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 54732 | 187108 | 0 | 187108 | 0 | 187108 | 0 | 187108 |  | 187108 | 0 | 0 | 100
|  |  |  | 20-02-21-80-01 | Water Trunk System | 3677562 | 3418962 | 3694262 | -275301 | 0 | 3418962 | 0 | 3418962 |  | 3418962 | 0 | 0 | 100
|  |  |  | 20-02-21-80-03 | Water Main & Laterals | 1583068 | 1539374 | 0 | 1539374 | 0 | 1539374 | 0 | 1539374 |  | 1539374 | 0 | 0 | 100
|  |  |  | 20-02-22-20-01 | Dry-Underground Utilities | 736267 | 364050 | 364050 | 0 | 0 | 364050 | 0 | 364050 |  | 364050 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 10000 | 6956 | 6956 | 0 | 0 | 6956 | 0 | 6956 |  | 6956 | 0 | 0 | 100
|  | Total 100690-ldcc-0407 |  |  |  | 6526785 | 5864767 | 4430025 | 1434741 | 0 | 5864767 | 0 | 5864767 |  | 5864767 | 0 | 0 | 100
|  | 100690-ldcc-0408 | San Miguel Road - Development | 20-02-23-00-02 | General Contractor-Onsite Development | 1580040 | 1580040 | 0 | 0 | 0 | 0 | 1580040 | 0 |  | 0 | 1580040 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 175560 | 175560 | 0 | 0 | 0 | 0 | 175560 | 0 |  | 0 | 175560 | 0 | 0
|  | Total 100690-ldcc-0408 |  |  |  | 1755600 | 1755600 | 0 | 0 | 0 | 0 | 1755600 | 0 |  | 0 | 1755600 | 0 | 0
|  | 100690-ldcc-0409 | Sendero Dr Ph3 - Development | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 3638191 | 3538191 | 0 | 0 | 0 | 0 | 3538191 | 0 |  | 0 | 3538191 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 |  | 0 | 100000 | 0 | 0
|  | Total 100690-ldcc-0409 |  |  |  | 3638191 | 3638191 | 0 | 0 | 0 | 0 | 3638191 | 0 |  | 0 | 3638191 | 0 | 0
|  | 100690-ldcc-0410 | Sendero Dr Ph2 - Development | 20-02-12-10-05 | Geotechnical Studies | 14300 | 3520 | 3520 | 0 | 0 | 3520 | 0 | 3520 |  | 3520 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 8861 | 2997 | 3497 | 0 | 0 | 3497 | -500 | 3333 |  | 3333 | -336 | 164 | 111
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 320 | 320 | 0 | 320 | 0 | 320 | 0 | 320 |  | 320 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 956 | 850 | 850 | 0 | 0 | 850 | 0 | 850 |  | 850 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 4415 | 550 | 550 | 0 | 0 | 550 | 0 | 550 |  | 550 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 15000 | 6007 | 0 | 6007 | 0 | 6007 | 0 | 6007 |  | 6007 | 0 | 0 | 100
|  |  |  | 20-02-21-40-02 | Inspection Fees | 3750 | 3750 | 0 | 3750 | 0 | 3750 | 0 | 3750 |  | 3750 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 87034 | 87403 | 0 | 87403 | 0 | 87403 | 0 | 87403 |  | 87403 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 3321 | 9963 | 0 | 9963 | 0 | 9963 | 0 | 9963 |  | 9963 | 0 | 0 | 100
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 33891 | 33891 | 33891 | 0 | 0 | 33891 | 0 | 33891 |  | 33891 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 11438 | 6692 | 6692 | 0 | 0 | 6692 | 0 | 6692 |  | 6692 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 475196 | 34257 | 34257 | 0 | 0 | 34257 | 0 | 34257 |  | 34257 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 708 | 402 | 402 | 0 | 0 | 402 | 0 | 402 |  | 402 | 0 | 0 | 100
|  |  |  | 20-02-21-60-02 | Paving | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-60-04 | Street Lights | 1091 | 1091 | 1091 | 0 | 0 | 1091 | 0 | 1091 |  | 1091 | 0 | 0 | 100
|  |  |  | 20-02-21-80-01 | Water Trunk System | 69219 | 69219 | 69219 | 0 | 0 | 69219 | 0 | 69219 |  | 69219 | 0 | 0 | 100
|  |  |  | 20-02-21-90-01 | Reclaimed Non-Potable Water | 37819 | 37819 | 37819 | 0 | 0 | 37819 | 0 | 37819 |  | 37819 | 0 | 0 | 100
|  |  |  | 20-02-22-00-02 | Sewer Collection | 16783 | 16783 | 16783 | 0 | 0 | 16783 | 0 | 16783 |  | 16783 | 0 | 0 | 100
|  |  |  | 20-02-22-10-01 | Storm Drainage System | 6207 | 6207 | 6207 | 0 | 0 | 6207 | 0 | 6207 |  | 6207 | 0 | 0 | 100
|  |  |  | 20-02-22-20-01 | Dry-Underground Utilities | 18514 | 18514 | 18514 | 0 | 0 | 18514 | 0 | 18514 |  | 18514 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 3165 | 3165 | 3165 | 0 | 0 | 3165 | 0 | 3165 |  | 3165 | 0 | 0 | 100
|  |  |  | 20-02-22-60-02 | Play/Tot Lot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 14750 | 14457 | 11800 | 2657 | 0 | 14457 | 0 | 14457 |  | 14457 | 0 | 0 | 100
|  |  |  | 22-02-24-00-00 | Environmental Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 25000 | 34992 | 0 | 0 | 0 | 0 | 34992 | 0 |  | 0 | 34992 | 0 | 0
|  | Total 100690-ldcc-0410 |  |  |  | 851738 | 392849 | 248257 | 110100 | 0 | 358357 | 34492 | 358193 |  | 358193 | 34656 | 164 | 91
|  | 100690-ldcc-0411 | Ardmore Road - Development | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 795986 | 710627 | 0 | 0 | 0 | 0 | 710627 | 0 |  | 0 | 710627 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 5760 | 0 | 0 | 0 | 0 | 5760 | 0 |  | 0 | 5760 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 0 | 79599 | 0 | 0 | 0 | 0 | 79599 | 0 |  | 0 | 79599 | 0 | 0
|  | Total 100690-ldcc-0411 |  |  |  | 795986 | 795986 | 0 | 0 | 0 | 0 | 795986 | 0 |  | 0 | 795986 | 0 | 0
|  | 100690-ldcc-0412 | Community 11 Traffic Signal - North | 20-02-12-10-07 | Engineering Studies | 38600 | 38600 | 19800 | 0 | 0 | 19800 | 18800 | 19800 |  | 19800 | 18800 | 0 | 51
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 39 | 1039 | 0 | 39 | 0 | 39 | 1000 | 39 |  | 39 | 1000 | 0 | 4
|  |  |  | 20-02-21-40-01 | Municipality Fees | 5000 | 14000 | 4084 | 1152 | 0 | 5236 | 8764 | 5236 |  | 5236 | 8764 | 0 | 37
|  |  |  | 20-02-21-45-04 | Performance Bonds | 0 | 3690 | 0 | 3690 | 0 | 3690 | 0 | 3690 |  | 3690 | 0 | 0 | 100
|  |  |  | 20-02-21-60-05 | Traffic Control Devices | 843585 | 843815 | 843585 | 0 | 0 | 843585 | 230 | 843815 |  | 843815 | 0 | -230 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 15000 | 15000 | 15000 | 0 | 0 | 15000 | 0 | 8300 |  | 8300 | 6700 | 6700 | 55
|  |  |  | 25-02-59-91-03 | Contingency - Development | 100000 | 86079 | 0 | 0 | 0 | 0 | 86079 | 0 |  | 0 | 86079 | 0 | 0
|  | Total 100690-ldcc-0412 |  |  |  | 1002224 | 1002223 | 882469 | 4881 | 0 | 887350 | 114873 | 880880 |  | 880880 | 121343 | 6470 | 88
|  | 100690-ldcc-0413 | Community 11 Nursery | 20-02-21-50-03 | Demolition-Razing | 61682 | 101071 | 57096 | 24389 | 0 | 81485 | 19586 | 81485 |  | 81485 | 19586 | 0 | 81
|  |  |  | 20-02-21-50-26 | Silt Fence | 10040 | 4525 | 4525 | 0 | 0 | 4525 | 0 | 4525 |  | 4525 | 0 | 0 | 100
|  | Total 100690-ldcc-0413 |  |  |  | 71722 | 105596 | 61621 | 24389 | 0 | 86010 | 19586 | 86010 |  | 86010 | 19586 | 0 | 81
|  | 100690-ldcc-0414 | Lucero Sub-Collector J/D3 | 20-02-12-10-07 | Engineering Studies | 100000 | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 |  | 0 | 100000 | 0 | 0
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 1226991 | 1226991 | 0 | 0 | 0 | 0 | 1226991 | 0 |  | 0 | 1226991 | 0 | 0
|  | Total 100690-ldcc-0414 |  |  |  | 1326991 | 1326991 | 0 | 0 | 0 | 0 | 1326991 | 0 |  | 0 | 1326991 | 0 | 0
|  | 100690-ldcc-0415 | Sendero Lift Station - Development | 20-02-23-00-02 | General Contractor-Onsite Development | 800000 | 800000 | 774463 | 0 | 0 | 774463 | 25537 | 183406 |  | 183406 | 616594 | 591057 | 23
|  | Total 100690-ldcc-0415 |  |  |  | 800000 | 800000 | 774463 | 0 | 0 | 774463 | 25537 | 183406 |  | 183406 | 616594 | 591057 | 23
|  | 100690-ldcc-0416 | Community 11 Traffic Signal - South | 20-02-12-20-24 | Final Engineering | 65639 | 65639 | 21200 | 0 | 0 | 21200 | 44439 | 20400 |  | 20400 | 45239 | 800 | 31
|  |  |  | 20-02-21-40-01 | Municipality Fees | 0 | 0 | 0 | 10608 | 0 | 10608 | -10608 | 10608 |  | 10608 | -10608 | 0 | 0
|  |  |  | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 590748 | 1216871 | 1216871 | 0 | 0 | 1216871 | 0 | 317280 |  | 317280 | 899591 | 899591 | 26
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 7929 | 7250 | 679 | 0 | 7929 | 0 | 7929 |  | 7929 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 72932 | 65003 | 0 | 0 | 0 | 0 | 65003 | 0 |  | 0 | 65003 | 0 | 0
|  | Total 100690-ldcc-0416 |  |  |  | 729319 | 1355442 | 1245321 | 11287 | 0 | 1256608 | 98834 | 356217 |  | 356217 | 999225 | 900391 | 26
|  | 100690-ldcc-0590 | Common Marketing Costs | 20-02-12-30-10 | Legal-Public Relations | 0 | 0 | 0 | 9300 | 0 | 9300 | -9300 | 9300 |  | 9300 | -9300 | 0 | 0
|  |  |  | 25-02-56-40-05 | Outdoor Advertising Production | 238150 | 238150 | 0 | 174299 | 0 | 174299 | 63851 | 174299 |  | 174299 | 63851 | 0 | 73
|  |  |  | 25-02-56-40-07 | Television Commercial Production | 110000 | 110000 | 0 | 53538 | 0 | 53538 | 56462 | 53538 |  | 53538 | 56462 | 0 | 49
|  |  |  | 25-02-56-40-08 | Online Advertising Production | 68000 | 68000 | 0 | 77259 | 0 | 77259 | -9259 | 77259 |  | 77259 | -9259 | 0 | 114
|  |  |  | 25-02-56-40-09 | Social Media Advertising Production | 477000 | 477000 | 0 | 312336 | 0 | 312336 | 164664 | 312336 |  | 312336 | 164664 | 0 | 65
|  |  |  | 25-02-56-40-10 | Printed Material Placement | 19800 | 19800 | 0 | 1089 | 0 | 1089 | 18711 | 1089 |  | 1089 | 18711 | 0 | 6
|  |  |  | 25-02-56-40-11 | Outdoor Advertising Placement | 14000 | 14000 | 0 | 3547 | 0 | 3547 | 10453 | 3547 |  | 3547 | 10453 | 0 | 25
|  |  |  | 25-02-56-40-13 | Television Commercial Placement | 0 | 0 | 0 | 7313 | 0 | 7313 | -7313 | 7313 |  | 7313 | -7313 | 0 | 0
|  |  |  | 25-02-56-40-14 | Online Advertising Placement | 57500 | 57500 | 0 | 12000 | 0 | 12000 | 45500 | 12000 |  | 12000 | 45500 | 0 | 21
|  |  |  | 25-02-56-40-16 | Brand Initiatives | 55000 | 55000 | 0 | 11000 | 0 | 11000 | 44000 | 11000 |  | 11000 | 44000 | 0 | 20
|  |  |  | 25-02-56-40-18 | Marketing Collateral Production | 40000 | 40000 | 0 | 45332 | 0 | 45332 | -5332 | 45332 |  | 45332 | -5332 | 0 | 113
|  |  |  | 25-02-56-40-21 | Photography | 55000 | 55000 | 0 | 3909 | 0 | 3909 | 51091 | 3909 |  | 3909 | 51091 | 0 | 7
|  |  |  | 25-02-56-40-23 | Website Development | 56000 | 56000 | 0 | 47217 | 0 | 47217 | 8783 | 47217 |  | 47217 | 8783 | 0 | 84
|  |  |  | 25-02-56-40-26 | Agency Retainer Fees | 0 | 0 | 0 | 40000 | 0 | 40000 | -40000 | 40000 |  | 40000 | -40000 | 0 | 0
|  |  |  | 25-02-56-40-31 | Marketing Miscellaneous | 59594 | 59594 | 0 | 392539 | 0 | 392539 | -332945 | 392539 |  | 392539 | -332945 | 0 | 659
|  |  |  | 25-02-56-40-37 | Community Relations | 26000 | 26000 | 0 | 0 | 0 | 0 | 26000 | 0 |  | 0 | 26000 | 0 | 0
|  |  |  | 25-02-56-40-38 | Public Relations | 90000 | 90000 | 0 | 64450 | 0 | 64450 | 25550 | 64450 |  | 64450 | 25550 | 0 | 72
|  |  |  | 25-02-56-40-39 | Client Relations | 165000 | 165000 | 0 | 122835 | 0 | 122835 | 42165 | 122835 |  | 122835 | 42165 | 0 | 74
|  |  |  | 25-02-56-40-40 | Realtor Relations | 7000 | 7000 | 0 | 3210 | 0 | 3210 | 3790 | 3210 |  | 3210 | 3790 | 0 | 46
|  |  |  | 25-02-56-40-46 | Marketing Emails & Nurturing | 12000 | 12000 | 0 | 22326 | 0 | 22326 | -10326 | 22326 |  | 22326 | -10326 | 0 | 186
|  |  |  | 25-02-56-40-48 | Agency Retainer Fees | 240000 | 240000 | 0 | 140000 | 0 | 140000 | 100000 | 140000 |  | 140000 | 100000 | 0 | 58
|  |  |  | 25-02-56-40-50 | Agency Social Media | 114000 | 114000 | 0 | 85500 | 0 | 85500 | 28500 | 85500 |  | 85500 | 28500 | 0 | 75
|  | Total 100690-ldcc-0590 |  |  |  | 1904044 | 1904044 | 0 | 1628999 | 0 | 1628999 | 275045 | 1628999 |  | 1628999 | 275045 | 0 | 86
|  | 100690-ldcc-0605 | Rainbow Valley Rd - Development | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 11289780 | 11289780 | 0 | 0 | 0 | 0 | 11289780 | 0 |  | 0 | 11289780 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 1254420 | 1254420 | 0 | 0 | 0 | 0 | 1254420 | 0 |  | 0 | 1254420 | 0 | 0
|  | Total 100690-ldcc-0605 |  |  |  | 12544200 | 12544200 | 0 | 0 | 0 | 0 | 12544200 | 0 |  | 0 | 12544200 | 0 | 0
|  | 100690-ldcf-0701 | General Cap Fee | 25-02-58-10-01 | Cap Dev Mgmt Fee | 0 | 0 | 0 | 774418 | 0 | 774418 | -774418 | 774418 |  | 774418 | -774418 | 0 | 0
|  |  |  | 25-02-58-10-02 | Cap Dev OH Mgmt Fee | 0 | 0 | 0 | 3583188 | 0 | 3583188 | -3583188 | 3583188 |  | 3583188 | -3583188 | 0 | 0
|  | Total 100690-ldcf-0701 |  |  |  | 0 | 0 | 0 | 4357606 | 0 | 4357606 | -4357606 | 4357606 |  | 4357606 | -4357606 | 0 | 0
|  | 100690-ldci-0959 | General Cap Interest | 25-02-55-20-01 | Interest Paid-N/P-Promissory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-55-20-06 | Interest Paid-B/P | 0 | 0 | 0 | 346481 | 0 | 346481 | -346481 | 346481 |  | 346481 | -346481 | 0 | 0
|  |  |  | 25-02-55-40-01 | Loan Fee Paid-N/P-Promissory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldci-0959 |  |  |  | 0 | 0 | 0 | 346481 | 0 | 346481 | -346481 | 346481 |  | 346481 | -346481 | 0 | 0
|  | 100690-ldco-0701 | General Cap Overhead | 20-02-12-30-10 | Legal-Public Relations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-10-09 | Cap OH-Administrative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-10-90 | Cap OH-Miscellaneous | 0 | 0 | 0 | 17703 | 0 | 17703 | -17703 | 17703 |  | 17703 | -17703 | 0 | 0
|  |  |  | 25-02-56-40-01 | Cap OH-Advertising & Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-05 | Outdoor Advertising Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-08 | Online Advertising Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-09 | Social Media Advertising Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-11 | Outdoor Advertising Placement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-13 | Television Commercial Placement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-18 | Marketing Collateral Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-23 | Website Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-31 | Marketing Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-39 | Client Relations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-46 | Marketing Emails & Nurturing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-48 | Agency Retainer Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-56-40-50 | Agency Social Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-57-10-06 | General Liability Insurance | 0 | 0 | 0 | 1039222 | 0 | 1039222 | -1039222 | 1039222 |  | 1039222 | -1039222 | 0 | 0
|  |  |  | 25-02-58-10-01 | Cap Dev Mgmt Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-58-10-02 | Cap Dev OH Mgmt Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-58-80-01 | Cap-Alloc-Personnel Exp-Bonus | 0 | 0 | 0 | 363012 | 0 | 363012 | -363012 | 363012 |  | 363012 | -363012 | 0 | 0
|  |  |  | 25-02-58-80-02 | Cap-Alloc-Personnel Exp-Vacation | 0 | 0 | 0 | 823182 | 0 | 823182 | -823182 | 823182 |  | 823182 | -823182 | 0 | 0
|  | Total 100690-ldco-0701 |  |  |  | 0 | 0 | 0 | 2243119 | 0 | 2243119 | -2243119 | 2243119 |  | 2243119 | -2243119 | 0 | 0
|  | 100690-ldct-0703 | General Cap RE Taxes | 25-02-57-10-01 | Real Property Tax | 0 | 0 | 0 | 3124893 | 0 | 3124893 | -3124893 | 3124893 |  | 3124893 | -3124893 | 0 | 0
|  | Total 100690-ldct-0703 |  |  |  | 0 | 0 | 0 | 3124893 | 0 | 3124893 | -3124893 | 3124893 |  | 3124893 | -3124893 | 0 | 0
|  | 100690-lddc-0009 | Community 10 Parcel B | 20-02-12-10-05 | Geotechnical Studies | 11200 | 11200 | 2900 | 0 | 0 | 2900 | 8300 | 1200 |  | 1200 | 10000 | 1700 | 11
|  |  |  | 20-02-12-20-04 | Staking | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 |  | 0 | 3000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 3855 | 3855 | 0 | 3855 | 0 | 3855 | 0 | 3855 |  | 3855 | 0 | 0 | 100
|  | Total 100690-lddc-0009 |  |  |  | 18055 | 18055 | 2900 | 3855 | 0 | 6755 | 11300 | 5055 |  | 5055 | 13000 | 1700 | 28
|  | 100690-lddc-0013 | Community 11 Parcel D1 (Legacy) | 20-02-12-10-05 | Geotechnical Studies | 950 | 950 | 950 | 0 | 0 | 950 | 0 | 950 |  | 950 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 326 | 326 | 326 | 0 | 0 | 326 | 0 | 326 |  | 326 | 0 | 0 | 100
|  | Total 100690-lddc-0013 |  |  |  | 1276 | 1276 | 1276 | 0 | 0 | 1276 | 0 | 1276 |  | 1276 | 0 | 0 | 100
|  | 100690-lddc-0015 | Community 11 Parcel E - Dev | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 4326852 | 5885268 | 0 | 511769 | 0 | 511769 | 5373499 | 511769 |  | 511769 | 5373499 | 0 | 9
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 4001753 | 5227508 | 0 | 597376 | 0 | 597376 | 4630132 | 597376 |  | 597376 | 4630132 | 0 | 11
|  |  |  | 22-01-00-00-01 | Division 01 - General Requirements | 0 | 0 | 15160 | 3561 | 0 | 18721 | -18721 | 7697 |  | 7697 | -7697 | 11024 | 0
|  | Total 100690-lddc-0015 |  |  |  | 8328605 | 11112776 | 15160 | 1112706 | 0 | 1127866 | 9984910 | 1116842 |  | 1116842 | 9995934 | 11024 | 10
|  | 100690-lddc-0016 | Community 11 Parcel F1 - Dev | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 3147459 | 4281089 | 0 | 372274 | 0 | 372274 | 3908815 | 372274 |  | 372274 | 3908815 | 0 | 9
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 3687588 | 4447431 | 0 | 617681 | 0 | 617681 | 3829750 | 617681 |  | 617681 | 3829750 | 0 | 14
|  |  |  | 22-01-00-00-01 | Division 01 - General Requirements | 0 | 0 | 9803 | 2185 | 0 | 11988 | -11988 | 4723 |  | 4723 | -4723 | 7265 | 0
|  | Total 100690-lddc-0016 |  |  |  | 6835047 | 8728520 | 9803 | 992140 | 0 | 1001943 | 7726577 | 994678 |  | 994678 | 7733842 | 7265 | 11
|  | 100690-lddc-0019 | Community 11 Parcel H | 20-02-11-20-03 | Title Insurance | 500 | 500 | 0 | 500 | 0 | 500 | 0 | 500 |  | 500 | 0 | 0 | 100
|  |  |  | 20-02-12-10-05 | Geotechnical Studies | 10540 | 10540 | 10540 | 0 | 0 | 10540 | 0 | 10540 |  | 10540 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 30351 | 6444 | 5000 | 1444 | 0 | 6444 | 0 | 6444 |  | 6444 | 0 | 0 | 100
|  |  |  | 20-02-12-10-08 | Engineering Testing | 350 | 350 | 0 | 350 | 0 | 350 | 0 | 350 |  | 350 | 0 | 0 | 100
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 455 | 455 | 0 | 455 | 0 | 455 | 0 | 455 |  | 455 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 11450 | 7342 | 12292 | 0 | 0 | 12292 | -4950 | 7342 |  | 7342 | 0 | 4950 | 100
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 2475 | 680 | 680 | 0 | 0 | 680 | 0 | 680 |  | 680 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 4620 | 4620 | 4620 | 0 | 0 | 4620 | 0 | 4620 |  | 4620 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 38633 | 38633 | 0 | 38633 | 0 | 38633 | 0 | 38633 |  | 38633 | 0 | 0 | 100
|  |  |  | 20-02-21-40-02 | Inspection Fees | 13715 | 13715 | 0 | 13715 | 0 | 13715 | 0 | 13715 |  | 13715 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 0 | 1305 | 0 | 1305 | 0 | 1305 | 0 | 1305 |  | 1305 | 0 | 0 | 100
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 23653 | 23653 | 23653 | 0 | 0 | 23653 | 0 | 23653 |  | 23653 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 7906 | 7906 | 7906 | 0 | 0 | 7906 | 0 | 7906 |  | 7906 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 666461 | 547419 | 547419 | 0 | 0 | 547419 | 0 | 547419 |  | 547419 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 3400 | 3400 | 3150 | 250 | 0 | 3400 | 0 | 3400 |  | 3400 | 0 | 0 | 100
|  |  |  | 20-02-21-60-02 | Paving | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-60-04 | Street Lights | 4272 | 4272 | 4272 | 0 | 0 | 4272 | 0 | 4272 |  | 4272 | 0 | 0 | 100
|  |  |  | 20-02-21-60-06 | Curb & Gutter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-80-01 | Water Trunk System | 335831 | 335831 | 335481 | 350 | 0 | 335831 | 0 | 335831 |  | 335831 | 0 | 0 | 100
|  |  |  | 20-02-22-00-02 | Sewer Collection | 339020 | 339020 | 339020 | 0 | 0 | 339020 | 0 | 339020 |  | 339020 | 0 | 0 | 100
|  |  |  | 20-02-22-10-01 | Storm Drainage System | 63127 | 63127 | 63127 | 0 | 0 | 63127 | 0 | 63127 |  | 63127 | 0 | 0 | 100
|  |  |  | 20-02-22-20-01 | Dry-Underground Utilities | 170136 | 170136 | 170136 | 0 | 0 | 170136 | 0 | 170136 |  | 170136 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 17254 | 17254 | 17254 | 0 | 0 | 17254 | 0 | 17254 |  | 17254 | 0 | 0 | 100
|  |  |  | 20-02-22-40-12 | Walls | 424213 | 424213 | 424213 | 0 | 0 | 424213 | 0 | 424213 |  | 424213 | 0 | 0 | 100
|  |  |  | 20-02-22-60-07 | Outdoor Furnishings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 2635 | 34275 | 7435 | 26840 | 0 | 34275 | 0 | 34275 |  | 34275 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 |  | 0 | 20000 | 0 | 0
|  | Total 100690-lddc-0019 |  |  |  | 2190997 | 2075090 | 1976198 | 83842 | 0 | 2060040 | 15050 | 2055090 |  | 2055090 | 20000 | 4950 | 99
|  | 100690-lddc-0020 | Community 11 Parcel I1 - Dev | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 1615334 | 2197134 | 0 | 191058 | 0 | 191058 | 2006076 | 191058 |  | 191058 | 2006076 | 0 | 9
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 2002059 | 2274451 | 0 | 67928 | 0 | 67928 | 2206523 | 67928 |  | 67928 | 2206523 | 0 | 3
|  |  |  | 22-01-00-00-01 | Division 01 - General Requirements | 0 | 0 | 6202 | 1457 | 0 | 7659 | -7659 | 3149 |  | 3149 | -3149 | 4510 | 0
|  | Total 100690-lddc-0020 |  |  |  | 3617393 | 4471585 | 6202 | 260443 | 0 | 266645 | 4204940 | 262135 |  | 262135 | 4209450 | 4510 | 6
|  | 100690-lddc-0021 | Community 11 Parcel I2 - Dev | 20-02-23-00-01 | General Contractor-Offsite Infrastructure | 977702 | 1329844 | 0 | 115640 | 0 | 115640 | 1214204 | 115640 |  | 115640 | 1214204 | 0 | 9
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 1272428 | 1580201 | 0 | 43080 | 0 | 43080 | 1537121 | 43080 |  | 43080 | 1537121 | 0 | 3
|  |  |  | 22-01-00-00-01 | Division 01 - General Requirements | 0 | 0 | 3790 | 890 | 0 | 4680 | -4680 | 1924 |  | 1924 | -1924 | 2756 | 0
|  | Total 100690-lddc-0021 |  |  |  | 2250130 | 2910045 | 3790 | 159610 | 0 | 163400 | 2746645 | 160644 |  | 160644 | 2749401 | 2756 | 6
|  | 100690-lddc-0022 | Community 11 Parcel J - Dev | 20-02-12-10-04 | Environmental Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-50-26 | Silt Fence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-lddc-0022 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-lddc-0036 | Community 7 Parcel 1 (Legacy) | 20-02-21-45-04 | Performance Bonds | 0 | 3438 | 0 | -3438 | 0 | -3438 | 6876 | -3438 |  | -3438 | 6876 | 0 | -100
|  |  |  | 20-02-21-50-26 | Silt Fence | 7500 | 1475 | 1475 | 0 | 0 | 1475 | 0 | 1475 |  | 1475 | 0 | 0 | 100
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 0 | 106330 | 106330 | 0 | 0 | 106330 | 0 | 105768 |  | 105768 | 562 | 562 | 99
|  | Total 100690-lddc-0036 |  |  |  | 7500 | 111243 | 107805 | -3438 | 0 | 104367 | 6876 | 103805 |  | 103805 | 7438 | 562 | 93
|  | 100690-lddc-0037 | Community 9 Parcel 22 (Legacy) | 20-02-12-10-07 | Engineering Studies | 5000 | 5550 | 4500 | 1050 | 0 | 5550 | 0 | 5550 |  | 5550 | 0 | 0 | 100
|  |  |  | 20-02-12-10-08 | Engineering Testing | 860 | 860 | 0 | 860 | 0 | 860 | 0 | 860 |  | 860 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 4080 | 4080 | 4080 | 0 | 0 | 4080 | 0 | 4080 |  | 4080 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 940 | 940 | 0 | 940 | 0 | 940 | 0 | 940 |  | 940 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 1579 | 3055 | 0 | 3055 | 0 | 3055 | 0 | 3055 |  | 3055 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 6518 | 3018 | 0 | 3018 | 0 | 3018 | 0 | 3018 |  | 3018 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 721 | 721 | 0 | 721 | 0 | 721 | 0 | 721 |  | 721 | 0 | 0 | 100
|  |  |  | 20-02-21-50-24 | Erosion Control | 206 | 206 | 0 | 206 | 0 | 206 | 0 | 206 |  | 206 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 6588 | 500 | 500 | 0 | 0 | 500 | 0 | 500 |  | 500 | 0 | 0 | 100
|  |  |  | 20-02-21-60-02 | Paving | 3563 | 3563 | 0 | 3563 | 0 | 3563 | 0 | 3563 |  | 3563 | 0 | 0 | 100
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 0 | 207147 | 204953 | 3305 | 0 | 208258 | -1111 | 207793 |  | 207793 | -646 | 465 | 100
|  |  |  | 20-02-22-00-02 | Sewer Collection | 819 | 819 | 0 | 819 | 0 | 819 | 0 | 819 |  | 819 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 81759 | 81759 | 80166 | 1593 | 0 | 81759 | 0 | 81759 |  | 81759 | 0 | 0 | 100
|  |  |  | 20-02-22-40-12 | Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-60-02 | Play/Tot Lot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-60-07 | Outdoor Furnishings | 318 | 318 | 0 | 318 | 0 | 318 | 0 | 318 |  | 318 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-lddc-0037 |  |  |  | 117951 | 312536 | 294199 | 19448 | 0 | 313647 | -1111 | 313182 |  | 313182 | -646 | 465 | 100
|  | 100690-lddc-0038 | Community 9 Parcel 28 & 30 | 20-02-12-10-05 | Geotechnical Studies | 13360 | 11360 | 11360 | 0 | 0 | 11360 | 0 | 11360 |  | 11360 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 12287 | 13247 | 12878 | 369 | 0 | 13247 | 0 | 13247 |  | 13247 | 0 | 0 | 100
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 240 | 321 | 0 | 321 | 0 | 321 | 0 | 321 |  | 321 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 2750 | 5550 | 5550 | 0 | 0 | 5550 | 0 | 5550 |  | 5550 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 25920 | 13205 | 13205 | 0 | 0 | 13205 | 0 | 13205 |  | 13205 | 0 | 0 | 100
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 2706 | 2600 | 0 | 0 | 2600 | 106 | 2706 |  | 2706 | 0 | -106 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 5825 | 6890 | 0 | 6890 | 0 | 6890 | 0 | 6890 |  | 6890 | 0 | 0 | 100
|  |  |  | 20-02-21-40-02 | Inspection Fees | 2422 | 2422 | 0 | 2422 | 0 | 2422 | 0 | 2422 |  | 2422 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 526 | 7296 | 0 | 4041 | 0 | 4041 | 3255 | 4041 |  | 4041 | 3255 | 0 | 55
|  |  |  | 20-02-21-45-04 | Performance Bonds | 15718 | 40328 | 0 | 34840 | 0 | 34840 | 5488 | 34840 |  | 34840 | 5488 | 0 | 86
|  |  |  | 20-02-21-50-19 | Grading & Fill | 107172 | 101671 | 99458 | 2214 | 0 | 101671 | 0 | 101671 |  | 101671 | 0 | 0 | 100
|  |  |  | 20-02-21-50-24 | Erosion Control | 111548 | 91548 | 88845 | 2703 | 0 | 91548 | 0 | 91548 |  | 91548 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 24245 | 4650 | 4650 | 0 | 0 | 4650 | 0 | 4650 |  | 4650 | 0 | 0 | 100
|  |  |  | 20-02-21-60-02 | Paving | 607678 | 626245 | 618485 | 6199 | 0 | 624684 | 1561 | 626245 |  | 626245 | 0 | -1561 | 100
|  |  |  | 20-02-21-60-04 | Street Lights | 58739 | 66634 | 66634 | 0 | 0 | 66634 | 0 | 66634 |  | 66634 | 0 | 0 | 100
|  |  |  | 20-02-21-60-06 | Curb & Gutter | 957974 | 962784 | 962784 | 0 | 0 | 962784 | 0 | 962784 |  | 962784 | 0 | 0 | 100
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 0 | 5433 | 0 | 5397 | 0 | 5397 | 36 | 5397 |  | 5397 | 36 | 0 | 99
|  |  |  | 20-02-21-80-01 | Water Trunk System | 47266 | 38233 | 28419 | 9814 | 0 | 38233 | 0 | 38233 |  | 38233 | 0 | 0 | 100
|  |  |  | 20-02-22-00-02 | Sewer Collection | 25445 | 22945 | 22945 | 0 | 0 | 22945 | 0 | 22945 |  | 22945 | 0 | 0 | 100
|  |  |  | 20-02-22-10-01 | Storm Drainage System | 295807 | 284153 | 280807 | 3346 | 0 | 284153 | 0 | 284153 |  | 284153 | 0 | 0 | 100
|  |  |  | 20-02-22-20-01 | Dry-Underground Utilities | 125924 | 97800 | 97800 | 0 | 0 | 97800 | 0 | 97800 |  | 97800 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 528791 | 652147 | 667725 | 153 | 0 | 667878 | -15731 | 661276 |  | 661276 | -9129 | 6602 | 101
|  |  |  | 20-02-22-40-12 | Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-60-02 | Play/Tot Lot | 92960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-60-07 | Outdoor Furnishings | 25362 | 25363 | 25363 | 0 | 0 | 25363 | 0 | 25363 |  | 25363 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 15000 | 43348 | 16000 | 0 | 0 | 16000 | 27348 | 43348 |  | 43348 | 0 | -27348 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 20000 | 40013 | 0 | 0 | 0 | 0 | 40013 | 0 |  | 0 | 40013 | 0 | 0
|  | Total 100690-lddc-0038 |  |  |  | 3122959 | 3166292 | 3025508 | 78709 | 0 | 3104216 | 62076 | 3126629 |  | 3126629 | 39663 | -22413 | 99
|  | 100690-lddc-0039 | Community 9 Parcel 29 & Great Lawn | 20-02-12-10-05 | Geotechnical Studies | 3861 | 3861 | 3861 | 0 | 0 | 3861 | 0 | 3861 |  | 3861 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 3660 | 6228 | 6228 | 0 | 0 | 6228 | 0 | 6228 |  | 6228 | 0 | 0 | 100
|  |  |  | 20-02-12-10-13 | Other Studies-Consultants | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-02 | Final Landscape | 2200 | 9100 | 9100 | 0 | 0 | 9100 | 0 | 9100 |  | 9100 | 0 | 0 | 100
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 1000 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 2755 | 2755 | 2755 | 0 | 0 | 2755 | 0 | 2755 |  | 2755 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 0 | 4000 | 4000 | 0 | 0 | 4000 | 0 | 4000 |  | 4000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 90 | 0 | 90 | 0 | 90 | 0 | 90 |  | 90 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 25824 | 26714 | 0 | 26714 | 0 | 26714 | 0 | 26714 |  | 26714 | 0 | 0 | 100
|  |  |  | 20-02-21-40-02 | Inspection Fees | 16650 | 16650 | 0 | 16650 | 0 | 16650 | 0 | 16650 |  | 16650 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 5045 | 6027 | 0 | 6027 | 0 | 6027 | 0 | 6027 |  | 6027 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 0 | 0 | 0 | 448 | 0 | 448 | -448 | 448 |  | 448 | -448 | 0 | 0
|  |  |  | 20-02-21-50-18 | Rock Blasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-50-26 | Silt Fence | 2750 | 2750 | 2500 | 250 | 0 | 2750 | 0 | 2750 |  | 2750 | 0 | 0 | 100
|  |  |  | 20-02-21-60-02 | Paving | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 0 | 26460 | 26110 | 350 | 0 | 26460 | 0 | 1675 |  | 1675 | 24785 | 24785 | 6
|  |  |  | 20-02-21-80-01 | Water Trunk System | 295399 | 295399 | 295399 | 0 | 0 | 295399 | 0 | 295399 |  | 295399 | 0 | 0 | 100
|  |  |  | 20-02-22-00-02 | Sewer Collection | 193681 | 193681 | 193681 | 0 | 0 | 193681 | 0 | 193681 |  | 193681 | 0 | 0 | 100
|  |  |  | 20-02-22-10-01 | Storm Drainage System | 35429 | 35429 | 35429 | 0 | 0 | 35429 | 0 | 35429 |  | 35429 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-60-02 | Play/Tot Lot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 13067 | 4800 | 8267 | 0 | 13067 | 0 | 13067 |  | 13067 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 0 | 8890 | 0 | 0 | 0 | 0 | 8890 | 0 |  | 0 | 8890 | 0 | 0
|  | Total 100690-lddc-0039 |  |  |  | 592254 | 652101 | 584863 | 58796 | 0 | 643659 | 8442 | 618874 |  | 618874 | 33227 | 24785 | 95
|  | 100690-lddc-0046 | Community 9 Parcel 43 (Legacy) | 20-02-12-10-05 | Geotechnical Studies | 9015 | 9015 | 9015 | 0 | 0 | 9015 | 0 | 9015 |  | 9015 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 25920 | 25289 | 24920 | 369 | 0 | 25289 | 0 | 25289 |  | 25289 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 0 | 2800 | 2800 | 0 | 0 | 2800 | 0 | 2800 |  | 2800 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 16400 | 15710 | 15710 | 0 | 0 | 15710 | 0 | 15710 |  | 15710 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 4050 | 4400 | 0 | 4400 | 0 | 4400 | 0 | 4400 |  | 4400 | 0 | 0 | 100
|  |  |  | 20-02-21-40-02 | Inspection Fees | 2610 | 2610 | 0 | 2610 | 0 | 2610 | 0 | 2610 |  | 2610 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 3342 | 8032 | 0 | 8032 | 0 | 8032 | 0 | 8032 |  | 8032 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 1930 | 4899 | 0 | 4899 | 0 | 4899 | 0 | 4899 |  | 4899 | 0 | 0 | 100
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 9300 | 7286 | 7286 | 0 | 0 | 7286 | 0 | 7286 |  | 7286 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 110101 | 105301 | 110101 | -4800 | 0 | 105301 | 0 | 105301 |  | 105301 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 5845 | 5845 | 4775 | 1070 | 0 | 5845 | 0 | 5845 |  | 5845 | 0 | 0 | 100
|  |  |  | 20-02-21-60-02 | Paving | 214875 | 214875 | 211728 | 3147 | 0 | 214875 | 0 | 214875 |  | 214875 | 0 | 0 | 100
|  |  |  | 20-02-21-60-04 | Street Lights | 7384 | 7384 | 7384 | 0 | 0 | 7384 | 0 | 7384 |  | 7384 | 0 | 0 | 100
|  |  |  | 20-02-21-60-06 | Curb & Gutter | 45229 | 34153 | 34153 | 0 | 0 | 34153 | 0 | 34153 |  | 34153 | 0 | 0 | 100
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 20000 | 38686 | 14670 | 24016 | 0 | 38686 | 0 | 38686 |  | 38686 | 0 | 0 | 100
|  |  |  | 20-02-22-10-01 | Storm Drainage System | 128731 | 175446 | 175446 | 0 | 0 | 175446 | 0 | 175446 |  | 175446 | 0 | 0 | 100
|  |  |  | 20-02-22-20-01 | Dry-Underground Utilities | 16319 | 16319 | 16319 | 0 | 0 | 16319 | 0 | 16319 |  | 16319 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 336849 | 336849 | 348391 | 0 | 0 | 348391 | -11542 | 348391 |  | 348391 | -11542 | 0 | 103
|  |  |  | 20-02-22-40-12 | Walls | 52962 | 52962 | 52962 | 0 | 0 | 52962 | 0 | 52962 |  | 52962 | 0 | 0 | 100
|  |  |  | 20-02-22-60-07 | Outdoor Furnishings | 138653 | 105901 | 105242 | 659 | 0 | 105901 | 0 | 105901 |  | 105901 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 12000 | 9672 | 9672 | 0 | 0 | 9672 | 0 | 9672 |  | 9672 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 0 | 32639 | 0 | 0 | 0 | 0 | 32639 | 0 |  | 0 | 32639 | 0 | 0
|  | Total 100690-lddc-0046 |  |  |  | 1161515 | 1216073 | 1150574 | 44402 | 0 | 1194976 | 21097 | 1194976 |  | 1194976 | 21097 | 0 | 98
|  | 100690-lddc-0048 | Community 12 Parcel 23A (Legacy) | 20-02-12-10-05 | Geotechnical Studies | 800 | 800 | 800 | 0 | 0 | 800 | 0 | 800 |  | 800 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 4123 | 4123 | 2500 | 1623 | 0 | 4123 | 0 | 4123 |  | 4123 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 8580 | 3000 | 3000 | 0 | 0 | 3000 | 0 | 3000 |  | 3000 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 175 | 175 | 0 | 175 | 0 | 175 | 0 | 175 |  | 175 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 1918 | 9298 | 0 | 9298 | 0 | 9298 | 0 | 9298 |  | 9298 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 6283 | 11953 | 0 | 11953 | 0 | 11953 | 0 | 11953 |  | 11953 | 0 | 0 | 100
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 10601 | 8258 | 8258 | 0 | 0 | 8258 | 0 | 8258 |  | 8258 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 32774 | 32774 | 23676 | 9098 | 0 | 32774 | 0 | 32774 |  | 32774 | 0 | 0 | 100
|  |  |  | 20-02-21-50-24 | Erosion Control | 3810 | 3810 | 3810 | 0 | 0 | 3810 | 0 | 3810 |  | 3810 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 6262 | 6262 | 6262 | 0 | 0 | 6262 | 0 | 6262 |  | 6262 | 0 | 0 | 100
|  |  |  | 20-02-21-60-02 | Paving | 17568 | 15679 | 15679 | 0 | 0 | 15679 | 0 | 15679 |  | 15679 | 0 | 0 | 100
|  |  |  | 20-02-21-60-06 | Curb & Gutter | 14927 | 358 | 358 | 0 | 0 | 358 | 0 | 358 |  | 358 | 0 | 0 | 100
|  |  |  | 20-02-21-80-01 | Water Trunk System | 45510 | 4510 | 4510 | 0 | 0 | 4510 | 0 | 4510 |  | 4510 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 109015 | 109015 | 109015 | 0 | 0 | 109015 | 0 | 109015 |  | 109015 | 0 | 0 | 100
|  |  |  | 20-02-22-40-12 | Walls | 21119 | 31529 | 21010 | 10519 | 0 | 31529 | 0 | 31529 |  | 31529 | 0 | 0 | 100
|  |  |  | 20-02-22-60-02 | Play/Tot Lot | 0 | 35832 | 35832 | 0 | 0 | 35832 | 0 | 35832 |  | 35832 | 0 | 0 | 100
|  |  |  | 20-02-22-60-07 | Outdoor Furnishings | 47806 | 52374 | 52374 | 0 | 0 | 52374 | 0 | 52374 |  | 52374 | 0 | 0 | 100
|  |  |  | 22-31-22-00-00 | Grading | 0 | 15172 | 9889 | 5283 | 0 | 15172 | 0 | 15172 |  | 15172 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 25000 | 12627 | 0 | 0 | 0 | 0 | 12627 | 0 |  | 0 | 12627 | 0 | 0
|  | Total 100690-lddc-0048 |  |  |  | 356271 | 357549 | 296973 | 47949 | 0 | 344922 | 12627 | 344922 |  | 344922 | 12627 | 0 | 96
|  | 100690-lddc-0050 | Community 12 Parcel 24 (Legacy) | 20-02-12-10-05 | Geotechnical Studies | 10400 | 10405 | 10405 | 0 | 0 | 10405 | 0 | 10405 |  | 10405 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 3025 | 5123 | 5000 | 123 | 0 | 5123 | 0 | 5123 |  | 5123 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 13100 | 4565 | 4565 | 0 | 0 | 4565 | 0 | 4565 |  | 4565 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 0 | 350 | 0 | 350 | 0 | 350 | 0 | 350 |  | 350 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 0 | 10572 | 0 | 6644 | 0 | 6644 | 3928 | 6644 |  | 6644 | 3928 | 0 | 63
|  |  |  | 20-02-21-45-04 | Performance Bonds | 0 | 15800 | 0 | 15800 | 0 | 15800 | 0 | 15800 |  | 15800 | 0 | 0 | 100
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 9000 | 6561 | 6561 | 0 | 0 | 6561 | 0 | 6561 |  | 6561 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 125000 | 106432 | 96834 | 9598 | 0 | 106432 | 0 | 106432 |  | 106432 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 1200 | 2625 | 2625 | 0 | 0 | 2625 | 0 | 2625 |  | 2625 | 0 | 0 | 100
|  |  |  | 20-02-21-60-02 | Paving | 400000 | 24913 | 24913 | 0 | 0 | 24913 | 0 | 24913 |  | 24913 | 0 | 0 | 100
|  |  |  | 20-02-21-60-04 | Street Lights | 16000 | 6540 | 6540 | 0 | 0 | 6540 | 0 | 6540 |  | 6540 | 0 | 0 | 100
|  |  |  | 20-02-21-60-06 | Curb & Gutter | 120000 | 97738 | 104275 | -6537 | 0 | 97738 | 0 | 97738 |  | 97738 | 0 | 0 | 100
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 35488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-80-01 | Water Trunk System | 14500 | 9020 | 9020 | 0 | 0 | 9020 | 0 | 9020 |  | 9020 | 0 | 0 | 100
|  |  |  | 20-02-22-00-02 | Sewer Collection | 4900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-10-01 | Storm Drainage System | 0 | 27683 | 27683 | 0 | 0 | 27683 | 0 | 27683 |  | 27683 | 0 | 0 | 100
|  |  |  | 20-02-22-20-01 | Dry-Underground Utilities | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-01 | Landscaping | 300000 | 352722 | 363602 | 0 | 0 | 363602 | -10880 | 363602 |  | 363602 | -10880 | 0 | 103
|  |  |  | 20-02-22-40-12 | Walls | 250000 | 254120 | 246675 | 7445 | 0 | 254120 | 0 | 254120 |  | 254120 | 0 | 0 | 100
|  |  |  | 20-02-22-60-07 | Outdoor Furnishings | 125000 | 99472 | 95066 | 4405 | 0 | 99472 | 0 | 99472 |  | 99472 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 6351 | 6351 | 0 | 0 | 6351 | 0 | 6351 |  | 6351 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 199809 | 22600 | 0 | 0 | 0 | 0 | 22600 | 0 |  | 0 | 22600 | 0 | 0
|  | Total 100690-lddc-0050 |  |  |  | 1635822 | 1063592 | 1010115 | 37828 | 0 | 1047944 | 15648 | 1047944 |  | 1047944 | 15648 | 0 | 99
|  | 100690-lddc-0078 | Community 9 Parcel 1 (Lagecy) | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 1524 | 1524 | 0 | 1524 | 0 | 1524 | 0 | 1524 |  | 1524 | 0 | 0 | 100
|  | Total 100690-lddc-0078 |  |  |  | 1524 | 1524 | 0 | 1524 | 0 | 1524 | 0 | 1524 |  | 1524 | 0 | 0 | 100
|  | 100690-lddc-0080 | Community 9 Parcel 8 (Legacy) | 20-02-22-40-12 | Walls | 61000 | 70264 | 70264 | 0 | 0 | 70264 | 0 | 70264 |  | 70264 | 0 | 0 | 100
|  | Total 100690-lddc-0080 |  |  |  | 61000 | 70264 | 70264 | 0 | 0 | 70264 | 0 | 70264 |  | 70264 | 0 | 0 | 100
|  | 100690-lddc-0085 | Community 9 Parcel 27A - Dev | 25-02-59-91-03 | Contingency - Development | 529933 | 529933 | 0 | 0 | 0 | 0 | 529933 | 0 |  | 0 | 529933 | 0 | 0
|  |  |  | 25-02-59-91-90 | Contingency-Other | 500 | 500 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 | 500 | 0 | 0
|  | Total 100690-lddc-0085 |  |  |  | 530433 | 530433 | 0 | 0 | 0 | 0 | 530433 | 0 |  | 0 | 530433 | 0 | 0
|  | 100690-lddc-0201 | Community 11 Parcel H (OTAGO) | 20-02-23-00-02 | General Contractor-Onsite Development | 2864371 | 2498177 | 2470044 | 28132 | 0 | 2498177 | 0 | 2498177 |  | 2498177 | 0 | 0 | 100
|  | Total 100690-lddc-0201 |  |  |  | 2864371 | 2498177 | 2470044 | 28132 | 0 | 2498177 | 0 | 2498177 |  | 2498177 | 0 | 0 | 100
|  | 100690-lddc-0202 | Community 9 Parcel 29 (OTAGO) | 20-02-23-00-02 | General Contractor-Onsite Development | 3443728 | 3593328 | 3443728 | 28470 | 0 | 3472198 | 121130 | 3593328 |  | 3593328 | 0 | -121130 | 100
|  | Total 100690-lddc-0202 |  |  |  | 3443728 | 3593328 | 3443728 | 28470 | 0 | 3472198 | 121130 | 3593328 |  | 3593328 | 0 | -121130 | 100
|  | 100690-lddc-0203 | Community 12 Parcel 23B (OTAGO) | 20-02-23-00-02 | General Contractor-Onsite Development | 4642050 | 4642050 | 4642050 | -441453 | 0 | 4200596 | 441454 | 4200596 |  | 4200596 | 441454 | 0 | 90
|  | Total 100690-lddc-0203 |  |  |  | 4642050 | 4642050 | 4642050 | -441453 | 0 | 4200596 | 441454 | 4200596 |  | 4200596 | 441454 | 0 | 90
|  | 100690-lddc-0204 | Sendero Dr Ph2 (OTAGO) | 20-02-23-00-02 | General Contractor-Onsite Development | 595589 | 545637 | 595589 | 0 | 0 | 595589 | -49952 | 395302 |  | 395302 | 150335 | 200287 | 72
|  | Total 100690-lddc-0204 |  |  |  | 595589 | 545637 | 595589 | 0 | 0 | 595589 | -49952 | 395302 |  | 395302 | 150335 | 200287 | 72
|  | 100690-ldlj-0349 | General Land Job | 20-02-11-10-01 | Purchase Price | 0 | 0 | 0 | 153821815 | 0 | 153821815 | -153821815 | 153821815 |  | 153821815 | -153821815 | 0 | 0
|  | Total 100690-ldlj-0349 |  |  |  | 0 | 0 | 0 | 153821815 | 0 | 153821815 | -153821815 | 153821815 |  | 153821815 | -153821815 | 0 | 0
|  | 100690-ldmp-0002 | Community 11 South Planning | 20-02-12-10-07 | Engineering Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-01 | Land Planning | 648450 | 648450 | 0 | 0 | 0 | 0 | 648450 | 0 |  | 0 | 648450 | 0 | 0
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 72050 | 72050 | 0 | 0 | 0 | 0 | 72050 | 0 |  | 0 | 72050 | 0 | 0
|  | Total 100690-ldmp-0002 |  |  |  | 720500 | 720500 | 0 | 0 | 0 | 0 | 720500 | 0 |  | 0 | 720500 | 0 | 0
|  | 100690-ldmp-0014 | Comm 11 Parcel D2 &D3 - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 0 | 0 | 4000 | 0 | 0 | 4000 | -4000 | 4000 |  | 4000 | -4000 | 0 | 0
|  |  |  | 20-02-12-10-06 | Geotechnical Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-02 | Final Landscape | 23500 | 23500 | 23500 | 0 | 0 | 23500 | 0 | 0 |  | 0 | 23500 | 23500 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 104400 | 104400 | 185200 | 0 | 0 | 185200 | -80800 | 115922 |  | 115922 | -11522 | 69278 | 111
|  |  |  | 20-02-12-20-08 | Structural Engineering | 12000 | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 |  | 0 | 12000 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 4000 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 |  | 0 | 4000 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 5000 | 5000 | 10533 | 0 | 0 | 10533 | -5533 | 0 |  | 0 | 5000 | 10533 | 0
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 3150 | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 |  | 0 | 3150 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 6500 | 6500 | 6500 | 0 | 0 | 6500 | 0 | 4050 |  | 4050 | 2450 | 2450 | 62
|  |  |  | 20-02-12-20-24 | Final Engineering | 130100 | 130100 | 295400 | 0 | 0 | 295400 | -165300 | 21320 |  | 21320 | 108780 | 274080 | 16
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 0 | 0 | 483 | 0 | 483 | -483 | 483 |  | 483 | -483 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 45000 | 45000 | 0 | 4853 | 0 | 4853 | 40147 | 4853 |  | 4853 | 40147 | 0 | 11
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 14050 | 14050 | 0 | 2750 | 0 | 2750 | 11300 | 2750 |  | 2750 | 11300 | 0 | 20
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 34770 | 34770 | 0 | 0 | 0 | 0 | 34770 | 0 |  | 0 | 34770 | 0 | 0
|  | Total 100690-ldmp-0014 |  |  |  | 382470 | 382470 | 525133 | 8086 | 0 | 533219 | -150749 | 153378 |  | 153378 | 229092 | 379841 | 40
|  | 100690-ldmp-0015 | Community 11 Parcel E - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 38450 | 6710 | 6710 | 0 | 0 | 6710 | 0 | 6710 |  | 6710 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 97546 | 98913 | 93755 | 5158 | 0 | 98913 | 0 | 98913 |  | 98913 | 0 | 0 | 100
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 93 | 93 | 0 | 93 | 0 | 93 | 0 | 93 |  | 93 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 13704 | 14154 | 13704 | 450 | 0 | 14154 | 0 | 9004 |  | 9004 | 5150 | 5150 | 64
|  |  |  | 20-02-12-20-04 | Staking | 58000 | 7500 | 7500 | 0 | 0 | 7500 | 0 | 7500 |  | 7500 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 1500 | 4000 | 4000 | 0 | 0 | 4000 | 0 | 3875 |  | 3875 | 125 | 125 | 97
|  |  |  | 20-02-21-40-01 | Municipality Fees | 3127 | 5327 | 0 | 30137 | 0 | 30137 | -24810 | 30137 |  | 30137 | -24810 | 0 | 566
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 70205 | 70205 | 70205 | 0 | 0 | 70205 | 0 | 70205 |  | 70205 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 309589 | 264949 | 264949 | 0 | 0 | 264949 | 0 | 264949 |  | 264949 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 1181113 | 1122161 | 1122161 | 0 | 0 | 1122161 | 0 | 1122161 |  | 1122161 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 36373 | 10875 | 10875 | 0 | 0 | 10875 | 0 | 10688 |  | 10688 | 187 | 187 | 98
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 44639 | 34737 | 19780 | 14957 | 0 | 34737 | 0 | 34737 |  | 34737 | 0 | 0 | 100
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 |  | 0 | 25000 | 0 | 0
|  | Total 100690-ldmp-0015 |  |  |  | 1854339 | 1664624 | 1613639 | 50795 | 0 | 1664434 | 190 | 1658972 |  | 1658972 | 5652 | 5462 | 100
|  | 100690-ldmp-0016 | Community 11 Parcel F1 - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 26850 | 7830 | 7830 | 0 | 0 | 7830 | 0 | 7830 |  | 7830 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 50693 | 50207 | 45048 | 5158 | 0 | 50207 | 0 | 50207 |  | 50207 | 0 | 0 | 100
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 853 | 853 | 0 | 853 | 0 | 853 | 0 | 853 |  | 853 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 9775 | 10675 | 9775 | 450 | 0 | 10225 | 450 | 10675 |  | 10675 | 0 | -450 | 100
|  |  |  | 20-02-12-20-04 | Staking | 38385 | 5000 | 5000 | 0 | 0 | 5000 | 0 | 5000 |  | 5000 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 3127 | 5402 | 0 | 36253 | 0 | 36253 | -30851 | 36253 |  | 36253 | -30851 | 0 | 671
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 81473 | 81473 | 81473 | 0 | 0 | 81473 | 0 | 81473 |  | 81473 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 23518 | 1650 | 1650 | 0 | 0 | 1650 | 0 | 1650 |  | 1650 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 1354874 | 1354874 | 1354874 | 0 | 0 | 1354874 | 0 | 1354874 |  | 1354874 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 44160 | 6894 | 6894 | 0 | 0 | 6894 | 0 | 6706 |  | 6706 | 188 | 188 | 97
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 37329 | 27399 | 12470 | 14929 | 0 | 27399 | 0 | 27399 |  | 27399 | 0 | 0 | 100
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 |  | 0 | 25000 | 0 | 0
|  | Total 100690-ldmp-0016 |  |  |  | 1671037 | 1577257 | 1525014 | 57643 | 0 | 1582658 | -5401 | 1582920 |  | 1582920 | -5663 | -262 | 100
|  | 100690-ldmp-0020 | Community 11 Parcel I1 - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 18100 | 6280 | 6280 | 0 | 0 | 6280 | 0 | 6280 |  | 6280 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 26714 | 20741 | 17962 | 4379 | 0 | 22341 | -1600 | 22341 |  | 22341 | -1600 | 0 | 108
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 17 | 17 | 0 | 133 | 0 | 133 | -116 | 133 |  | 133 | -116 | 0 | 782
|  |  |  | 20-02-12-20-02 | Final Landscape | 6212 | 9062 | 6212 | 450 | 0 | 6662 | 2400 | 9062 |  | 9062 | 0 | -2400 | 100
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 4492 | 2543 | 4492 | 0 | 0 | 4492 | -1949 | 3652 |  | 3652 | -1109 | 840 | 144
|  |  |  | 20-02-12-20-04 | Staking | 27100 | 4400 | 4400 | 0 | 0 | 4400 | 0 | 4400 |  | 4400 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 0 | 800 | 800 | 0 | 0 | 800 | 0 | 760 |  | 760 | 40 | 40 | 95
|  |  |  | 20-02-21-40-01 | Municipality Fees | 3127 | 3552 | 0 | 28547 | 0 | 28547 | -24995 | 28547 |  | 28547 | -24995 | 0 | 804
|  |  |  | 20-02-21-40-02 | Inspection Fees | 700 | 700 | 0 | 700 | 0 | 700 | 0 | 700 |  | 700 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 583 | 1166 | 0 | 1166 | 0 | 1166 | 0 | 1166 |  | 1166 | 0 | 0 | 100
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 61624 | 61624 | 61624 | 0 | 0 | 61624 | 0 | 61624 |  | 61624 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 23518 | -128 | 1650 | -1778 | 0 | -128 | 0 | -128 |  | -128 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 421601 | 394205 | 394205 | 0 | 0 | 394205 | 0 | 394205 |  | 394205 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 29286 | 6607 | 6607 | 0 | 0 | 6607 | 0 | 6420 |  | 6420 | 187 | 187 | 97
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 40439 | 31529 | 15580 | 15949 | 0 | 31529 | 0 | 31529 |  | 31529 | 0 | 0 | 100
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 |  | 0 | 25000 | 0 | 0
|  | Total 100690-ldmp-0020 |  |  |  | 663513 | 568098 | 519812 | 49546 | 0 | 569358 | -1260 | 570691 |  | 570691 | -2593 | -1333 | 100
|  | 100690-ldmp-0021 | Community 11 Parcel I2 - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 15500 | 4300 | 4300 | 0 | 0 | 4300 | 0 | 4300 |  | 4300 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 17444 | 15531 | 11152 | 4379 | 0 | 15531 | 0 | 15531 |  | 15531 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 1500 | 1950 | 1500 | 450 | 0 | 1950 | 0 | 1950 |  | 1950 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 23100 | 4415 | 4415 | 0 | 0 | 4415 | 0 | 4415 |  | 4415 | 0 | 0 | 100
|  |  |  | 20-02-12-20-24 | Final Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 3222 | 4747 | 0 | 22321 | 0 | 22321 | -17574 | 22321 |  | 22321 | -17574 | 0 | 470
|  |  |  | 20-02-21-40-02 | Inspection Fees | 550 | 550 | 0 | 550 | 0 | 550 | 0 | 550 |  | 550 | 0 | 0 | 100
|  |  |  | 20-02-21-50-03 | Demolition-Razing | 23984 | 23984 | 23984 | 0 | 0 | 23984 | 0 | 23984 |  | 23984 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 0 | -2627 | 0 | -2627 | 0 | -2627 | 0 | -2627 |  | -2627 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 164683 | 158376 | 158376 | 0 | 0 | 158376 | 0 | 158376 |  | 158376 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 23528 | 7130 | 6780 | 350 | 0 | 7130 | 0 | 6942 |  | 6942 | 188 | 188 | 97
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 34289 | 24359 | 9430 | 14929 | 0 | 24359 | 0 | 24359 |  | 24359 | 0 | 0 | 100
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 |  | 0 | 25000 | 0 | 0
|  | Total 100690-ldmp-0021 |  |  |  | 307800 | 267715 | 219937 | 40352 | 0 | 260289 | 7426 | 260101 |  | 260101 | 7614 | 188 | 97
|  | 100690-ldmp-0022 | Community 11 Parcel J - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 0 | 0 | 2000 | 0 | 0 | 2000 | -2000 | 2000 |  | 2000 | -2000 | 0 | 0
|  |  |  | 20-02-12-10-06 | Geotechnical Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-10-07 | Engineering Studies | 442846 | 442846 | 65300 | 0 | 0 | 65300 | 377546 | 9975 |  | 9975 | 432871 | 55325 | 2
|  |  |  | 20-02-12-20-01 | Land Planning | 4000 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 |  | 0 | 4000 | 0 | 0
|  |  |  | 20-02-12-20-02 | Final Landscape | 0 | 0 | 56700 | 0 | 0 | 56700 | -56700 | 13490 |  | 13490 | -13490 | 43210 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 1700 | 1700 | 1700 | 0 | 0 | 1700 | 0 | 1700 |  | 1700 | 0 | 0 | 100
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 0 | 0 | 225500 | 0 | 0 | 225500 | -225500 | 72484 |  | 72484 | -72484 | 153016 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 0 | 5267 | 0 | 0 | 5267 | -5267 | 0 |  | 0 | 0 | 5267 | 0
|  |  |  | 20-02-12-20-24 | Final Engineering | 0 | 0 | 168300 | 0 | 0 | 168300 | -168300 | 19620 |  | 19620 | -19620 | 148680 | 0
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 350 | 350 | 0 | 2574 | 0 | 2574 | -2224 | 2574 |  | 2574 | -2224 | 0 | 735
|  |  |  | 20-02-21-40-02 | Inspection Fees | 1104 | 1104 | 0 | 1104 | 0 | 1104 | 0 | 1104 |  | 1104 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 0 | 0 | 7450 | 0 | 0 | 7450 | -7450 | 5425 |  | 5425 | -5425 | 2025 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 0 | 5700 | 0 | 0 | 5700 | -5700 | 5700 |  | 5700 | -5700 | 0 | 0
|  | Total 100690-ldmp-0022 |  |  |  | 450000 | 450000 | 537917 | 3678 | 0 | 541595 | -91595 | 134072 |  | 134072 | 315928 | 407523 | 30
|  | 100690-ldmp-0027 | Community 2 Parcel 45A - Pre Dev | 20-02-12-10-07 | Engineering Studies | 0 | 20498 | 42998 | 0 | 0 | 42998 | -22500 | 26862 |  | 26862 | -6364 | 16136 | 131
|  |  |  | 20-02-12-10-15 | Drainage/ 404 | 0 | 4800 | 4800 | 0 | 0 | 4800 | 0 | 4800 |  | 4800 | 0 | 0 | 100
|  |  |  | 20-02-12-20-01 | Land Planning | 55400 | 65934 | 114500 | 10434 | 0 | 124934 | -59000 | 48574 |  | 48574 | 17360 | 76360 | 74
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 5000 | 6100 | 6100 | 0 | 0 | 6100 | 0 | 6100 |  | 6100 | 0 | 0 | 100
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 10199 | 10199 | 0 | 251 | 0 | 251 | 9948 | 251 |  | 251 | 9948 | 0 | 2
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 100000 | 63069 | 0 | 4678 | 0 | 4678 | 58391 | 4678 |  | 4678 | 58391 | 0 | 7
|  | Total 100690-ldmp-0027 |  |  |  | 170599 | 170600 | 168398 | 15363 | 0 | 183761 | -13161 | 91265 |  | 91265 | 79335 | 92496 | 53
|  | 100690-ldmp-0028 | Community 2 Parcel 48 - Pre Dev | 20-02-12-10-07 | Engineering Studies | 1320 | 3320 | 3320 | 0 | 0 | 3320 | 0 | 1832 |  | 1832 | 1488 | 1488 | 55
|  |  |  | 20-02-12-10-13 | Other Studies-Consultants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-10-14 | Other Studies-Incidentals | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 |  | 0 | 10000 | 0 | 0
|  |  |  | 20-02-12-20-01 | Land Planning | 45000 | 45000 | 32500 | 0 | 0 | 32500 | 12500 | 25105 |  | 25105 | 19895 | 7395 | 56
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 5700 | 12400 | 12400 | 0 | 0 | 12400 | 0 | 12400 |  | 12400 | 0 | 0 | 100
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 40000 | 31300 | 0 | 8187 | 0 | 8187 | 23113 | 8187 |  | 8187 | 23113 | 0 | 26
|  | Total 100690-ldmp-0028 |  |  |  | 102020 | 102020 | 48220 | 8187 | 0 | 56407 | 45613 | 47524 |  | 47524 | 54496 | 8883 | 47
|  | 100690-ldmp-0040 | Community 9 Parcel 39.40 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 1500 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 33675 | 55750 | 55750 | 0 | 0 | 55750 | 0 | 37925 |  | 37925 | 17825 | 17825 | 68
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 3329 | 3329 | 0 | 0 | 3329 | 0 | 3329 |  | 3329 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 5450 | 5450 | 5000 | 0 | 0 | 5000 | 450 | 4340 |  | 4340 | 1110 | 660 | 80
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 4350 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 |  | 20000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 6300 | 6300 | 0 | 0 | 0 | 0 | 6300 | 0 |  | 0 | 6300 | 0 | 0
|  |  |  | 20-02-12-20-24 | Final Engineering | 196241 | 203155 | 203155 | 0 | 0 | 203155 | 0 | 141477 |  | 141477 | 61678 | 61678 | 70
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 2000 | 1000 | 1000 | 109 | 0 | 1109 | -109 | 118 |  | 118 | 882 | 991 | 12
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 10000 | 10000 | 0 | 2062 | 0 | 2062 | 7938 | 2062 |  | 2062 | 7938 | 0 | 21
|  |  |  | 20-02-21-40-01 | Municipality Fees | 50000 | 50000 | 0 | 5212 | 0 | 5212 | 44788 | 5212 |  | 5212 | 44788 | 0 | 10
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 88200 | 44800 | 44800 | 0 | 0 | 44800 | 0 | 25800 |  | 25800 | 19000 | 19000 | 58
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 15412 | 15412 | 0 | 0 | 0 | 0 | 15412 | 0 |  | 0 | 15412 | 0 | 0
|  | Total 100690-ldmp-0040 |  |  |  | 418128 | 416196 | 314034 | 27383 | 0 | 341417 | 74779 | 241263 |  | 241263 | 174933 | 100154 | 58
|  | 100690-ldmp-0041 | Community 9 Parcel 18 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 1000 | 881 | 881 | 0 | 0 | 881 | 0 | 881 |  | 881 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 17400 | 28000 | 28000 | 0 | 0 | 28000 | 0 | 21384 |  | 21384 | 6616 | 6616 | 76
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 4850 | 4850 | 4850 | 0 | 0 | 4850 | 0 | 0 |  | 0 | 4850 | 4850 | 0
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 3329 | 3329 | 0 | 0 | 3329 | 0 | 3329 |  | 3329 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 2650 | 4350 | 4350 | 0 | 0 | 4350 | 0 | 3820 |  | 3820 | 530 | 530 | 88
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 3500 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 |  | 20000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-24 | Final Engineering | 61632 | 63632 | 63632 | 0 | 0 | 63632 | 0 | 65154 |  | 65154 | -1522 | -1522 | 102
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 866 | 0 | 866 | 134 | 866 |  | 866 | 134 | 0 | 87
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 2062 | 0 | 2062 | 2938 | 2062 |  | 2062 | 2938 | 0 | 41
|  |  |  | 20-02-21-40-01 | Municipality Fees | 30000 | 30000 | 0 | 6726 | 0 | 6726 | 23274 | 6726 |  | 6726 | 23274 | 0 | 22
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 26250 | 28000 | 28000 | 0 | 0 | 28000 | 0 | 16125 |  | 16125 | 11875 | 11875 | 58
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 9035 | 9035 | 0 | 0 | 0 | 0 | 9035 | 0 |  | 0 | 9035 | 0 | 0
|  | Total 100690-ldmp-0041 |  |  |  | 167317 | 198077 | 133042 | 29654 | 0 | 162696 | 35381 | 140347 |  | 140347 | 57730 | 22349 | 71
|  | 100690-ldmp-0042 | Community 9 Parcel 21 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 1000 | 7394 | 7394 | 0 | 0 | 7394 | 0 | 7394 |  | 7394 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 18750 | 29350 | 29350 | 0 | 0 | 29350 | 0 | 22669 |  | 22669 | 6681 | 6681 | 77
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 5500 | 5500 | 0 | 0 | 5500 | 0 | 0 |  | 0 | 5500 | 5500 | 0
|  |  |  | 20-02-12-20-08 | Structural Engineering | 0 | 3329 | 3329 | 0 | 0 | 3329 | 0 | 3329 |  | 3329 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 3100 | 4800 | 4800 | 0 | 0 | 4800 | 0 | 4180 |  | 4180 | 620 | 620 | 87
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 3500 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 |  | 20000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-24 | Final Engineering | 88071 | 90524 | 90071 | 452 | 0 | 90524 | 0 | 92277 |  | 92277 | -1753 | -1753 | 102
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 117 | 0 | 117 | 883 | 117 |  | 117 | 883 | 0 | 12
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 2062 | 0 | 2062 | 2938 | 2062 |  | 2062 | 2938 | 0 | 41
|  |  |  | 20-02-21-40-01 | Municipality Fees | 25000 | 18035 | 0 | 7148 | 0 | 7148 | 10887 | 7148 |  | 7148 | 10887 | 0 | 40
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 46200 | 49280 | 49280 | 0 | 0 | 49280 | 0 | 28380 |  | 28380 | 20900 | 20900 | 58
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 10212 | 10212 | 0 | 0 | 0 | 0 | 10212 | 0 |  | 0 | 10212 | 0 | 0
|  | Total 100690-ldmp-0042 |  |  |  | 201833 | 244424 | 189724 | 29779 | 0 | 219504 | 24920 | 187556 |  | 187556 | 56868 | 31948 | 77
|  | 100690-ldmp-0044 | Community 9 Parcel 41 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 1000 | 881 | 881 | 0 | 0 | 881 | 0 | 881 |  | 881 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 22300 | 32900 | 32900 | 0 | 0 | 32900 | 0 | 26108 |  | 26108 | 6792 | 6792 | 79
|  |  |  | 20-02-12-20-08 | Structural Engineering | 0 | 3329 | 3329 | 0 | 0 | 3329 | 0 | 3329 |  | 3329 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 2900 | 4600 | 4600 | 0 | 0 | 4600 | 0 | 4020 |  | 4020 | 580 | 580 | 87
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 3500 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 |  | 20000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-24 | Final Engineering | 86150 | 104070 | 104070 | 0 | 0 | 104070 | 0 | 72373 |  | 72373 | 31697 | 31697 | 70
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 7 | 0 | 7 | 993 | 7 |  | 7 | 993 | 0 | 1
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 2062 | 0 | 2062 | 2938 | 2062 |  | 2062 | 2938 | 0 | 41
|  |  |  | 20-02-21-40-01 | Municipality Fees | 25000 | 25000 | 0 | 3530 | 0 | 3530 | 21470 | 3530 |  | 3530 | 21470 | 0 | 14
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 27300 | 29120 | 29120 | 0 | 0 | 29120 | 0 | 16770 |  | 16770 | 12350 | 12350 | 58
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 14824 | 14824 | 0 | 0 | 0 | 0 | 14824 | 0 |  | 0 | 14824 | 0 | 0
|  | Total 100690-ldmp-0044 |  |  |  | 188974 | 240724 | 174900 | 25599 | 0 | 200499 | 40225 | 149080 |  | 149080 | 91644 | 51419 | 62
|  | 100690-ldmp-0045 | Community 9 Parcel 42 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 1000 | 18481 | 18481 | 0 | 0 | 18481 | 0 | 18481 |  | 18481 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 23990 | 30390 | 30390 | 0 | 0 | 30390 | 0 | 27145 |  | 27145 | 3245 | 3245 | 89
|  |  |  | 20-02-12-20-08 | Structural Engineering | 0 | 3329 | 3329 | 0 | 0 | 3329 | 0 | 3329 |  | 3329 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 3100 | 4800 | 4800 | 0 | 0 | 4800 | 0 | 4180 |  | 4180 | 620 | 620 | 87
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 0 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 |  | 20000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-24 | Final Engineering | 160208 | 196758 | 196758 | 0 | 0 | 196758 | 0 | 196758 |  | 196758 | 0 | 0 | 100
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 46 | 0 | 46 | 954 | 46 |  | 46 | 954 | 0 | 5
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 2062 | 0 | 2062 | 2938 | 2062 |  | 2062 | 2938 | 0 | 41
|  |  |  | 20-02-21-40-01 | Municipality Fees | 25000 | 25000 | 0 | 5927 | 0 | 5927 | 19073 | 5927 |  | 5927 | 19073 | 0 | 24
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 63525 | 67760 | 67760 | 0 | 0 | 67760 | 0 | 39023 |  | 39023 | 28737 | 28737 | 58
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 24025 | 24025 | 0 | 0 | 0 | 0 | 24025 | 0 |  | 0 | 24025 | 0 | 0
|  | Total 100690-ldmp-0045 |  |  |  | 306848 | 396543 | 321518 | 28035 | 0 | 349553 | 46990 | 316951 |  | 316951 | 79592 | 32602 | 80
|  | 100690-ldmp-0049 | Community 12 Parcel 23B- Pre Dev | 20-02-12-10-07 | Engineering Studies | 60000 | 54693 | 54570 | 123 | 0 | 54693 | 0 | 54408 |  | 54408 | 285 | 285 | 99
|  |  |  | 20-02-12-20-04 | Staking | 7100 | 2550 | 2550 | 0 | 0 | 2550 | 0 | 2550 |  | 2550 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 0 | 5175 | 5175 | 0 | 0 | 5175 | 0 | 5175 |  | 5175 | 0 | 0 | 100
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 270 | 0 | 270 | 0 | 270 | 0 | 270 |  | 270 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 5000 | 13769 | 0 | 13769 | 0 | 13769 | 0 | 13769 |  | 13769 | 0 | 0 | 100
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 0 | 694 | 0 | 694 | 0 | 694 | 0 | 694 |  | 694 | 0 | 0 | 100
|  |  |  | 20-02-21-50-24 | Erosion Control | 13964 | 13964 | 13964 | 0 | 0 | 13964 | 0 | 13964 |  | 13964 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 650 | 650 | 650 | 0 | 0 | 650 | 0 | 650 |  | 650 | 0 | 0 | 100
|  |  |  | 20-02-21-60-06 | Curb & Gutter | 873 | 873 | 873 | 0 | 0 | 873 | 0 | 873 |  | 873 | 0 | 0 | 100
|  |  |  | 20-02-22-40-01 | Landscaping | 12929 | 12929 | 12929 | 0 | 0 | 12929 | 0 | 12929 |  | 12929 | 0 | 0 | 100
|  |  |  | 20-02-22-60-07 | Outdoor Furnishings | 41914 | 41417 | 41417 | 0 | 0 | 41417 | 0 | 41417 |  | 41417 | 0 | 0 | 100
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 5777 | 5777 | 0 | 5777 | 0 | 5777 | 0 | 5777 |  | 5777 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 5175 | 19467 | 8800 | 8267 | 0 | 17067 | 2400 | 19467 |  | 19467 | 0 | -2400 | 100
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 3500 | 34213 | 0 | 0 | 0 | 0 | 34213 | 0 |  | 0 | 34213 | 0 | 0
|  | Total 100690-ldmp-0049 |  |  |  | 156882 | 206441 | 140928 | 28900 | 0 | 169828 | 36613 | 171943 |  | 171943 | 34498 | -2115 | 83
|  | 100690-ldmp-0051 | Community 12 Parcel 25 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 16300 | 16300 | 4259 | 0 | 0 | 4259 | 12041 | 3814 |  | 3814 | 12486 | 445 | 23
|  |  |  | 20-02-12-20-01 | Land Planning | 0 | 0 | 1175 | 0 | 0 | 1175 | -1175 | 1166 |  | 1166 | -1166 | 9 | 0
|  |  |  | 20-02-12-20-02 | Final Landscape | 15500 | 15500 | 15500 | 0 | 0 | 15500 | 0 | 12236 |  | 12236 | 3264 | 3264 | 79
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 2400 | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 |  | 0 | 2400 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 85700 | 85700 | 85700 | 0 | 0 | 85700 | 0 | 78900 |  | 78900 | 6800 | 6800 | 92
|  |  |  | 20-02-12-20-08 | Structural Engineering | 7500 | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 |  | 0 | 7500 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 5000 | 5000 | 4600 | 0 | 0 | 4600 | 400 | 4600 |  | 4600 | 400 | 0 | 92
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 6500 | 6500 | 5950 | 0 | 0 | 5950 | 550 | 5355 |  | 5355 | 1145 | 595 | 82
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 3800 | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 |  | 0 | 3800 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 10217 | 10217 | 10217 | 0 | 0 | 10217 | 0 | 10217 |  | 10217 | 0 | 0 | 100
|  |  |  | 20-02-12-20-24 | Final Engineering | 80000 | 80000 | 80000 | 0 | 0 | 80000 | 0 | 61660 |  | 61660 | 18340 | 18340 | 77
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1900 | 1900 | 0 | 567 | 0 | 567 | 1333 | 567 |  | 567 | 1333 | 0 | 30
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 10000 | 10000 | 0 | 46692 | 0 | 46692 | -36692 | 46692 |  | 46692 | -36692 | 0 | 467
|  |  |  | 20-02-21-40-01 | Municipality Fees | 39860 | 39860 | 0 | 10769 | 0 | 10769 | 29091 | 10769 |  | 10769 | 29091 | 0 | 27
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 13460 | 13460 | 54077 | 0 | 0 | 54077 | -40617 | 1583 |  | 1583 | 11877 | 52494 | 12
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 29814 | 29814 | 0 | 0 | 0 | 0 | 29814 | 0 |  | 0 | 29814 | 0 | 0
|  | Total 100690-ldmp-0051 |  |  |  | 327951 | 327951 | 261478 | 58028 | 0 | 319506 | 8445 | 237559 |  | 237559 | 90392 | 81947 | 72
|  | 100690-ldmp-0052 | Community 12 Parcel 36 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 16300 | 16300 | 2241 | 0 | 0 | 2241 | 14059 | 2007 |  | 2007 | 14293 | 234 | 12
|  |  |  | 20-02-12-20-01 | Land Planning | 0 | 0 | 1175 | 0 | 0 | 1175 | -1175 | 1166 |  | 1166 | -1166 | 9 | 0
|  |  |  | 20-02-12-20-02 | Final Landscape | 10000 | 10000 | 10000 | 0 | 0 | 10000 | 0 | 8479 |  | 8479 | 1521 | 1521 | 85
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 2400 | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 |  | 0 | 2400 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 57700 | 57700 | 78600 | 0 | 0 | 78600 | -20900 | 68330 |  | 68330 | -10630 | 10270 | 118
|  |  |  | 20-02-12-20-08 | Structural Engineering | 7500 | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 |  | 0 | 7500 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 5000 | 5000 | 4200 | 0 | 0 | 4200 | 800 | 4200 |  | 4200 | 800 | 0 | 84
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 4400 | 4400 | 5950 | 0 | 0 | 5950 | -1550 | 5355 |  | 5355 | -955 | 595 | 122
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 2000 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 |  | 0 | 2000 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 7417 | 7417 | 10217 | 0 | 0 | 10217 | -2800 | 10217 |  | 10217 | -2800 | 0 | 138
|  |  |  | 20-02-12-20-24 | Final Engineering | 72600 | 72600 | 72600 | 0 | 0 | 72600 | 0 | 58680 |  | 58680 | 13920 | 13920 | 81
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 12 | 0 | 12 | 988 | 12 |  | 12 | 988 | 0 | 1
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 10000 | 10000 | 0 | 46692 | 0 | 46692 | -36692 | 46692 |  | 46692 | -36692 | 0 | 467
|  |  |  | 20-02-21-40-01 | Municipality Fees | 32940 | 32940 | 0 | 4512 | 0 | 4512 | 28428 | 4512 |  | 4512 | 28428 | 0 | 14
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 10400 | 10400 | 44652 | 0 | 0 | 44652 | -34252 | 1583 |  | 1583 | 8817 | 43069 | 15
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 23966 | 23966 | 0 | 0 | 0 | 0 | 23966 | 0 |  | 0 | 23966 | 0 | 0
|  | Total 100690-ldmp-0052 |  |  |  | 263623 | 263623 | 229635 | 51216 | 0 | 280851 | -17228 | 211233 |  | 211233 | 52390 | 69618 | 80
|  | 100690-ldmp-0053 | Community 12 Parcel 41 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 0 | 0 | 3250 | 0 | 0 | 3250 | -3250 | 2907 |  | 2907 | -2907 | 343 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 143550 | 143550 | 18500 | 0 | 0 | 18500 | 125050 | 7410 |  | 7410 | 136140 | 11090 | 5
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 0 | 0 | 0 | 750 | 0 | 750 | -750 | 750 |  | 750 | -750 | 0 | 0
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 15950 | 15950 | 0 | 0 | 0 | 0 | 15950 | 0 |  | 0 | 15950 | 0 | 0
|  | Total 100690-ldmp-0053 |  |  |  | 159500 | 159500 | 21750 | 750 | 0 | 22500 | 137000 | 11067 |  | 11067 | 148433 | 11433 | 7
|  | 100690-ldmp-0055 | Community 12 Parcel 42 - Pre Dev | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 8500 | 8500 | 0 | 0 | 8500 | 0 | 8500 |  | 8500 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 0 | 94 | 0 | 94 | 0 | 94 | 0 | 94 |  | 94 | 0 | 0 | 100
|  | Total 100690-ldmp-0055 |  |  |  | 0 | 8594 | 8500 | 94 | 0 | 8594 | 0 | 8594 |  | 8594 | 0 | 0 | 100
|  | 100690-ldmp-0064 | Community 9 Parcel 7 - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 3500 | 3500 | 3500 | 0 | 0 | 3500 | 0 | 3500 |  | 3500 | 0 | 0 | 100
|  |  |  | 20-02-12-10-15 | Drainage/ 404 | 18000 | 18000 | 18000 | 0 | 0 | 18000 | 0 | 18000 |  | 18000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 43180 | 38600 | 38600 | 0 | 0 | 38600 | 0 | 30472 |  | 30472 | 8128 | 8128 | 79
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 58860 | 58860 | 58860 | 0 | 0 | 58860 | 0 | 58860 |  | 58860 | 0 | 0 | 100
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 3329 | 3329 | 0 | 0 | 3329 | 0 | 3329 |  | 3329 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 3100 | 4800 | 4800 | 0 | 0 | 4800 | 0 | 4800 |  | 4800 | 0 | 0 | 100
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 4553 | 4553 | 4553 | 0 | 0 | 4553 | 0 | 4553 |  | 4553 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 3500 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 |  | 20000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-24 | Final Engineering | 117690 | 117690 | 117690 | 0 | 0 | 117690 | 0 | 107825 |  | 107825 | 9865 | 9865 | 92
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 581 | 0 | 581 | 419 | 581 |  | 581 | 419 | 0 | 58
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 2399 | 0 | 2399 | 2601 | 2399 |  | 2399 | 2601 | 0 | 48
|  |  |  | 20-02-21-40-01 | Municipality Fees | 30000 | 29300 | 0 | 11485 | 0 | 11485 | 17815 | 11485 |  | 11485 | 17815 | 0 | 39
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 59250 | 59950 | 59950 | 0 | 0 | 59950 | 0 | 32325 |  | 32325 | 27625 | 27625 | 54
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  | Total 100690-ldmp-0064 |  |  |  | 357633 | 369582 | 309282 | 34465 | 0 | 343747 | 25835 | 298129 |  | 298129 | 71453 | 45618 | 81
|  | 100690-ldmp-0065 | Community 9 Parcel 9 - Pre Dev | 20-02-12-20-05 | Preliminary Engineering | 6912 | 6912 | 6912 | 0 | 0 | 6912 | 0 | 6912 |  | 6912 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 1593 | 1596 | 1593 | 3 | 0 | 1596 | 0 | 1956 |  | 1956 | -360 | -360 | 123
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 12 | 0 | 12 | 988 | 12 |  | 12 | 988 | 0 | 1
|  |  |  | 20-02-21-40-01 | Municipality Fees | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 2375 | 4872 | 2375 | 83 | 0 | 2458 | 2414 | 2161 |  | 2161 | 2711 | 297 | 44
|  |  |  | 22-31-22-00-00 | Grading | 0 | 2500 | 5892 | 0 | 0 | 5892 | -3392 | 1819 |  | 1819 | 681 | 4073 | 73
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 640 | 640 | 0 | 0 | 0 | 0 | 640 | 0 |  | 0 | 640 | 0 | 0
|  | Total 100690-ldmp-0065 |  |  |  | 17520 | 17520 | 16772 | 98 | 0 | 16870 | 650 | 12860 |  | 12860 | 4660 | 4010 | 73
|  | 100690-ldmp-0067 | Community 9 Parcel 11 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 23900 | 36841 | 0 | 0 | 0 | 0 | 36841 | 0 |  | 0 | 36841 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 5457 | 5457 | 5457 | 0 | 0 | 5457 | 0 | 5457 |  | 5457 | 0 | 0 | 100
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 3500 | 6094 | 0 | 0 | 0 | 0 | 6094 | 0 |  | 0 | 6094 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 |  | 0 | 1000 | 0 | 0
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 1150 | 21150 | 0 | 0 | 0 | 0 | 21150 | 0 |  | 0 | 21150 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 1257 | 1257 | 1257 | 3 | 0 | 1261 | -4 | 1487 |  | 1487 | -230 | -226 | 118
|  |  |  | 20-02-12-20-24 | Final Engineering | 102480 | 102480 | 102480 | 0 | 0 | 102480 | 0 | 14100 |  | 14100 | 88380 | 88380 | 14
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 17 | 0 | 17 | 983 | 17 |  | 17 | 983 | 0 | 2
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 6015 | 10353 | 1875 | 83 | 0 | 1958 | 8395 | 1723 |  | 1723 | 8630 | 235 | 17
|  |  |  | 22-31-22-00-00 | Grading | 0 | 5892 | 5892 | 0 | 0 | 5892 | 0 | 1819 |  | 1819 | 4073 | 4073 | 31
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 17681 | 17681 | 0 | 0 | 0 | 0 | 17681 | 0 |  | 0 | 17681 | 0 | 0
|  | Total 100690-ldmp-0067 |  |  |  | 209890 | 257941 | 119411 | 103 | 0 | 119515 | 138426 | 25505 |  | 25505 | 232436 | 94010 | 10
|  | 100690-ldmp-0068 | Community 9 Parcel 12 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 47530 | 81176 | 0 | 0 | 0 | 0 | 81176 | 0 |  | 0 | 81176 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 26361 | 26361 | 26361 | 0 | 0 | 26361 | 0 | 26361 |  | 26361 | 0 | 0 | 100
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 4500 | 7094 | 0 | 0 | 0 | 0 | 7094 | 0 |  | 0 | 7094 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 3200 | 23200 | 0 | 0 | 0 | 0 | 23200 | 0 |  | 0 | 23200 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 5533 | 5533 | 5533 | 3 | 0 | 5536 | -3 | 4057 |  | 4057 | 1476 | 1479 | 73
|  |  |  | 20-02-12-20-24 | Final Engineering | 157220 | 157220 | 157220 | 0 | 0 | 157220 | 0 | 24500 |  | 24500 | 132720 | 132720 | 16
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 17 | 0 | 17 | 983 | 17 |  | 17 | 983 | 0 | 2
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 19770 | 24108 | 8250 | 83 | 0 | 8333 | 15775 | 7302 |  | 7302 | 16806 | 1031 | 30
|  |  |  | 22-31-22-00-00 | Grading | 0 | 5892 | 5892 | 0 | 0 | 5892 | 0 | 1819 |  | 1819 | 4073 | 4073 | 31
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 26373 | 26373 | 0 | 0 | 0 | 0 | 26373 | 0 |  | 0 | 26373 | 0 | 0
|  | Total 100690-ldmp-0068 |  |  |  | 338937 | 407693 | 206706 | 103 | 0 | 206809 | 200884 | 65958 |  | 65958 | 341735 | 140851 | 16
|  | 100690-ldmp-0069 | Community 9 Parcel 13 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 42220 | 73278 | 0 | 0 | 0 | 0 | 73278 | 0 |  | 0 | 73278 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 23815 | 23815 | 23815 | 0 | 0 | 23815 | 0 | 23815 |  | 23815 | 0 | 0 | 100
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 4000 | 6594 | 0 | 0 | 0 | 0 | 6594 | 0 |  | 0 | 6594 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 2800 | 22800 | 0 | 0 | 0 | 0 | 22800 | 0 |  | 0 | 22800 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 4946 | 4946 | 4946 | 3 | 0 | 4949 | -3 | 3709 |  | 3709 | 1237 | 1240 | 75
|  |  |  | 20-02-12-20-24 | Final Engineering | 139810 | 139810 | 139810 | 0 | 0 | 139810 | 0 | 19950 |  | 19950 | 119860 | 119860 | 14
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 17 | 0 | 17 | 983 | 17 |  | 17 | 983 | 0 | 2
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 17455 | 21793 | 7375 | 83 | 0 | 7458 | 14335 | 6536 |  | 6536 | 15257 | 922 | 30
|  |  |  | 22-31-22-00-00 | Grading | 0 | 5892 | 5892 | 0 | 0 | 5892 | 0 | 1819 |  | 1819 | 4073 | 4073 | 31
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 23981 | 23981 | 0 | 0 | 0 | 0 | 23981 | 0 |  | 0 | 23981 | 0 | 0
|  | Total 100690-ldmp-0069 |  |  |  | 307477 | 373645 | 185288 | 103 | 0 | 185391 | 188254 | 57748 |  | 57748 | 315897 | 127643 | 15
|  | 100690-ldmp-0070 | Community 9 Parcel 14 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 31130 | 51835 | 0 | 0 | 0 | 0 | 51835 | 0 |  | 0 | 51835 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 15083 | 15083 | 15083 | 0 | 0 | 15083 | 0 | 15083 |  | 15083 | 0 | 0 | 100
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 4000 | 6594 | 0 | 0 | 0 | 0 | 6594 | 0 |  | 0 | 6594 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 1950 | 21950 | 0 | 0 | 0 | 0 | 21950 | 0 |  | 0 | 21950 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 2934 | 2934 | 2934 | 3 | 0 | 2937 | -3 | 2515 |  | 2515 | 419 | 422 | 86
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 12 | 0 | 12 | 988 | 12 |  | 12 | 988 | 0 | 1
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 11395 | 15733 | 4375 | 83 | 0 | 4458 | 11275 | 3911 |  | 3911 | 11822 | 547 | 25
|  |  |  | 22-31-22-00-00 | Grading | 0 | 5892 | 5892 | 0 | 0 | 5892 | 0 | 1819 |  | 1819 | 4073 | 4073 | 31
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 9341 | 9341 | 0 | 0 | 0 | 0 | 9341 | 0 |  | 0 | 9341 | 0 | 0
|  | Total 100690-ldmp-0070 |  |  |  | 124283 | 180098 | 31734 | 98 | 0 | 31832 | 148266 | 25242 |  | 25242 | 154856 | 6590 | 14
|  | 100690-ldmp-0071 | Community 9 Parcel 15 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 35300 | 61182 | 0 | 0 | 0 | 0 | 61182 | 0 |  | 0 | 61182 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 21996 | 21996 | 21996 | 0 | 0 | 21996 | 0 | 21996 |  | 21996 | 0 | 0 | 100
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 4500 | 7094 | 0 | 0 | 0 | 0 | 7094 | 0 |  | 0 | 7094 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 2400 | 22400 | 0 | 0 | 0 | 0 | 22400 | 0 |  | 0 | 22400 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 4527 | 4527 | 4527 | 3 | 0 | 4530 | -3 | 3460 |  | 3460 | 1067 | 1070 | 76
|  |  |  | 20-02-12-20-24 | Final Engineering | 170625 | 170625 | 170625 | 0 | 0 | 170625 | 0 | 25800 |  | 25800 | 144825 | 144825 | 15
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 17 | 0 | 17 | 983 | 17 |  | 17 | 983 | 0 | 2
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 15390 | 19728 | 6750 | 83 | 0 | 6833 | 12895 | 5989 |  | 5989 | 13739 | 844 | 30
|  |  |  | 22-31-22-00-00 | Grading | 0 | 5892 | 5892 | 0 | 0 | 5892 | 0 | 1819 |  | 1819 | 4073 | 4073 | 31
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 25919 | 25919 | 0 | 0 | 0 | 0 | 25919 | 0 |  | 0 | 25919 | 0 | 0
|  | Total 100690-ldmp-0071 |  |  |  | 329107 | 390099 | 213240 | 103 | 0 | 213343 | 176756 | 60983 |  | 60983 | 329116 | 152360 | 16
|  | 100690-ldmp-0072 | Community 9 Parcel 16 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 39810 | 68280 | 0 | 0 | 0 | 0 | 68280 | 0 |  | 0 | 68280 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 20177 | 20177 | 20177 | 0 | 0 | 20177 | 0 | 20177 |  | 20177 | 0 | 0 | 100
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 4000 | 6594 | 0 | 0 | 0 | 0 | 6594 | 0 |  | 0 | 6594 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 2750 | 22750 | 0 | 0 | 0 | 0 | 22750 | 0 |  | 0 | 22750 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 4108 | 4108 | 4108 | 3 | 0 | 4111 | -4 | 3211 |  | 3211 | 897 | 900 | 78
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 12 | 0 | 12 | 988 | 12 |  | 12 | 988 | 0 | 1
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 16025 | 20363 | 6125 | 83 | 0 | 6208 | 14155 | 5442 |  | 5442 | 14921 | 766 | 27
|  |  |  | 22-31-22-00-00 | Grading | 0 | 0 | 5892 | 0 | 0 | 5892 | -5892 | 1819 |  | 1819 | -1819 | 4073 | 0
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 10146 | 10146 | 0 | 0 | 0 | 0 | 10146 | 0 |  | 0 | 10146 | 0 | 0
|  | Total 100690-ldmp-0072 |  |  |  | 140466 | 203154 | 39752 | 98 | 0 | 39850 | 163303 | 32563 |  | 32563 | 170591 | 7287 | 16
|  | 100690-ldmp-0073 | Community 9 Parcel 17 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 65360 | 119711 | 0 | 0 | 0 | 0 | 119711 | 0 |  | 0 | 119711 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 42733 | 42733 | 42733 | 0 | 0 | 42733 | 0 | 31354 |  | 31354 | 11379 | 11379 | 73
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 5000 | 7594 | 0 | 0 | 0 | 0 | 7594 | 0 |  | 0 | 7594 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 5150 | 25150 | 0 | 0 | 0 | 0 | 25150 | 0 |  | 0 | 25150 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 9305 | 9305 | 9305 | 3 | 0 | 9308 | -3 | 7824 |  | 7824 | 1481 | 1484 | 84
|  |  |  | 20-02-12-20-24 | Final Engineering | 128305 | 128305 | 128305 | 0 | 0 | 128305 | 0 | 18800 |  | 18800 | 109505 | 109505 | 15
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 17 | 0 | 17 | 983 | 17 |  | 17 | 983 | 0 | 2
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 22415 | 26753 | 13875 | 83 | 0 | 13958 | 12795 | 12223 |  | 12223 | 14530 | 1735 | 46
|  |  |  | 22-31-22-00-00 | Grading | 0 | 5892 | 5892 | 0 | 0 | 5892 | 0 | 1819 |  | 1819 | 4073 | 4073 | 31
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 25957 | 25957 | 0 | 0 | 0 | 0 | 25957 | 0 |  | 0 | 25957 | 0 | 0
|  | Total 100690-ldmp-0073 |  |  |  | 352675 | 442136 | 203560 | 103 | 0 | 203663 | 238473 | 73939 |  | 73939 | 368197 | 129724 | 17
|  | 100690-ldmp-0074 | Community 9 Parcel 19 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 28720 | 46837 | 0 | 0 | 0 | 0 | 46837 | 0 |  | 0 | 46837 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 91149 | 91149 | 12369 | 0 | 0 | 12369 | 78780 | 12369 |  | 12369 | 78780 | 0 | 14
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 3500 | 6094 | 0 | 0 | 0 | 0 | 6094 | 0 |  | 0 | 6094 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 1750 | 21750 | 0 | 0 | 0 | 0 | 21750 | 0 |  | 0 | 21750 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 2850 | 2850 | 2850 | 3 | 0 | 2854 | -4 | 2466 |  | 2466 | 384 | 388 | 87
|  |  |  | 20-02-12-20-24 | Final Engineering | 78825 | 78825 | 78825 | 0 | 0 | 78825 | 0 | 10150 |  | 10150 | 68675 | 68675 | 13
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 17 | 0 | 17 | 983 | 17 |  | 17 | 983 | 0 | 2
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 10550 | 14888 | 4250 | 83 | 0 | 4333 | 10555 | 3802 |  | 3802 | 11086 | 531 | 26
|  |  |  | 22-31-22-00-00 | Grading | 0 | 5892 | 5892 | 0 | 0 | 5892 | 0 | 1819 |  | 1819 | 4073 | 4073 | 31
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 23273 | 23273 | 0 | 0 | 0 | 0 | 23273 | 0 |  | 0 | 23273 | 0 | 0
|  | Total 100690-ldmp-0074 |  |  |  | 284067 | 337294 | 107636 | 103 | 0 | 107740 | 229554 | 32525 |  | 32525 | 304769 | 75215 | 10
|  | 100690-ldmp-0075 | Community 9 Parcel 20 - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 2450 | 2450 | 2450 | 0 | 0 | 2450 | 0 | 902 |  | 902 | 1548 | 1548 | 37
|  |  |  | 20-02-12-20-02 | Final Landscape | 44630 | 78276 | 0 | 0 | 0 | 0 | 78276 | 0 |  | 0 | 78276 | 0 | 0
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 26361 | 26361 | 23647 | 0 | 0 | 23647 | 2714 | 18263 |  | 18263 | 8098 | 5384 | 69
|  |  |  | 20-02-12-20-08 | Structural Engineering | 5000 | 6286 | 0 | 0 | 0 | 0 | 6286 | 0 |  | 0 | 6286 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 4500 | 7094 | 0 | 0 | 0 | 0 | 7094 | 0 |  | 0 | 7094 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 1000 | 1000 | 0 | 0 | 1000 | 0 | 1000 |  | 1000 | 0 | 0 | 100
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 3250 | 23250 | 0 | 0 | 0 | 0 | 23250 | 0 |  | 0 | 23250 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 5449 | 10897 | 5449 | 3 | 0 | 5452 | 5445 | 4007 |  | 4007 | 6890 | 1445 | 37
|  |  |  | 20-02-12-20-24 | Final Engineering | 112495 | 112495 | 112495 | 0 | 0 | 112495 | 0 | 22950 |  | 22950 | 89545 | 89545 | 20
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1000 | 1000 | 0 | 17 | 0 | 17 | 983 | 17 |  | 17 | 983 | 0 | 2
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 5000 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-21-50-30 | Plant Salvage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-22-40-05 | Landscape Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 19825 | 24163 | 8125 | 83 | 0 | 8208 | 15955 | 7192 |  | 7192 | 16971 | 1016 | 30
|  |  |  | 22-31-22-00-00 | Grading | 0 | 5892 | 5892 | 0 | 0 | 5892 | 0 | 1819 |  | 1819 | 4073 | 4073 | 31
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 22151 | 22151 | 0 | 0 | 0 | 0 | 22151 | 0 |  | 0 | 22151 | 0 | 0
|  | Total 100690-ldmp-0075 |  |  |  | 287111 | 361315 | 159058 | 103 | 0 | 159161 | 202154 | 56150 |  | 56150 | 305165 | 103011 | 16
|  | 100690-ldmp-0086 | Community 9 Parcel 27B - Pre Dev | 20-02-12-20-06 | Engineering-General | 99660 | 89660 | 0 | 0 | 0 | 0 | 89660 | 0 |  | 0 | 89660 | 0 | 0
|  |  |  | 20-02-12-20-09 | Soils Engineering | 0 | 0 | 4000 | 0 | 0 | 4000 | -4000 | 4000 |  | 4000 | -4000 | 0 | 0
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 0 | 10000 | 0 | 710 | 0 | 710 | 9290 | 710 |  | 710 | 9290 | 0 | 7
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 11073 | 11073 | 0 | 0 | 0 | 0 | 11073 | 0 |  | 0 | 11073 | 0 | 0
|  | Total 100690-ldmp-0086 |  |  |  | 110733 | 110733 | 4000 | 710 | 0 | 4710 | 106023 | 4710 |  | 4710 | 106023 | 0 | 4
|  | 100690-ldmp-0087 | Community 9 Parcel 27A&C - Pre Dev | 25-02-59-91-03 | Contingency - Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-59-91-90 | Contingency-Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldmp-0087 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldmp-0090 | Community 3 Parcel 49/50 - Pre Dev | 20-02-12-20-01 | Land Planning | 0 | 50000 | 10500 | 0 | 0 | 10500 | 39500 | 10492 |  | 10492 | 39508 | 8 | 21
|  | Total 100690-ldmp-0090 |  |  |  | 0 | 50000 | 10500 | 0 | 0 | 10500 | 39500 | 10492 |  | 10492 | 39508 | 8 | 21
|  | 100690-ldmp-0100 | Community 5 Planning | 20-02-12-20-01 | Land Planning | 0 | 50000 | 15000 | 0 | 0 | 15000 | 35000 | 13026 |  | 13026 | 36974 | 1974 | 26
|  |  |  | 20-02-12-30-01 | Legal-Acquisition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldmp-0100 |  |  |  | 0 | 50000 | 15000 | 0 | 0 | 15000 | 35000 | 13026 |  | 13026 | 36974 | 1974 | 26
|  | 100690-ldmp-0350 | Estrella Master Planning - East | 20-02-12-10-03 | Traffic Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10959 |  | 10959 | -10959 | -10959 | 0
|  |  |  | 20-02-12-10-07 | Engineering Studies | 0 | 200000 | 261037 | 0 | 0 | 261037 | -61037 | 100946 |  | 100946 | 99054 | 160091 | 50
|  |  |  | 20-02-12-10-13 | Other Studies-Consultants | 0 | 100000 | 10000 | 0 | 0 | 10000 | 90000 | 5990 |  | 5990 | 94010 | 4010 | 6
|  |  |  | 20-02-12-10-15 | Drainage/ 404 | 0 | 0 | 59000 | 0 | 0 | 59000 | -59000 | 46515 |  | 46515 | -46515 | 12485 | 0
|  |  |  | 20-02-12-20-01 | Land Planning | 0 | 20000 | 217500 | 44096 | 0 | 261596 | -241596 | 192686 |  | 192686 | -172686 | 68910 | 963
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 0 | 50000 | 322400 | 0 | 0 | 322400 | -272400 | 10689 |  | 10689 | 39311 | 311711 | 21
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 10000 | 0 | 142 | 0 | 142 | 9858 | 142 |  | 142 | 9858 | 0 | 1
|  | Total 100690-ldmp-0350 |  |  |  | 0 | 380000 | 869937 | 44238 | 0 | 914175 | -534175 | 367927 |  | 367927 | 12073 | 546248 | 97
|  | 100690-ldmp-0351 | Montecito Ph3 Planning (Delete) | 20-02-12-10-07 | Engineering Studies | 0 | 0 | 25300 | 0 | 0 | 25300 | -25300 | 0 |  | 0 | 0 | 25300 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldmp-0351 |  |  |  | 0 | 0 | 25300 | 0 | 0 | 25300 | -25300 | 0 |  | 0 | 0 | 25300 | 0
|  | 100690-ldmp-0352 | Community 14 Planning | 20-02-12-10-03 | Traffic Studies | 46500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-10-04 | Environmental Studies | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-10-05 | Geotechnical Studies | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-10-07 | Engineering Studies | 175070 | 84600 | 84600 | 0 | 0 | 84600 | 0 | 84391 |  | 84391 | 209 | 209 | 100
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 25000 | 3077 | 0 | 3077 | 0 | 3077 | 0 | 3077 |  | 3077 | 0 | 0 | 100
|  |  |  | 20-02-12-10-13 | Other Studies-Consultants | 175070 | 21884 | 21884 | 0 | 0 | 21884 | 0 | 21884 |  | 21884 | 0 | 0 | 100
|  |  |  | 20-02-12-20-01 | Land Planning | 144600 | 39492 | 0 | 47011 | 0 | 47011 | -7519 | 47011 |  | 47011 | -7519 | 0 | 119
|  |  |  | 20-02-12-20-02 | Final Landscape | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 292430 | 55658 | 55658 | 0 | 0 | 55658 | 0 | 57028 |  | 57028 | -1370 | -1370 | 102
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 382 | 0 | 382 | 0 | 382 | 0 | 382 |  | 382 | 0 | 0 | 100
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 0 | 1838 | 0 | 1838 | 0 | 1838 | 0 | 1838 |  | 1838 | 0 | 0 | 100
|  |  |  | 20-02-21-40-02 | Inspection Fees | 144300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-31-22-00-00 | Grading | 0 | 15100 | 15100 | 0 | 0 | 15100 | 0 | 15100 |  | 15100 | 0 | 0 | 100
|  |  |  | 25-02-59-91-03 | Contingency - Development | 100040 | 100040 | 0 | 0 | 0 | 0 | 100040 | 0 |  | 0 | 100040 | 0 | 0
|  | Total 100690-ldmp-0352 |  |  |  | 1275510 | 322071 | 177242 | 52308 | 0 | 229550 | 92521 | 230711 |  | 230711 | 91360 | -1161 | 72
|  | 100690-ldmp-0353 | Community 14 Planning (New) | 20-02-12-20-01 | Land Planning | 8666955 | 8666955 | 0 | 0 | 0 | 0 | 8666955 | 0 |  | 0 | 8666955 | 0 | 0
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 962995 | 962995 | 0 | 0 | 0 | 0 | 962995 | 0 |  | 0 | 962995 | 0 | 0
|  | Total 100690-ldmp-0353 |  |  |  | 9629950 | 9629950 | 0 | 0 | 0 | 0 | 9629950 | 0 |  | 0 | 9629950 | 0 | 0
|  | 100690-ldmp-0355 | Community 13 Planning | 20-02-12-20-01 | Land Planning | 2116125 | 2116125 | 0 | 0 | 0 | 0 | 2116125 | 0 |  | 0 | 2116125 | 0 | 0
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 235125 | 235125 | 0 | 0 | 0 | 0 | 235125 | 0 |  | 0 | 235125 | 0 | 0
|  | Total 100690-ldmp-0355 |  |  |  | 2351250 | 2351250 | 0 | 0 | 0 | 0 | 2351250 | 0 |  | 0 | 2351250 | 0 | 0
|  | 100690-ldmp-0357 | Estrella Master Planning | 20-02-12-10-03 | Traffic Studies | 0 | 100000 | 66500 | 0 | 0 | 66500 | 33500 | 75037 |  | 75037 | 24963 | -8537 | 75
|  |  |  | 20-02-12-10-07 | Engineering Studies | 33920 | 150000 | 115550 | 0 | 0 | 115550 | 34450 | 105528 |  | 105528 | 44472 | 10022 | 70
|  |  |  | 20-02-12-10-13 | Other Studies-Consultants | 0 | 100000 | 35600 | 13784 | 0 | 49384 | 50616 | 47372 |  | 47372 | 52628 | 2012 | 47
|  |  |  | 20-02-12-10-15 | Drainage/ 404 | 0 | 50000 | 19000 | 0 | 0 | 19000 | 31000 | 18911 |  | 18911 | 31089 | 89 | 38
|  |  |  | 20-02-12-20-01 | Land Planning | 3351560 | 1799039 | 68675 | 1270 | 0 | 69945 | 1729094 | 68482 |  | 68482 | 1730557 | 1463 | 4
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 14520 | 100000 | 14712 | 44359 | 0 | 59071 | 40929 | 59071 |  | 59071 | 40929 | 0 | 59
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 500 | 0 | 139 | 0 | 139 | 361 | 139 |  | 139 | 361 | 0 | 28
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 0 | 350000 | 0 | 185381 | 0 | 185381 | 164619 | 185381 |  | 185381 | 164619 | 0 | 53
|  |  |  | 20-02-21-40-01 | Municipality Fees | 0 | 10000 | 0 | 585 | 0 | 585 | 9415 | 585 |  | 585 | 9415 | 0 | 6
|  |  |  | 20-02-21-50-26 | Silt Fence | 0 | 10000 | 1250 | 0 | 0 | 1250 | 8750 | 1250 |  | 1250 | 8750 | 0 | 12
|  | Total 100690-ldmp-0357 |  |  |  | 3400000 | 2669539 | 321287 | 245518 | 0 | 566805 | 2102734 | 561756 |  | 561756 | 2107783 | 5049 | 21
|  | 100690-ldmp-0358 | Community 15 South Planning | 20-02-12-20-01 | Land Planning | 3972375 | 3972375 | 0 | 0 | 0 | 0 | 3972375 | 0 |  | 0 | 3972375 | 0 | 0
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 441375 | 441375 | 0 | 0 | 0 | 0 | 441375 | 0 |  | 0 | 441375 | 0 | 0
|  | Total 100690-ldmp-0358 |  |  |  | 4413750 | 4413750 | 0 | 0 | 0 | 0 | 4413750 | 0 |  | 0 | 4413750 | 0 | 0
|  | 100690-ldmp-0359 | Montecito School Site | 20-02-12-20-01 | Land Planning | 0 | 22500 | 22500 | 0 | 0 | 22500 | 0 | 3731 |  | 3731 | 18769 | 18769 | 17
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 |  | 0 | 15000 | 0 | 0
|  | Total 100690-ldmp-0359 |  |  |  | 0 | 37500 | 22500 | 0 | 0 | 22500 | 15000 | 3731 |  | 3731 | 33769 | 18769 | 10
|  | 100690-ldmp-0360 | Master Commercial Planning | 20-02-12-10-07 | Engineering Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-10-13 | Other Studies-Consultants | 0 | 50000 | 12000 | 0 | 0 | 12000 | 38000 | 11929 |  | 11929 | 38071 | 71 | 24
|  |  |  | 20-02-12-10-15 | Drainage/ 404 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 |  | 0 | 25000 | 0 | 0
|  |  |  | 20-02-12-20-01 | Land Planning | 0 | 25000 | 14000 | 0 | 0 | 14000 | 11000 | 14000 |  | 14000 | 11000 | 0 | 56
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 0 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 |  | 0 | 35000 | 0 | 0
|  |  |  | 20-02-12-30-02 | Legal - Land Use | 0 | 25000 | 0 | 4504 | 0 | 4504 | 20496 | 4504 |  | 4504 | 20496 | 0 | 18
|  |  |  | 20-02-21-40-01 | Municipality Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 0 | 180000 | 42000 | 0 | 0 | 42000 | 138000 | 90000 |  | 90000 | 90000 | -48000 | 50
|  | Total 100690-ldmp-0360 |  |  |  | 0 | 340000 | 68000 | 4504 | 0 | 72504 | 267496 | 120433 |  | 120433 | 219567 | -47929 | 35
|  | 100690-ldmp-0403 | Calistoga Drive 4 - Pre Dev | 20-02-12-10-07 | Engineering Studies | 90000 | 57425 | 57425 | 0 | 0 | 57425 | 0 | 32800 |  | 32800 | 24625 | 24625 | 57
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 9 | 9 | 0 | 9 | 0 | 9 | 0 | 9 |  | 9 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 24750 | 25150 | 16800 | 0 | 0 | 16800 | 8350 | 16300 |  | 16300 | 8850 | 500 | 65
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 0 | 5150 | 5150 | 0 | 0 | 5150 | 0 | 4805 |  | 4805 | 345 | 345 | 93
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 22500 | 0 | 1100 | 0 | 1100 | 21400 | 1100 |  | 1100 | 21400 | 0 | 5
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 0 | 683 | 0 | 683 | 0 | 683 | 0 | 683 |  | 683 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 13900 | 15400 | 15400 | 0 | 0 | 15400 | 0 | 6555 |  | 6555 | 8845 | 8845 | 43
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 50000 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 |  | 0 | 50000 | 0 | 0
|  | Total 100690-ldmp-0403 |  |  |  | 218659 | 176317 | 94775 | 1792 | 0 | 96567 | 79750 | 62252 |  | 62252 | 114065 | 34315 | 35
|  | 100690-ldmp-0405 | West Mountain Vista Drive - Pre Dev | 20-02-12-10-07 | Engineering Studies | 115000 | 97000 | 97000 | 0 | 0 | 97000 | 0 | 59000 |  | 59000 | 38000 | 38000 | 61
|  |  |  | 20-02-12-10-09 | Engineering Incidentals | 57 | 57 | 0 | 57 | 0 | 57 | 0 | 57 |  | 57 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 41900 | 21980 | 17000 | 0 | 0 | 17000 | 4980 | 16500 |  | 16500 | 5480 | 500 | 75
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 0 | 5900 | 5900 | 0 | 0 | 5900 | 0 | 5480 |  | 5480 | 420 | 420 | 93
|  |  |  | 20-02-12-20-15 | Dry Utility Design | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 0 | 65 | 0 | 65 | 0 | 65 | 0 | 65 |  | 65 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 35000 | 25638 | 0 | 2562 | 0 | 2562 | 23076 | 2562 |  | 2562 | 23076 | 0 | 10
|  |  |  | 20-02-21-40-13 | Water/Sewer Connection Tap Fees | 0 | 2063 | 0 | 2063 | 0 | 2063 | 0 | 2063 |  | 2063 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 0 | 850 | 850 | 0 | 0 | 850 | 0 | 850 |  | 850 | 0 | 0 | 100
|  |  |  | 20-02-21-60-14 | Warranty / Punch List | 0 | 4500 | 4500 | 12502 | 0 | 17002 | -12502 | 16440 |  | 16440 | -11940 | 562 | 365
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 34375 | 35875 | 35875 | 0 | 0 | 35875 | 0 | 14000 |  | 14000 | 21875 | 21875 | 39
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 50000 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 |  | 0 | 50000 | 0 | 0
|  | Total 100690-ldmp-0405 |  |  |  | 281332 | 243928 | 161125 | 17249 | 0 | 178374 | 65554 | 117017 |  | 117017 | 126911 | 61357 | 48
|  | 100690-ldmp-0408 | San Miguel Road - Pre Dev | 20-02-12-10-15 | Drainage/ 404 | 6400 | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 |  | 0 | 6400 | 0 | 0
|  |  |  | 20-02-12-20-02 | Final Landscape | 6500 | 16454 | 8900 | 0 | 0 | 8900 | 7554 | 7548 |  | 7548 | 8906 | 1352 | 46
|  |  |  | 20-02-12-20-03 | ALTA Survey / Topo | 2400 | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 |  | 0 | 2400 | 0 | 0
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 5000 | 5000 | 2400 | 0 | 0 | 2400 | 2600 | 2400 |  | 2400 | 2600 | 0 | 48
|  |  |  | 20-02-12-20-14 | Traffic Engineering | 1000 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 |  | 0 | 1000 | 0 | 0
|  |  |  | 20-02-12-20-23 | Preliminary Landscape | 1167 | 1167 | 1167 | 0 | 0 | 1167 | 0 | 1167 |  | 1167 | 0 | 0 | 100
|  |  |  | 20-02-12-20-24 | Final Engineering | 54200 | 54200 | 54200 | 0 | 0 | 54200 | 0 | 41100 |  | 41100 | 13100 | 13100 | 76
|  |  |  | 20-02-12-20-90 | Reimb Design & Engineering | 1020 | 1020 | 0 | 12 | 0 | 12 | 1008 | 12 |  | 12 | 1008 | 0 | 1
|  |  |  | 20-02-21-40-01 | Municipality Fees | 16050 | 2929 | 0 | 0 | 0 | 0 | 2929 | 0 |  | 0 | 2929 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 31590 | 34757 | 34757 | 0 | 0 | 34757 | 0 | 1583 |  | 1583 | 33174 | 33174 | 5
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 12533 | 12533 | 0 | 0 | 0 | 0 | 12533 | 0 |  | 0 | 12533 | 0 | 0
|  | Total 100690-ldmp-0408 |  |  |  | 137860 | 137860 | 101424 | 12 | 0 | 101436 | 36424 | 53810 |  | 53810 | 84050 | 47626 | 39
|  | 100690-ldmp-0409 | Sendero Dr Ph3 - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 21300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-12-10-07 | Engineering Studies | 27165 | 20990 | 26010 | 0 | 0 | 26010 | -5020 | 24297 |  | 24297 | -3307 | 1713 | 116
|  |  |  | 20-02-12-20-02 | Final Landscape | 4356 | 3400 | 3400 | 0 | 0 | 3400 | 0 | 3400 |  | 3400 | 0 | 0 | 100
|  |  |  | 20-02-12-20-04 | Staking | 39735 | 4950 | 4950 | 0 | 0 | 4950 | 0 | 4950 |  | 4950 | 0 | 0 | 100
|  |  |  | 20-02-12-20-11 | Street Light/ Electrical Engineering | 0 | 0 | 1500 | 0 | 0 | 1500 | -1500 | 1500 |  | 1500 | -1500 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 2457 | 2457 | 0 | 17964 | 0 | 17964 | -15507 | 17964 |  | 17964 | -15507 | 0 | 731
|  |  |  | 20-02-21-40-02 | Inspection Fees | 825 | 825 | 0 | 825 | 0 | 825 | 0 | 825 |  | 825 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 21594 | 43188 | 0 | 43188 | 0 | 43188 | 0 | 43188 |  | 43188 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 102941 | 60229 | 60229 | 0 | 0 | 60229 | 0 | 60229 |  | 60229 | 0 | 0 | 100
|  |  |  | 20-02-21-50-19 | Grading & Fill | 308312 | 308312 | 308312 | 0 | 0 | 308312 | 0 | 308312 |  | 308312 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 3622 | 3622 | 3622 | 0 | 0 | 3622 | 0 | 3622 |  | 3622 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 24466 | 24466 | 7750 | 16716 | 0 | 24466 | 0 | 24466 |  | 24466 | 0 | 0 | 100
|  | Total 100690-ldmp-0409 |  |  |  | 556773 | 472439 | 415773 | 78693 | 0 | 494466 | -22027 | 492753 |  | 492753 | -20314 | 1713 | 104
|  | 100690-ldmp-0411 | Ardmore Road - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 9400 | 500 | 500 | 0 | 0 | 500 | 0 | 500 |  | 500 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 6215 | 6915 | 700 | 6215 | 0 | 6915 | 0 | 6915 |  | 6915 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 4600 | 5190 | 4600 | 450 | 0 | 5050 | 140 | 5190 |  | 5190 | 0 | -140 | 100
|  |  |  | 20-02-12-20-04 | Staking | 17000 | 3000 | 3000 | 0 | 0 | 3000 | 0 | 3000 |  | 3000 | 0 | 0 | 100
|  |  |  | 20-02-21-40-01 | Municipality Fees | 2470 | 3420 | 0 | 11336 | 0 | 11336 | -7916 | 11336 |  | 11336 | -7916 | 0 | 331
|  |  |  | 20-02-21-40-02 | Inspection Fees | 4252 | 4252 | 0 | 4252 | 0 | 4252 | 0 | 4252 |  | 4252 | 0 | 0 | 100
|  |  |  | 20-02-21-45-04 | Performance Bonds | 1509 | 3018 | 0 | 3018 | 0 | 3018 | 0 | 3018 |  | 3018 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-50-19 | Grading & Fill | 49865 | 49865 | 49865 | 0 | 0 | 49865 | 0 | 49865 |  | 49865 | 0 | 0 | 100
|  |  |  | 20-02-21-50-26 | Silt Fence | 7075 | 4675 | 4675 | 0 | 0 | 4675 | 0 | 4675 |  | 4675 | 0 | 0 | 100
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 31209 | 21209 | 6350 | 14859 | 0 | 21209 | 0 | 21209 |  | 21209 | 0 | 0 | 100
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldmp-0411 |  |  |  | 137795 | 102044 | 69690 | 40130 | 0 | 109820 | -7776 | 109960 |  | 109960 | -7916 | -140 | 108
|  | 100690-ldmp-0415 | Sendero Lift Station - Pre Dev | 20-02-12-10-05 | Geotechnical Studies | 7200 | 780 | 780 | 0 | 0 | 780 | 0 | 780 |  | 780 | 0 | 0 | 100
|  |  |  | 20-02-12-10-07 | Engineering Studies | 63490 | 49648 | 49148 | 500 | 0 | 49648 | 0 | 49648 |  | 49648 | 0 | 0 | 100
|  |  |  | 20-02-12-20-02 | Final Landscape | 815 | 815 | 815 | 0 | 0 | 815 | 0 | 815 |  | 815 | 0 | 0 | 100
|  |  |  | 20-02-12-20-05 | Preliminary Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 20-02-21-40-01 | Municipality Fees | 2800 | 2917 | 0 | 7036 | 0 | 7036 | -4119 | 7036 |  | 7036 | -4119 | 0 | 241
|  |  |  | 20-02-21-45-04 | Performance Bonds | 3633 | 7266 | 0 | 7266 | 0 | 7266 | 0 | 7266 |  | 7266 | 0 | 0 | 100
|  |  |  | 20-02-21-50-18 | Rock Blasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 22-01-31-00-00 | Project Management and Coordination | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-59-91-02 | Contingency - Pre Development | 5000 | 85000 | 0 | 0 | 0 | 0 | 85000 | 0 |  | 0 | 85000 | 0 | 0
|  | Total 100690-ldmp-0415 |  |  |  | 92938 | 146426 | 50743 | 14802 | 0 | 65545 | 80881 | 65545 |  | 65545 | 80881 | 0 | 45
|  | 100690-ldmp-0605 | Rainbow Valley Road - Pre Dev | 20-02-12-30-02 | Legal - Land Use | 545400 | 545400 | 0 | 11118 | 0 | 11118 | 534282 | 11118 |  | 11118 | 534282 | 0 | 2
|  | Total 100690-ldmp-0605 |  |  |  | 545400 | 545400 | 0 | 11118 | 0 | 11118 | 534282 | 11118 |  | 11118 | 534282 | 0 | 2
|  | 100690-ldrj-0001 | Impact Fees (Legacy Parcels) | 25-02-50-30-07 | Impact Fee Credit-Sewer | 0 | 0 | 0 | -116946 | 0 | -116946 | 116946 | -116946 |  | -116946 | 116946 | 0 | 0
|  |  |  | 25-02-50-30-08 | Impact Fee Credit-Water | 0 | 0 | 0 | -2403819 | 0 | -2403819 | 2403819 | -2403819 |  | -2403819 | 2403819 | 0 | 0
|  |  |  | 25-02-50-30-09 | Impact Fee Credit-Fire | 0 | 0 | 0 | -988574 | 0 | -988574 | 988574 | -988574 |  | -988574 | 988574 | 0 | 0
|  |  |  | 25-02-50-30-10 | Impact Fee Credit-Park | 0 | 0 | 0 | -95479 | 0 | -95479 | 95479 | -95479 |  | -95479 | 95479 | 0 | 0
|  | Total 100690-ldrj-0001 |  |  |  | 0 | 0 | 0 | -3604818 | 0 | -3604818 | 3604818 | -3604818 |  | -3604818 | 3604818 | 0 | 0
|  | 100690-ldrj-0019 | Community 11 Parcel H - Inc Rev | 25-02-50-30-08 | Impact Fee Credit-Water | 0 | 0 | 0 | -91806 | 0 | -91806 | 91806 | -91806 |  | -91806 | 91806 | 0 | 0
|  |  |  | 25-02-50-30-09 | Impact Fee Credit-Fire | 0 | 0 | 0 | -4973 | 0 | -4973 | 4973 | -4973 |  | -4973 | 4973 | 0 | 0
|  | Total 100690-ldrj-0019 |  |  |  | 0 | 0 | 0 | -96779 | 0 | -96779 | 96779 | -96779 |  | -96779 | 96779 | 0 | 0
|  | 100690-ldrj-0038 | Community 9 Parcel 28&30 - Inc Rev | 25-02-50-30-08 | Impact Fee Credit-Water | 0 | 0 | 0 | -183612 | 0 | -183612 | 183612 | -183612 |  | -183612 | 183612 | 0 | 0
|  |  |  | 25-02-50-30-09 | Impact Fee Credit-Fire | 0 | 0 | 0 | -10568 | 0 | -10568 | 10568 | -10568 |  | -10568 | 10568 | 0 | 0
|  | Total 100690-ldrj-0038 |  |  |  | 0 | 0 | 0 | -194180 | 0 | -194180 | 194180 | -194180 |  | -194180 | 194180 | 0 | 0
|  | 100690-ldrj-0039 | Community 9 Parcel 29 - Inc Rev | 25-02-50-30-08 | Impact Fee Credit-Water | 0 | 0 | 0 | -166920 | 0 | -166920 | 166920 | -166920 |  | -166920 | 166920 | 0 | 0
|  |  |  | 25-02-50-30-09 | Impact Fee Credit-Fire | 0 | 0 | 0 | -12433 | 0 | -12433 | 12433 | -12433 |  | -12433 | 12433 | 0 | 0
|  | Total 100690-ldrj-0039 |  |  |  | 0 | 0 | 0 | -179353 | 0 | -179353 | 179353 | -179353 |  | -179353 | 179353 | 0 | 0
|  | 100690-ldrj-0076 | Canta Mia - Inc Rev | 25-02-50-30-07 | Impact Fee Credit-Sewer | 0 | 0 | 0 | -7614 | 0 | -7614 | 7614 | -7614 |  | -7614 | 7614 | 0 | 0
|  |  |  | 25-02-50-30-08 | Impact Fee Credit-Water | 0 | 0 | 0 | -1318668 | 0 | -1318668 | 1318668 | -1318668 |  | -1318668 | 1318668 | 0 | 0
|  |  |  | 25-02-50-30-09 | Impact Fee Credit-Fire | 0 | 0 | 0 | -101948 | 0 | -101948 | 101948 | -101948 |  | -101948 | 101948 | 0 | 0
|  |  |  | 25-02-50-30-10 | Impact Fee Credit-Park | 0 | 0 | 0 | -4510 | 0 | -4510 | 4510 | -4510 |  | -4510 | 4510 | 0 | 0
|  | Total 100690-ldrj-0076 |  |  |  | 0 | 0 | 0 | -1432740 | 0 | -1432740 | 1432740 | -1432740 |  | -1432740 | 1432740 | 0 | 0
|  | 100690-ldrj-0113 | Comm 11 Parcel D1 B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -12840 | 0 | -12840 | 12840 | -12840 |  | -12840 | 12840 | 0 | 0
|  | Total 100690-ldrj-0113 |  |  |  | 0 | 0 | 0 | -12840 | 0 | -12840 | 12840 | -12840 |  | -12840 | 12840 | 0 | 0
|  | 100690-ldrj-0115 | Comm 11 Parcel E B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -1375615 | 0 | -1375615 | 1375615 | -1375615 |  | -1375615 | 1375615 | 0 | 0
|  | Total 100690-ldrj-0115 |  |  |  | 0 | 0 | 0 | -1375615 | 0 | -1375615 | 1375615 | -1375615 |  | -1375615 | 1375615 | 0 | 0
|  | 100690-ldrj-0116 | Comm 11 Parcel F1 B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -867235 | 0 | -867235 | 867235 | -867235 |  | -867235 | 867235 | 0 | 0
|  | Total 100690-ldrj-0116 |  |  |  | 0 | 0 | 0 | -867235 | 0 | -867235 | 867235 | -867235 |  | -867235 | 867235 | 0 | 0
|  | 100690-ldrj-0119 | Comm 11 Parcel H B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -1001806 | 0 | -1001806 | 1001806 | -1001806 |  | -1001806 | 1001806 | 0 | 0
|  | Total 100690-ldrj-0119 |  |  |  | 0 | 0 | 0 | -1001806 | 0 | -1001806 | 1001806 | -1001806 |  | -1001806 | 1001806 | 0 | 0
|  | 100690-ldrj-0120 | Comm 11 Parcel I1 B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -550433 | 0 | -550433 | 550433 | -550433 |  | -550433 | 550433 | 0 | 0
|  | Total 100690-ldrj-0120 |  |  |  | 0 | 0 | 0 | -550433 | 0 | -550433 | 550433 | -550433 |  | -550433 | 550433 | 0 | 0
|  | 100690-ldrj-0121 | Comm 11 Parcel I2 B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -343904 | 0 | -343904 | 343904 | -343904 |  | -343904 | 343904 | 0 | 0
|  | Total 100690-ldrj-0121 |  |  |  | 0 | 0 | 0 | -343904 | 0 | -343904 | 343904 | -343904 |  | -343904 | 343904 | 0 | 0
|  | 100690-ldrj-0137 | Comm 9 Parcel 22 B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -33866 | 0 | -33866 | 33866 | -33866 |  | -33866 | 33866 | 0 | 0
|  | Total 100690-ldrj-0137 |  |  |  | 0 | 0 | 0 | -33866 | 0 | -33866 | 33866 | -33866 |  | -33866 | 33866 | 0 | 0
|  | 100690-ldrj-0138 | Comm 9 Parcel 28 B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -312040 | 0 | -312040 | 312040 | -312040 |  | -312040 | 312040 | 0 | 0
|  | Total 100690-ldrj-0138 |  |  |  | 0 | 0 | 0 | -312040 | 0 | -312040 | 312040 | -312040 |  | -312040 | 312040 | 0 | 0
|  | 100690-ldrj-0139 | Comm 9 Parcel 29 B/P-Assign Sales | 25-02-50-20-02 | CFD Assignment Sale | 0 | 0 | 0 | -147144 | 0 | -147144 | 147144 | -147144 |  | -147144 | 147144 | 0 | 0
|  | Total 100690-ldrj-0139 |  |  |  | 0 | 0 | 0 | -147144 | 0 | -147144 | 147144 | -147144 |  | -147144 | 147144 | 0 | 0
|  | 100690-ldrj-0200 | North Tenant Rent - Inc Rev | 25-02-50-30-05 | Incidental Rental Revenue | 0 | 0 | 0 | -44048 | 0 | -44048 | 44048 | -44048 |  | -44048 | 44048 | 0 | 0
|  | Total 100690-ldrj-0200 |  |  |  | 0 | 0 | 0 | -44048 | 0 | -44048 | 44048 | -44048 |  | -44048 | 44048 | 0 | 0
|  | 100690-ldrj-0300 | Estrella - GO Bond | 25-02-50-20-01 | CFD Reimbursements | -11085000 | -11085000 | 0 | -11085084 | 0 | -11085084 | 84 | -11085084 |  | -11085084 | 84 | 0 | 100
|  | Total 100690-ldrj-0300 |  |  |  | -11085000 | -11085000 | 0 | -11085084 | 0 | -11085084 | 84 | -11085084 |  | -11085084 | 84 | 0 | 100
|  | 100690-ldsc-0715 | COS Contra Job | 10-04-11-11-00 | L/D COS-Closing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 30-04-11-11-00 | L/D COS-Contra-Closing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsc-0715 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0002 | Community 11 South | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -824545 | -824545 | 0 | 0 | 0 | 0 | -824545 | 0 |  | 0 | -824545 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -713506 | -713506 | 0 | 0 | 0 | 0 | -713506 | 0 |  | 0 | -713506 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -1119223 | -1119223 | 0 | 0 | 0 | 0 | -1119223 | 0 |  | 0 | -1119223 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0002 |  |  |  | -2657274 | -2657274 | 0 | 0 | 0 | 0 | -2657274 | 0 |  | 0 | -2657274 | 0 | 0
|  | 100690-ldsj-0009 | Community 10 Parcel B | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-02-18-95-00 | L/D Selling Exp-Closing-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0009 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0011 | Community 11 Parcel B (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0011 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0012 | Community 11 Parcel C (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | -212705 | -212705 | 0 | -212705 | 0 | -212705 | 0 | -212705 |  | -212705 | 0 | 0 | 100
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -41338 | -41338 | 0 | -41338 | 0 | -41338 | 0 | -41338 |  | -41338 | 0 | 0 | 100
|  | Total 100690-ldsj-0012 |  |  |  | -254043 | -254043 | 0 | -254043 | 0 | -254043 | 0 | -254043 |  | -254043 | 0 | 0 | 200
|  | 100690-ldsj-0013 | Community 11 Parcel D1 (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | -249452 | -249452 | 0 | -249452 | 0 | -249452 | 0 | -249452 |  | -249452 | 0 | 0 | 100
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -10000 | -10000 | 0 | -10000 | 0 | -10000 | 0 | -10000 |  | -10000 | 0 | 0 | 100
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -32197 | -32197 | 0 | -32197 | 0 | -32197 | 0 | -32197 |  | -32197 | 0 | 0 | 100
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -46573 | -46573 | 0 | -46573 | 0 | -46573 | 0 | -46573 |  | -46573 | 0 | 0 | 100
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 2619 | 2619 | 0 | 2619 | 0 | 2619 | 0 | 2619 |  | 2619 | 0 | 0 | 100
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 1112 | 1112 | 0 | 1112 | 0 | 1112 | 0 | 1112 |  | 1112 | 0 | 0 | 100
|  | Total 100690-ldsj-0013 |  |  |  | -334491 | -334491 | 0 | -334491 | 0 | -334491 | 0 | -334491 |  | -334491 | 0 | 0 | 600
|  | 100690-ldsj-0014 | Community 11 Parcel D2 &D3 | 10-01-11-11-00 | Land Dev Sales-SF Lots | -8356325 | -8356325 | 0 | 0 | 0 | 0 | -8356325 | 0 |  | 0 | -8356325 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -188827 | -188827 | 0 | 0 | 0 | 0 | -188827 | 0 |  | 0 | -188827 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -163398 | -163398 | 0 | 0 | 0 | 0 | -163398 | 0 |  | 0 | -163398 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -256311 | -256311 | 0 | 0 | 0 | 0 | -256311 | 0 |  | 0 | -256311 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 101000 | 101000 | 0 | 0 | 0 | 0 | 101000 | 0 |  | 0 | 101000 | 0 | 0
|  | Total 100690-ldsj-0014 |  |  |  | -8863861 | -8863861 | 0 | 0 | 0 | 0 | -8863861 | 0 |  | 0 | -8863861 | 0 | 0
|  | 100690-ldsj-0015 | Community 11 Parcel E | 10-01-11-11-00 | Land Dev Sales-SF Lots | -15189200 | -15189200 | 0 | -3160179 | 0 | -3160179 | -12029021 | -3160179 |  | -3160179 | -12029021 | 0 | 21
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -289524 | -289524 | 0 | 0 | 0 | 0 | -289524 | 0 |  | 0 | -289524 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -250516 | -250516 | 0 | 0 | 0 | 0 | -250516 | 0 |  | 0 | -250516 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -393024 | -393024 | 0 | 0 | 0 | 0 | -393024 | 0 |  | 0 | -393024 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 206938 | 206938 | 0 | 115749 | 0 | 115749 | 91189 | 115749 |  | 115749 | 91189 | 0 | 56
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 33168 | 0 | 33168 | -33168 | 33168 |  | 33168 | -33168 | 0 | 0
|  |  |  | 10-04-11-11-00 | L/D COS-Closing-SF Lots | 0 | 0 | 0 | 3833874 | 0 | 3833874 | -3833874 | 3833874 |  | 3833874 | -3833874 | 0 | 0
|  |  |  | 30-04-11-11-00 | L/D COS-Contra-Closing-SF Lots | 0 | 0 | 0 | -3833874 | 0 | -3833874 | 3833874 | -3833874 |  | -3833874 | 3833874 | 0 | 0
|  | Total 100690-ldsj-0015 |  |  |  | -15915326 | -15915326 | 0 | -3011262 | 0 | -3011262 | -12904064 | -3011262 |  | -3011262 | -12904064 | 0 | 77
|  | 100690-ldsj-0016 | Community 11 Parcel F1 | 10-01-11-11-00 | Land Dev Sales-SF Lots | -10788000 | -10788000 | 0 | -2470981 | 0 | -2470981 | -8317019 | -2470981 |  | -2470981 | -8317019 | 0 | 23
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -182526 | -182526 | 0 | 0 | 0 | 0 | -182526 | 0 |  | 0 | -182526 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -157934 | -157934 | 0 | 0 | 0 | 0 | -157934 | 0 |  | 0 | -157934 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -247776 | -247776 | 0 | 0 | 0 | 0 | -247776 | 0 |  | 0 | -247776 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 103840 | 103840 | 0 | 60048 | 0 | 60048 | 43792 | 60048 |  | 60048 | 43792 | 0 | 58
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 33712 | 0 | 33712 | -33712 | 33712 |  | 33712 | -33712 | 0 | 0
|  |  |  | 10-04-11-11-00 | L/D COS-Closing-SF Lots | 0 | 0 | 0 | 3274169 | 0 | 3274169 | -3274169 | 3274169 |  | 3274169 | -3274169 | 0 | 0
|  |  |  | 30-04-11-11-00 | L/D COS-Contra-Closing-SF Lots | 0 | 0 | 0 | -3274169 | 0 | -3274169 | 3274169 | -3274169 |  | -3274169 | 3274169 | 0 | 0
|  | Total 100690-ldsj-0016 |  |  |  | -11272396 | -11272396 | 0 | -2377221 | 0 | -2377221 | -8895175 | -2377221 |  | -2377221 | -8895175 | 0 | 81
|  | 100690-ldsj-0019 | Community 11 Parcel H | 10-01-11-11-00 | Land Dev Sales-SF Lots | -7849469 | -7849469 | 0 | -6943739 | 0 | -6943739 | -905730 | -6943739 |  | -6943739 | -905730 | 0 | 88
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -210849 | -210849 | 0 | -5278 | 0 | -5278 | -205571 | -5278 |  | -5278 | -205571 | 0 | 3
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -182441 | -182441 | 0 | 0 | 0 | 0 | -182441 | 0 |  | 0 | -182441 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -286224 | -286224 | 0 | 0 | 0 | 0 | -286224 | 0 |  | 0 | -286224 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 142925 | 142925 | 0 | 148457 | 0 | 148457 | -5532 | 148457 |  | 148457 | -5532 | 0 | 104
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 7530 | 0 | 7530 | -7530 | 7530 |  | 7530 | -7530 | 0 | 0
|  |  |  | 10-04-11-11-00 | L/D COS-Closing-SF Lots | 0 | 0 | 0 | 5376468 | 0 | 5376468 | -5376468 | 5376468 |  | 5376468 | -5376468 | 0 | 0
|  |  |  | 30-04-11-11-00 | L/D COS-Contra-Closing-SF Lots | 0 | 0 | 0 | -5376468 | 0 | -5376468 | 5376468 | -5376468 |  | -5376468 | 5376468 | 0 | 0
|  | Total 100690-ldsj-0019 |  |  |  | -8386058 | -8386058 | 0 | -6793030 | 0 | -6793030 | -1593028 | -6793030 |  | -6793030 | -1593028 | 0 | 195
|  | 100690-ldsj-0020 | Community 11 Parcel I1& I2 | 10-01-11-11-00 | Land Dev Sales-SF Lots | -9174400 | -9174400 | 0 | -1675836 | 0 | -1675836 | -7498564 | -1675836 |  | -1675836 | -7498564 | 0 | 18
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -191967 | -191967 | 0 | 0 | 0 | 0 | -191967 | 0 |  | 0 | -191967 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -166103 | -166103 | 0 | 0 | 0 | 0 | -166103 | 0 |  | 0 | -166103 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -260592 | -260592 | 0 | 0 | 0 | 0 | -260592 | 0 |  | 0 | -260592 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 87809 | 87809 | 0 | 54240 | 0 | 54240 | 33569 | 54240 |  | 54240 | 33569 | 0 | 62
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 31902 | 0 | 31902 | -31902 | 31902 |  | 31902 | -31902 | 0 | 0
|  |  |  | 10-04-11-11-00 | L/D COS-Closing-SF Lots | 0 | 0 | 0 | 2157554 | 0 | 2157554 | -2157554 | 2157554 |  | 2157554 | -2157554 | 0 | 0
|  |  |  | 30-04-11-11-00 | L/D COS-Contra-Closing-SF Lots | 0 | 0 | 0 | -2157554 | 0 | -2157554 | 2157554 | -2157554 |  | -2157554 | 2157554 | 0 | 0
|  | Total 100690-ldsj-0020 |  |  |  | -9705253 | -9705253 | 0 | -1589694 | 0 | -1589694 | -8115559 | -1589694 |  | -1589694 | -8115559 | 0 | 80
|  | 100690-ldsj-0022 | Community 11 Parcel J | 10-01-17-30-00 | Land Dev Sales-MF-Mixed Use | -12000000 | -12000000 | 0 | 0 | 0 | 0 | -12000000 | 0 |  | 0 | -12000000 | 0 | 0
|  |  |  | 10-02-17-30-00 | L/D Selling Exp-Closing-MF-Mixed Use | 539886 | 539886 | 0 | 0 | 0 | 0 | 539886 | 0 |  | 0 | 539886 | 0 | 0
|  |  |  | 10-03-17-20-00 | L/D Selling Exp-XClosing-MF-Mixed Use | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0022 |  |  |  | -11460114 | -11460114 | 0 | 0 | 0 | 0 | -11460114 | 0 |  | 0 | -11460114 | 0 | 0
|  | 100690-ldsj-0023 | Community 2 Parcel 84 | 10-01-18-95-00 | Land Dev Sales-Other Commercial | -1129718 | -1129718 | 0 | 0 | 0 | 0 | -1129718 | 0 |  | 0 | -1129718 | 0 | 0
|  |  |  | 10-03-18-90-00 | L/D Selling Exp-XClosing-Other Commercial | 50837 | 50837 | 0 | 0 | 0 | 0 | 50837 | 0 |  | 0 | 50837 | 0 | 0
|  | Total 100690-ldsj-0023 |  |  |  | -1078881 | -1078881 | 0 | 0 | 0 | 0 | -1078881 | 0 |  | 0 | -1078881 | 0 | 0
|  | 100690-ldsj-0024 | Community 2 Parcel 16 | 10-01-16-11-00 | Land Dev Sales-SF Parcel-Size | 3024000 | 3024000 | 0 | 0 | 0 | 0 | 3024000 | 0 |  | 0 | 3024000 | 0 | 0
|  |  |  | 10-02-16-10-00 | L/D Selling Exp-Closing-SF Parcel-Size | 136080 | 136080 | 0 | 0 | 0 | 0 | 136080 | 0 |  | 0 | 136080 | 0 | 0
|  | Total 100690-ldsj-0024 |  |  |  | 3160080 | 3160080 | 0 | 0 | 0 | 0 | 3160080 | 0 |  | 0 | 3160080 | 0 | 0
|  | 100690-ldsj-0025 | Community 2 Parcel 18 | 10-01-16-11-00 | Land Dev Sales-SF Parcel-Size | -3780000 | -3780000 | 0 | 0 | 0 | 0 | -3780000 | 0 |  | 0 | -3780000 | 0 | 0
|  |  |  | 10-02-16-10-00 | L/D Selling Exp-Closing-SF Parcel-Size | 170100 | 170100 | 0 | 0 | 0 | 0 | 170100 | 0 |  | 0 | 170100 | 0 | 0
|  | Total 100690-ldsj-0025 |  |  |  | -3609900 | -3609900 | 0 | 0 | 0 | 0 | -3609900 | 0 |  | 0 | -3609900 | 0 | 0
|  | 100690-ldsj-0027 | Community 2 Parcel 45A | 10-01-17-30-00 | Land Dev Sales-MF-Mixed Use | -18295200 | -18295200 | 0 | 0 | 0 | 0 | -18295200 | 0 |  | 0 | -18295200 | 0 | 0
|  |  |  | 10-02-17-30-00 | L/D Selling Exp-Closing-MF-Mixed Use | 823284 | 823284 | 0 | 0 | 0 | 0 | 823284 | 0 |  | 0 | 823284 | 0 | 0
|  |  |  | 10-03-17-20-00 | L/D Selling Exp-XClosing-MF-Mixed Use | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0027 |  |  |  | -17471916 | -17471916 | 0 | 0 | 0 | 0 | -17471916 | 0 |  | 0 | -17471916 | 0 | 0
|  | 100690-ldsj-0028 | Community 2 Parcel 48 | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-18-90-00 | L/D Selling Exp-XClosing-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0028 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0029 | Community 2 Parcel 45B | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-18-90-00 | L/D Selling Exp-XClosing-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0029 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0030 | Community 13 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -2690787 | -2690787 | 0 | 0 | 0 | 0 | -2690787 | 0 |  | 0 | -2690787 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -2328427 | -2328427 | 0 | 0 | 0 | 0 | -2328427 | 0 |  | 0 | -2328427 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -3652427 | -3652427 | 0 | 0 | 0 | 0 | -3652427 | 0 |  | 0 | -3652427 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-19-00-00 | L/D Selling Exp-XClosing-Bulk Residential | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0030 |  |  |  | -8671641 | -8671641 | 0 | 0 | 0 | 0 | -8671641 | 0 |  | 0 | -8671641 | 0 | 0
|  | 100690-ldsj-0036 | Community 7 Parcel 1 (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | 0 | 0 | 0 | -94922 | 0 | -94922 | 94922 | -94922 |  | -94922 | 94922 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0036 |  |  |  | 0 | 0 | 0 | -94922 | 0 | -94922 | 94922 | -94922 |  | -94922 | 94922 | 0 | 0
|  | 100690-ldsj-0037 | Community 9 Parcel 22 (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | -749885 | -749885 | 0 | -749885 | 0 | -749885 | 0 | -749885 |  | -749885 | 0 | 0 | 100
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -46293 | -46293 | 0 | -46293 | 0 | -46293 | 0 | -46293 |  | -46293 | 0 | 0 | 100
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -89220 | -89220 | 0 | -89220 | 0 | -89220 | 0 | -89220 |  | -89220 | 0 | 0 | 100
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 16228 | 16228 | 0 | 16228 | 0 | 16228 | 0 | 16228 |  | 16228 | 0 | 0 | 100
|  | Total 100690-ldsj-0037 |  |  |  | -869170 | -869170 | 0 | -869170 | 0 | -869170 | 0 | -869170 |  | -869170 | 0 | 0 | 400
|  | 100690-ldsj-0038 | Community 9 Parcel 28 & 30 | 10-01-11-11-00 | Land Dev Sales-SF Lots | -3984000 | -3984000 | 0 | -4211123 | 0 | -4211123 | 227123 | -4211123 |  | -4211123 | 227123 | 0 | 106
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -210849 | -210849 | 0 | 0 | 0 | 0 | -210849 | 0 |  | 0 | -210849 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -182441 | -182441 | 0 | -1184132 | 0 | -1184132 | 1001691 | -1184132 |  | -1184132 | 1001691 | 0 | 649
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -286224 | -286224 | 0 | 0 | 0 | 0 | -286224 | 0 |  | 0 | -286224 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 179280 | 179280 | 0 | 132912 | 0 | 132912 | 46368 | 132912 |  | 132912 | 46368 | 0 | 74
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 16814 | 0 | 16814 | -16814 | 16814 |  | 16814 | -16814 | 0 | 0
|  |  |  | 10-04-11-11-00 | L/D COS-Closing-SF Lots | 0 | 0 | 0 | 3792758 | 0 | 3792758 | -3792758 | 3792758 |  | 3792758 | -3792758 | 0 | 0
|  |  |  | 30-04-11-11-00 | L/D COS-Contra-Closing-SF Lots | 0 | 0 | 0 | -3792758 | 0 | -3792758 | 3792758 | -3792758 |  | -3792758 | 3792758 | 0 | 0
|  | Total 100690-ldsj-0038 |  |  |  | -4484234 | -4484234 | 0 | -5245529 | 0 | -5245529 | 761295 | -5245529 |  | -5245529 | 761295 | 0 | 829
|  | 100690-ldsj-0039 | Community 9 Parcel 29 & Great Lawn | 10-01-11-11-00 | Land Dev Sales-SF Lots | -2957500 | -2957500 | 0 | -2957500 | 0 | -2957500 | 0 | -2957500 |  | -2957500 | 0 | 0 | 100
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -204555 | -204555 | 0 | 0 | 0 | 0 | -204555 | 0 |  | 0 | -204555 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -176995 | -176995 | 0 | -1923405 | 0 | -1923405 | 1746410 | -1923405 |  | -1923405 | 1746410 | 0 | 1087
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -277680 | -277680 | 0 | 0 | 0 | 0 | -277680 | 0 |  | 0 | -277680 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 133088 | 133088 | 0 | 113274 | 0 | 113274 | 19814 | 113274 |  | 113274 | 19814 | 0 | 85
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 7620 | 57654 | 0 | 65274 | -65274 | 65274 |  | 65274 | -65274 | 0 | 0
|  |  |  | 10-04-11-11-00 | L/D COS-Closing-SF Lots | 0 | 0 | 0 | 5117444 | 0 | 5117444 | -5117444 | 5117444 |  | 5117444 | -5117444 | 0 | 0
|  |  |  | 30-04-11-11-00 | L/D COS-Contra-Closing-SF Lots | 0 | 0 | 0 | -5117444 | 0 | -5117444 | 5117444 | -5117444 |  | -5117444 | 5117444 | 0 | 0
|  | Total 100690-ldsj-0039 |  |  |  | -3483642 | -3483642 | 7620 | -4709977 | 0 | -4702357 | 1218715 | -4702357 |  | -4702357 | 1218715 | 0 | 1272
|  | 100690-ldsj-0040 | Community 9 Parcel 39.40 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -305271 | -305271 | 0 | 0 | 0 | 0 | -305271 | 0 |  | 0 | -305271 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -264161 | -264161 | 0 | 0 | 0 | 0 | -264161 | 0 |  | 0 | -264161 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -414369 | -414369 | 0 | 0 | 0 | 0 | -414369 | 0 |  | 0 | -414369 | 0 | 0
|  | Total 100690-ldsj-0040 |  |  |  | -983801 | -983801 | 0 | 0 | 0 | 0 | -983801 | 0 |  | 0 | -983801 | 0 | 0
|  | 100690-ldsj-0041 | Community 9 Parcel 18 | 10-01-11-11-00 | Land Dev Sales-SF Lots | -1569798 | -1569798 | 0 | 0 | 0 | 0 | -1569798 | 0 |  | 0 | -1569798 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 70641 | 70641 | 0 | 0 | 0 | 0 | 70641 | 0 |  | 0 | 70641 | 0 | 0
|  | Total 100690-ldsj-0041 |  |  |  | -1499157 | -1499157 | 0 | 0 | 0 | 0 | -1499157 | 0 |  | 0 | -1499157 | 0 | 0
|  | 100690-ldsj-0042 | Community 9 Parcel 21 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -289535 | -289535 | 0 | 0 | 0 | 0 | -289535 | 0 |  | 0 | -289535 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -250544 | -250544 | 0 | 0 | 0 | 0 | -250544 | 0 |  | 0 | -250544 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -393010 | -393010 | 0 | 0 | 0 | 0 | -393010 | 0 |  | 0 | -393010 | 0 | 0
|  | Total 100690-ldsj-0042 |  |  |  | -933089 | -933089 | 0 | 0 | 0 | 0 | -933089 | 0 |  | 0 | -933089 | 0 | 0
|  | 100690-ldsj-0043 | Community 9 Parcel 31 (Legacy) | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -78743 | -78743 | 0 | -78743 | 0 | -78743 | 0 | -78743 |  | -78743 | 0 | 0 | 100
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -16367 | -16367 | 0 | -16367 | 0 | -16367 | 0 | -16367 |  | -16367 | 0 | 0 | 100
|  | Total 100690-ldsj-0043 |  |  |  | -95110 | -95110 | 0 | -95110 | 0 | -95110 | 0 | -95110 |  | -95110 | 0 | 0 | 200
|  | 100690-ldsj-0044 | Community 9 Parcel 41 | 10-01-11-11-00 | Land Dev Sales-SF Lots | 9702732 | 9702732 | 0 | 0 | 0 | 0 | 9702732 | 0 |  | 0 | 9702732 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -163650 | -163650 | 0 | 0 | 0 | 0 | -163650 | 0 |  | 0 | -163650 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -141612 | -141612 | 0 | 0 | 0 | 0 | -141612 | 0 |  | 0 | -141612 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -222136 | -222136 | 0 | 0 | 0 | 0 | -222136 | 0 |  | 0 | -222136 | 0 | 0
|  | Total 100690-ldsj-0044 |  |  |  | 9175334 | 9175334 | 0 | 0 | 0 | 0 | 9175334 | 0 |  | 0 | 9175334 | 0 | 0
|  | 100690-ldsj-0045 | Community 9 Parcel 42 | 10-01-11-11-00 | Land Dev Sales-SF Lots | 17924713 | 17924713 | 0 | 0 | 0 | 0 | 17924713 | 0 |  | 0 | 17924713 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -380801 | -380801 | 0 | 0 | 0 | 0 | -380801 | 0 |  | 0 | -380801 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -329520 | -329520 | 0 | 0 | 0 | 0 | -329520 | 0 |  | 0 | -329520 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -516893 | -516893 | 0 | 0 | 0 | 0 | -516893 | 0 |  | 0 | -516893 | 0 | 0
|  | Total 100690-ldsj-0045 |  |  |  | 16697499 | 16697499 | 0 | 0 | 0 | 0 | 16697499 | 0 |  | 0 | 16697499 | 0 | 0
|  | 100690-ldsj-0046 | Community 9 Parcel 43 (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | -42500 | 0 | -42500 | 42500 | -42500 |  | -42500 | 42500 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | 0 | 0 | 0 | -99196 | 0 | -99196 | 99196 | -99196 |  | -99196 | 99196 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | 0 | 0 | 0 | -25796 | 0 | -25796 | 25796 | -25796 |  | -25796 | 25796 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 939 | 0 | 939 | -939 | 939 |  | 939 | -939 | 0 | 0
|  | Total 100690-ldsj-0046 |  |  |  | 0 | 0 | 0 | -166553 | 0 | -166553 | 166553 | -166553 |  | -166553 | 166553 | 0 | 0
|  | 100690-ldsj-0048 | Community 12 Parcel 23A (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | 0 | 0 | 0 | -159755 | 0 | -159755 | 159755 | -159755 |  | -159755 | 159755 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0048 |  |  |  | 0 | 0 | 0 | -159755 | 0 | -159755 | 159755 | -159755 |  | -159755 | 159755 | 0 | 0
|  | 100690-ldsj-0049 | Community 12 Parcel 23B | 10-01-11-11-00 | Land Dev Sales-SF Lots | -9242550 | -9242550 | 0 | -7992283 | 0 | -7992283 | -1250267 | -7992283 |  | -7992283 | -1250267 | 0 | 86
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -217143 | -217143 | 0 | 0 | 0 | 0 | -217143 | 0 |  | 0 | -217143 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -187887 | -187887 | 0 | 0 | 0 | 0 | -187887 | 0 |  | 0 | -187887 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -294768 | -294768 | 0 | 0 | 0 | 0 | -294768 | 0 |  | 0 | -294768 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 147298 | 147298 | 0 | 146391 | 0 | 146391 | 907 | 146391 |  | 146391 | 907 | 0 | 99
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 13112 | 0 | 13112 | -13112 | 13112 |  | 13112 | -13112 | 0 | 0
|  |  |  | 10-04-11-11-00 | L/D COS-Closing-SF Lots | 0 | 0 | 0 | 5679384 | 0 | 5679384 | -5679384 | 5679384 |  | 5679384 | -5679384 | 0 | 0
|  |  |  | 30-04-11-11-00 | L/D COS-Contra-Closing-SF Lots | 0 | 0 | 0 | -5679384 | 0 | -5679384 | 5679384 | -5679384 |  | -5679384 | 5679384 | 0 | 0
|  | Total 100690-ldsj-0049 |  |  |  | -9795050 | -9795050 | 0 | -7832780 | 0 | -7832780 | -1962270 | -7832780 |  | -7832780 | -1962270 | 0 | 185
|  | 100690-ldsj-0050 | Community 12 Parcel 24 (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | 0 | 0 | 0 | -663963 | 0 | -663963 | 663963 | -663963 |  | -663963 | 663963 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | -1250 | 0 | -1250 | 1250 | -1250 |  | -1250 | 1250 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | 0 | 0 | 0 | -393318 | 0 | -393318 | 393318 | -393318 |  | -393318 | 393318 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | 0 | 0 | 0 | -115850 | 0 | -115850 | 115850 | -115850 |  | -115850 | 115850 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 240 | 0 | 240 | -240 | 240 |  | 240 | -240 | 0 | 0
|  | Total 100690-ldsj-0050 |  |  |  | 0 | 0 | 0 | -1174141 | 0 | -1174141 | 1174141 | -1174141 |  | -1174141 | 1174141 | 0 | 0
|  | 100690-ldsj-0051 | Community 12 Parcel 25 | 10-01-11-11-00 | Land Dev Sales-SF Lots | -11620960 | -11620960 | 0 | 0 | 0 | 0 | -11620960 | 0 |  | 0 | -11620960 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -232887 | -232887 | 0 | 0 | 0 | 0 | -232887 | 0 |  | 0 | -232887 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -201525 | -201525 | 0 | 0 | 0 | 0 | -201525 | 0 |  | 0 | -201525 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -316116 | -316116 | 0 | 0 | 0 | 0 | -316116 | 0 |  | 0 | -316116 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 152729 | 152729 | 0 | 0 | 0 | 0 | 152729 | 0 |  | 0 | 152729 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0051 |  |  |  | -12218759 | -12218759 | 0 | 0 | 0 | 0 | -12218759 | 0 |  | 0 | -12218759 | 0 | 0
|  | 100690-ldsj-0052 | Community 12 Parcel 36 | 10-01-11-11-00 | Land Dev Sales-SF Lots | -5790000 | -5790000 | 0 | 0 | 0 | 0 | -5790000 | 0 |  | 0 | -5790000 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -125885 | -125885 | 0 | 0 | 0 | 0 | -125885 | 0 |  | 0 | -125885 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -108932 | -108932 | 0 | 0 | 0 | 0 | -108932 | 0 |  | 0 | -108932 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -170874 | -170874 | 0 | 0 | 0 | 0 | -170874 | 0 |  | 0 | -170874 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 24723 | 24723 | 0 | 0 | 0 | 0 | 24723 | 0 |  | 0 | 24723 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0052 |  |  |  | -6170968 | -6170968 | 0 | 0 | 0 | 0 | -6170968 | 0 |  | 0 | -6170968 | 0 | 0
|  | 100690-ldsj-0053 | Community 12 Parcel 41 | 10-01-11-11-00 | Land Dev Sales-SF Lots | -4707285 | -4707285 | 0 | 0 | 0 | 0 | -4707285 | 0 |  | 0 | -4707285 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -103855 | -103855 | 0 | 0 | 0 | 0 | -103855 | 0 |  | 0 | -103855 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -89869 | -89869 | 0 | 0 | 0 | 0 | -89869 | 0 |  | 0 | -89869 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -140971 | -140971 | 0 | 0 | 0 | 0 | -140971 | 0 |  | 0 | -140971 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 56682 | 56682 | 0 | 0 | 0 | 0 | 56682 | 0 |  | 0 | 56682 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0053 |  |  |  | -4985298 | -4985298 | 0 | 0 | 0 | 0 | -4985298 | 0 |  | 0 | -4985298 | 0 | 0
|  | 100690-ldsj-0055 | Community 12 Parcel 42 | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-18-90-00 | L/D Selling Exp-XClosing-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0055 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0057 | Community 12 Parcel 79 | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-18-90-00 | L/D Selling Exp-XClosing-Other Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0057 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0058 | Community 12 Parcel 80 | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 1546380 | 1546380 | 0 | 0 | 0 | 0 | 1546380 | 0 |  | 0 | 1546380 | 0 | 0
|  |  |  | 10-02-18-95-00 | L/D Selling Exp-Closing-Other Commercial | 69587 | 69587 | 0 | 0 | 0 | 0 | 69587 | 0 |  | 0 | 69587 | 0 | 0
|  | Total 100690-ldsj-0058 |  |  |  | 1615967 | 1615967 | 0 | 0 | 0 | 0 | 1615967 | 0 |  | 0 | 1615967 | 0 | 0
|  | 100690-ldsj-0059 | Community 12 Parcel 81 | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 1546380 | 1546380 | 0 | 0 | 0 | 0 | 1546380 | 0 |  | 0 | 1546380 | 0 | 0
|  |  |  | 10-02-18-95-00 | L/D Selling Exp-Closing-Other Commercial | 69587 | 69587 | 0 | 0 | 0 | 0 | 69587 | 0 |  | 0 | 69587 | 0 | 0
|  | Total 100690-ldsj-0059 |  |  |  | 1615967 | 1615967 | 0 | 0 | 0 | 0 | 1615967 | 0 |  | 0 | 1615967 | 0 | 0
|  | 100690-ldsj-0064 | Community 9 Parcel 7 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -298976 | -298976 | 0 | 0 | 0 | 0 | -298976 | 0 |  | 0 | -298976 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -258714 | -258714 | 0 | 0 | 0 | 0 | -258714 | 0 |  | 0 | -258714 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -405825 | -405825 | 0 | 0 | 0 | 0 | -405825 | 0 |  | 0 | -405825 | 0 | 0
|  | Total 100690-ldsj-0064 |  |  |  | -963515 | -963515 | 0 | 0 | 0 | 0 | -963515 | 0 |  | 0 | -963515 | 0 | 0
|  | 100690-ldsj-0065 | Community 9 Parcel 9 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -81825 | -81825 | 0 | 0 | 0 | 0 | -81825 | 0 |  | 0 | -81825 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -70806 | -70806 | 0 | 0 | 0 | 0 | -70806 | 0 |  | 0 | -70806 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -111068 | -111068 | 0 | 0 | 0 | 0 | -111068 | 0 |  | 0 | -111068 | 0 | 0
|  |  |  | 10-01-16-11-00 | Land Dev Sales-SF Parcel-Size | -5824000 | -5824000 | 0 | 0 | 0 | 0 | -5824000 | 0 |  | 0 | -5824000 | 0 | 0
|  | Total 100690-ldsj-0065 |  |  |  | -6087699 | -6087699 | 0 | 0 | 0 | 0 | -6087699 | 0 |  | 0 | -6087699 | 0 | 0
|  | 100690-ldsj-0067 | Community 9 Parcel 11 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -44060 | -44060 | 0 | 0 | 0 | 0 | -44060 | 0 |  | 0 | -44060 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -38126 | -38126 | 0 | 0 | 0 | 0 | -38126 | 0 |  | 0 | -38126 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -59806 | -59806 | 0 | 0 | 0 | 0 | -59806 | 0 |  | 0 | -59806 | 0 | 0
|  | Total 100690-ldsj-0067 |  |  |  | -141992 | -141992 | 0 | 0 | 0 | 0 | -141992 | 0 |  | 0 | -141992 | 0 | 0
|  | 100690-ldsj-0068 | Community 9 Parcel 12 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -201416 | -201416 | 0 | 0 | 0 | 0 | -201416 | 0 |  | 0 | -201416 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -174292 | -174292 | 0 | 0 | 0 | 0 | -174292 | 0 |  | 0 | -174292 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -273398 | -273398 | 0 | 0 | 0 | 0 | -273398 | 0 |  | 0 | -273398 | 0 | 0
|  | Total 100690-ldsj-0068 |  |  |  | -649106 | -649106 | 0 | 0 | 0 | 0 | -649106 | 0 |  | 0 | -649106 | 0 | 0
|  | 100690-ldsj-0069 | Community 9 Parcel 13 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -182533 | -182533 | 0 | 0 | 0 | 0 | -182533 | 0 |  | 0 | -182533 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -157952 | -157952 | 0 | 0 | 0 | 0 | -157952 | 0 |  | 0 | -157952 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -247767 | -247767 | 0 | 0 | 0 | 0 | -247767 | 0 |  | 0 | -247767 | 0 | 0
|  | Total 100690-ldsj-0069 |  |  |  | -588252 | -588252 | 0 | 0 | 0 | 0 | -588252 | 0 |  | 0 | -588252 | 0 | 0
|  | 100690-ldsj-0070 | Community 9 Parcel 14 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -110149 | -110149 | 0 | 0 | 0 | 0 | -110149 | 0 |  | 0 | -110149 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -95316 | -95316 | 0 | 0 | 0 | 0 | -95316 | 0 |  | 0 | -95316 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -149515 | -149515 | 0 | 0 | 0 | 0 | -149515 | 0 |  | 0 | -149515 | 0 | 0
|  | Total 100690-ldsj-0070 |  |  |  | -354980 | -354980 | 0 | 0 | 0 | 0 | -354980 | 0 |  | 0 | -354980 | 0 | 0
|  | 100690-ldsj-0071 | Community 9 Parcel 15 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -166797 | -166797 | 0 | 0 | 0 | 0 | -166797 | 0 |  | 0 | -166797 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -144335 | -144335 | 0 | 0 | 0 | 0 | -144335 | 0 |  | 0 | -144335 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -226408 | -226408 | 0 | 0 | 0 | 0 | -226408 | 0 |  | 0 | -226408 | 0 | 0
|  | Total 100690-ldsj-0071 |  |  |  | -537540 | -537540 | 0 | 0 | 0 | 0 | -537540 | 0 |  | 0 | -537540 | 0 | 0
|  | 100690-ldsj-0072 | Community 9 Parcel 16 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -157356 | -157356 | 0 | 0 | 0 | 0 | -157356 | 0 |  | 0 | -157356 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -136165 | -136165 | 0 | 0 | 0 | 0 | -136165 | 0 |  | 0 | -136165 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -213592 | -213592 | 0 | 0 | 0 | 0 | -213592 | 0 |  | 0 | -213592 | 0 | 0
|  | Total 100690-ldsj-0072 |  |  |  | -507113 | -507113 | 0 | 0 | 0 | 0 | -507113 | 0 |  | 0 | -507113 | 0 | 0
|  | 100690-ldsj-0073 | Community 9 Parcel 17 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -330447 | -330447 | 0 | 0 | 0 | 0 | -330447 | 0 |  | 0 | -330447 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -285947 | -285947 | 0 | 0 | 0 | 0 | -285947 | 0 |  | 0 | -285947 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -448544 | -448544 | 0 | 0 | 0 | 0 | -448544 | 0 |  | 0 | -448544 | 0 | 0
|  | Total 100690-ldsj-0073 |  |  |  | -1064938 | -1064938 | 0 | 0 | 0 | 0 | -1064938 | 0 |  | 0 | -1064938 | 0 | 0
|  | 100690-ldsj-0074 | Community 9 Parcel 19 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -107002 | -107002 | 0 | 0 | 0 | 0 | -107002 | 0 |  | 0 | -107002 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -92592 | -92592 | 0 | 0 | 0 | 0 | -92592 | 0 |  | 0 | -92592 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -145243 | -145243 | 0 | 0 | 0 | 0 | -145243 | 0 |  | 0 | -145243 | 0 | 0
|  | Total 100690-ldsj-0074 |  |  |  | -344837 | -344837 | 0 | 0 | 0 | 0 | -344837 | 0 |  | 0 | -344837 | 0 | 0
|  | 100690-ldsj-0075 | Community 9 Parcel 20 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -207710 | -207710 | 0 | 0 | 0 | 0 | -207710 | 0 |  | 0 | -207710 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -179738 | -179738 | 0 | 0 | 0 | 0 | -179738 | 0 |  | 0 | -179738 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -281942 | -281942 | 0 | 0 | 0 | 0 | -281942 | 0 |  | 0 | -281942 | 0 | 0
|  | Total 100690-ldsj-0075 |  |  |  | -669390 | -669390 | 0 | 0 | 0 | 0 | -669390 | 0 |  | 0 | -669390 | 0 | 0
|  | 100690-ldsj-0076 | Canta Mia | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | 0 | 0 | 0 | -214759 | 0 | -214759 | 214759 | -214759 |  | -214759 | 214759 | 0 | 0
|  | Total 100690-ldsj-0076 |  |  |  | 0 | 0 | 0 | -214759 | 0 | -214759 | 214759 | -214759 |  | -214759 | 214759 | 0 | 0
|  | 100690-ldsj-0078 | Community 9 Parcel 1 (Legacy) | 10-01-11-11-00 | Land Dev Sales-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | 0 | 0 | 0 | -351303 | 0 | -351303 | 351303 | -351303 |  | -351303 | 351303 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | 0 | 0 | 0 | -58616 | 0 | -58616 | 58616 | -58616 |  | -58616 | 58616 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0078 |  |  |  | 0 | 0 | 0 | -409919 | 0 | -409919 | 409919 | -409919 |  | -409919 | 409919 | 0 | 0
|  | 100690-ldsj-0083 | Community 9 Parcel 25 | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 1016037 | 1016037 | 0 | 0 | 0 | 0 | 1016037 | 0 |  | 0 | 1016037 | 0 | 0
|  |  |  | 10-02-18-95-00 | L/D Selling Exp-Closing-Other Commercial | 45722 | 45722 | 0 | 0 | 0 | 0 | 45722 | 0 |  | 0 | 45722 | 0 | 0
|  | Total 100690-ldsj-0083 |  |  |  | 1061759 | 1061759 | 0 | 0 | 0 | 0 | 1061759 | 0 |  | 0 | 1061759 | 0 | 0
|  | 100690-ldsj-0085 | Community 9 Parcel 27A | 10-01-17-30-00 | Land Dev Sales-MF-Mixed Use | -4665276 | -4665276 | 0 | 0 | 0 | 0 | -4665276 | 0 |  | 0 | -4665276 | 0 | 0
|  |  |  | 10-02-17-30-00 | L/D Selling Exp-Closing-MF-Mixed Use | 209937 | 209937 | 0 | 0 | 0 | 0 | 209937 | 0 |  | 0 | 209937 | 0 | 0
|  | Total 100690-ldsj-0085 |  |  |  | -4455339 | -4455339 | 0 | 0 | 0 | 0 | -4455339 | 0 |  | 0 | -4455339 | 0 | 0
|  | 100690-ldsj-0086 | Community 9 Parcel 27B | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -188827 | -188827 | 0 | 0 | 0 | 0 | -188827 | 0 |  | 0 | -188827 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -163398 | -163398 | 0 | 0 | 0 | 0 | -163398 | 0 |  | 0 | -163398 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -256311 | -256311 | 0 | 0 | 0 | 0 | -256311 | 0 |  | 0 | -256311 | 0 | 0
|  | Total 100690-ldsj-0086 |  |  |  | -608536 | -608536 | 0 | 0 | 0 | 0 | -608536 | 0 |  | 0 | -608536 | 0 | 0
|  | 100690-ldsj-0087 | Community 9 Parcel 27C | 10-01-17-30-00 | Land Dev Sales-MF-Mixed Use | -3939566 | -3939566 | 0 | 0 | 0 | 0 | -3939566 | 0 |  | 0 | -3939566 | 0 | 0
|  |  |  | 10-02-17-30-00 | L/D Selling Exp-Closing-MF-Mixed Use | 177280 | 177280 | 0 | 0 | 0 | 0 | 177280 | 0 |  | 0 | 177280 | 0 | 0
|  | Total 100690-ldsj-0087 |  |  |  | -3762286 | -3762286 | 0 | 0 | 0 | 0 | -3762286 | 0 |  | 0 | -3762286 | 0 | 0
|  | 100690-ldsj-0089 | Community 3 Parcel 44 | 10-01-17-30-00 | Land Dev Sales-MF-Mixed Use | -3924756 | -3924756 | 0 | 0 | 0 | 0 | -3924756 | 0 |  | 0 | -3924756 | 0 | 0
|  |  |  | 10-02-17-30-00 | L/D Selling Exp-Closing-MF-Mixed Use | 176614 | 176614 | 0 | 0 | 0 | 0 | 176614 | 0 |  | 0 | 176614 | 0 | 0
|  | Total 100690-ldsj-0089 |  |  |  | -3748142 | -3748142 | 0 | 0 | 0 | 0 | -3748142 | 0 |  | 0 | -3748142 | 0 | 0
|  | 100690-ldsj-0090 | Community 3 Parcel 49/50 | 10-01-17-30-00 | Land Dev Sales-MF-Mixed Use | -5776056 | -5776056 | 0 | 0 | 0 | 0 | -5776056 | 0 |  | 0 | -5776056 | 0 | 0
|  |  |  | 10-02-17-30-00 | L/D Selling Exp-Closing-MF-Mixed Use | 259923 | 259923 | 0 | 0 | 0 | 0 | 259923 | 0 |  | 0 | 259923 | 0 | 0
|  | Total 100690-ldsj-0090 |  |  |  | -5516133 | -5516133 | 0 | 0 | 0 | 0 | -5516133 | 0 |  | 0 | -5516133 | 0 | 0
|  | 100690-ldsj-0092 | Community 3 Parcel 59 | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -33018 | -33018 | 0 | -33018 | 0 | -33018 | 0 | -33018 |  | -33018 | 0 | 0 | 100
|  | Total 100690-ldsj-0092 |  |  |  | -33018 | -33018 | 0 | -33018 | 0 | -33018 | 0 | -33018 |  | -33018 | 0 | 0 | 100
|  | 100690-ldsj-0093 | Resmark Warranty Work | 10-01-11-11-00 | Land Dev Sales-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0093 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0099 | Estrella N Spec Land (Webner) | 10-01-11-11-00 | Land Dev Sales-SF Lots | 0 | 0 | 0 | -7040790 | 0 | -7040790 | 7040790 | -7040790 |  | -7040790 | 7040790 | 0 | 0
|  |  |  | 10-02-11-11-00 | L/D Selling Exp-Closing-SF Lots | 0 | 0 | 0 | 222441 | 0 | 222441 | -222441 | 222441 |  | 222441 | -222441 | 0 | 0
|  |  |  | 10-03-19-00-00 | L/D Selling Exp-XClosing-Bulk Residential | 0 | 0 | 0 | 20770 | 0 | 20770 | -20770 | 20770 |  | 20770 | -20770 | 0 | 0
|  | Total 100690-ldsj-0099 |  |  |  | 0 | 0 | 0 | -6797579 | 0 | -6797579 | 6797579 | -6797579 |  | -6797579 | 6797579 | 0 | 0
|  | 100690-ldsj-0101 | Community 5 Parcel 2 | 10-01-16-11-00 | Land Dev Sales-SF Parcel-Size | 816000 | 816000 | 0 | 0 | 0 | 0 | 816000 | 0 |  | 0 | 816000 | 0 | 0
|  |  |  | 10-02-16-10-00 | L/D Selling Exp-Closing-SF Parcel-Size | 36720 | 36720 | 0 | 0 | 0 | 0 | 36720 | 0 |  | 0 | 36720 | 0 | 0
|  | Total 100690-ldsj-0101 |  |  |  | 852720 | 852720 | 0 | 0 | 0 | 0 | 852720 | 0 |  | 0 | 852720 | 0 | 0
|  | 100690-ldsj-0102 | Community 5 Parcel 4 | 10-01-16-11-00 | Land Dev Sales-SF Parcel-Size | 384000 | 384000 | 0 | 0 | 0 | 0 | 384000 | 0 |  | 0 | 384000 | 0 | 0
|  |  |  | 10-02-16-10-00 | L/D Selling Exp-Closing-SF Parcel-Size | 17280 | 17280 | 0 | 0 | 0 | 0 | 17280 | 0 |  | 0 | 17280 | 0 | 0
|  | Total 100690-ldsj-0102 |  |  |  | 401280 | 401280 | 0 | 0 | 0 | 0 | 401280 | 0 |  | 0 | 401280 | 0 | 0
|  | 100690-ldsj-0103 | Community 5 Parcel 9 (Legacy) | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -1000 | -1000 | 0 | -1000 | 0 | -1000 | 0 | -1000 |  | -1000 | 0 | 0 | 100
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -23477 | -23477 | 0 | -23477 | 0 | -23477 | 0 | -23477 |  | -23477 | 0 | 0 | 100
|  | Total 100690-ldsj-0103 |  |  |  | -24477 | -24477 | 0 | -24477 | 0 | -24477 | 0 | -24477 |  | -24477 | 0 | 0 | 200
|  | 100690-ldsj-0104 | Community 5 Parcel 14, 15, & 16 | 10-01-16-11-00 | Land Dev Sales-SF Parcel-Size | 3984000 | 3984000 | 0 | 0 | 0 | 0 | 3984000 | 0 |  | 0 | 3984000 | 0 | 0
|  |  |  | 10-02-16-10-00 | L/D Selling Exp-Closing-SF Parcel-Size | 179280 | 179280 | 0 | 0 | 0 | 0 | 179280 | 0 |  | 0 | 179280 | 0 | 0
|  | Total 100690-ldsj-0104 |  |  |  | 4163280 | 4163280 | 0 | 0 | 0 | 0 | 4163280 | 0 |  | 0 | 4163280 | 0 | 0
|  | 100690-ldsj-0110 | Community 10 Parcel A | 10-01-18-95-00 | Land Dev Sales-Other Commercial | 1411344 | 1411344 | 0 | 0 | 0 | 0 | 1411344 | 0 |  | 0 | 1411344 | 0 | 0
|  |  |  | 10-02-18-95-00 | L/D Selling Exp-Closing-Other Commercial | 63510 | 63510 | 0 | 0 | 0 | 0 | 63510 | 0 |  | 0 | 63510 | 0 | 0
|  | Total 100690-ldsj-0110 |  |  |  | 1474854 | 1474854 | 0 | 0 | 0 | 0 | 1474854 | 0 |  | 0 | 1474854 | 0 | 0
|  | 100690-ldsj-0352 | Community 14 | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -11021210 | -11021210 | 0 | 0 | 0 | 0 | -11021210 | 0 |  | 0 | -11021210 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -9537020 | -9537020 | 0 | 0 | 0 | 0 | -9537020 | 0 |  | 0 | -9537020 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -14959998 | -14959998 | 0 | 0 | 0 | 0 | -14959998 | 0 |  | 0 | -14959998 | 0 | 0
|  | Total 100690-ldsj-0352 |  |  |  | -35518228 | -35518228 | 0 | 0 | 0 | 0 | -35518228 | 0 |  | 0 | -35518228 | 0 | 0
|  | 100690-ldsj-0356 | Community 15 - North | 10-03-11-10-00 | L/D Selling Exp-XClosing-SF Lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100690-ldsj-0356 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | 100690-ldsj-0358 | Community 15 - South | 10-01-12-20-00 | Land Dev Sales-Variable Premiums Lots | -5051126 | -5051126 | 0 | 0 | 0 | 0 | -5051126 | 0 |  | 0 | -5051126 | 0 | 0
|  |  |  | 10-01-13-20-00 | Land Dev Sales-Variable Participation Lots | -4370907 | -4370907 | 0 | 0 | 0 | 0 | -4370907 | 0 |  | 0 | -4370907 | 0 | 0
|  |  |  | 10-01-14-20-00 | Land Dev Sales-Variable Marketing Fee Lots | -6856310 | -6856310 | 0 | 0 | 0 | 0 | -6856310 | 0 |  | 0 | -6856310 | 0 | 0
|  | Total 100690-ldsj-0358 |  |  |  | -16278343 | -16278343 | 0 | 0 | 0 | 0 | -16278343 | 0 |  | 0 | -16278343 | 0 | 0
|  | 100690-si-0001 | Wayfinding Upgrades | 25-02-56-40-31 | Marketing Miscellaneous | 420000 | 329085 | 0 | 329085 | 0 | 329085 | 0 | 329085 |  | 329085 | 0 | 0 | 100
|  | Total 100690-si-0001 |  |  |  | 420000 | 329085 | 0 | 329085 | 0 | 329085 | 0 | 329085 |  | 329085 | 0 | 0 | 100
|  | 100690-si-0002 | Marketing Amenity Upgrades | 25-02-56-40-31 | Marketing Miscellaneous | 250000 | 16231 | 0 | 16231 | 0 | 16231 | 0 | 16231 |  | 16231 | 0 | 0 | 100
|  | Total 100690-si-0002 |  |  |  | 250000 | 16231 | 0 | 16231 | 0 | 16231 | 0 | 16231 |  | 16231 | 0 | 0 | 100
|  | 100690-si-0003 | 2024 Capital MKT Trail Upgrades | 20-02-12-20-11 | Street Light/ Electrical Engineering | 200000 | 200000 | 69651 | 0 | 0 | 69651 | 130349 | 34351 |  | 34351 | 165649 | 35300 | 17
|  |  |  | 20-02-22-40-01 | Landscaping | 0 | 0 | 11900 | 0 | 0 | 11900 | -11900 | 2450 |  | 2450 | -2450 | 9450 | 0
|  | Total 100690-si-0003 |  |  |  | 200000 | 200000 | 81551 | 0 | 0 | 81551 | 118449 | 36801 |  | 36801 | 163199 | 44750 | 18
Total 100690 | [5 empty] | 162073390 | 176423208 | 41077918 | 107949970 | 0 | 149027892 | 27395315 | 144170122 |  | 144170122 | 32253086 | 4857770 | 82
100790 | Estrella South LLC | 100790-ullj-0349 | Estrella South Land Job | 20-02-11-10-01 | Purchase Price | 0 | 0 | 0 | 39792161 | 0 | 39792161 | -39792161 | 39792161 |  | 39792161 | -39792161 | 0 | 0
|  |  |  | 25-02-50-30-05 | Incidental Rental Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-57-10-01 | Real Property Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-58-10-01 | Cap Dev Mgmt Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-58-80-01 | Cap-Alloc-Personnel Exp-Bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-58-80-02 | Cap-Alloc-Personnel Exp-Vacation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100790-ullj-0349 |  |  |  | 0 | 0 | 0 | 39792161 | 0 | 39792161 | -39792161 | 39792161 |  | 39792161 | -39792161 | 0 | 0
|  | 100790-ulmp-0001 | South - Master Planning | 10-03-19-00-00 | L/D Selling Exp-XClosing-Bulk Residential | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-19-10-00 | L/D Selling Exp-XClosing-Bulk Non-Residential | 0 | 0 | 0 | 11868 | 0 | 11868 | -11868 | 11868 |  | 11868 | -11868 | 0 | 0
|  | Total 100790-ulmp-0001 |  |  |  | 0 | 0 | 0 | 11868 | 0 | 11868 | -11868 | 11868 |  | 11868 | -11868 | 0 | 0
|  | 100790-ulsj-0001 | South - Farm Land 1 - Lofdahl | 10-01-19-20-00 | Land Dev Sales-Bulk Non-Residential | 46409600 | 46409600 | 0 | -27155225 | 0 | -27155225 | 73564825 | -27155225 |  | -27155225 | 73564825 | 0 | -59
|  |  |  | 10-02-19-20-00 | L/D Selling Exp-Closing-Bulk Non-Residential | 1160240 | 1160240 | 0 | 1026844 | 0 | 1026844 | 133396 | 1026844 |  | 1026844 | 133396 | 0 | 89
|  |  |  | 10-03-19-10-00 | L/D Selling Exp-XClosing-Bulk Non-Residential | 232048 | 232048 | 0 | 207827 | 0 | 207827 | 24221 | 207827 |  | 207827 | 24221 | 0 | 90
|  |  |  | 10-04-19-20-00 | L/D COS-Closing-Bulk Non-Residential | 0 | 0 | 0 | 5505763 | 0 | 5505763 | -5505763 | 5505763 |  | 5505763 | -5505763 | 0 | 0
|  |  |  | 30-04-19-20-00 | L/D COS-Contra-Closing-Bulk Non-Residential | 0 | 0 | 0 | -5505763 | 0 | -5505763 | 5505763 | -5505763 |  | -5505763 | 5505763 | 0 | 0
|  | Total 100790-ulsj-0001 |  |  |  | 47801888 | 47801888 | 0 | -25920554 | 0 | -25920554 | 73722442 | -25920554 |  | -25920554 | 73722442 | 0 | -54
|  | 100790-ulsj-0002 | South - Farm Land 2 - Jorde | 10-01-19-20-00 | Land Dev Sales-Bulk Non-Residential | 12500000 | 12500000 | 0 | -1250000 | 0 | -1250000 | 13750000 | -1250000 |  | -1250000 | 13750000 | 0 | -10
|  |  |  | 10-02-19-20-00 | L/D Selling Exp-Closing-Bulk Non-Residential | 437500 | 437500 | 0 | 53649 | 0 | 53649 | 383851 | 53649 |  | 53649 | 383851 | 0 | 12
|  |  |  | 10-03-19-10-00 | L/D Selling Exp-XClosing-Bulk Non-Residential | 62500 | 62500 | 0 | 64210 | 0 | 64210 | -1710 | 64210 |  | 64210 | -1710 | 0 | 103
|  |  |  | 10-04-19-20-00 | L/D COS-Closing-Bulk Non-Residential | 0 | 0 | 0 | 246533 | 0 | 246533 | -246533 | 246533 |  | 246533 | -246533 | 0 | 0
|  |  |  | 30-04-19-20-00 | L/D COS-Contra-Closing-Bulk Non-Residential | 0 | 0 | 0 | -246533 | 0 | -246533 | 246533 | -246533 |  | -246533 | 246533 | 0 | 0
|  | Total 100790-ulsj-0002 |  |  |  | 13000000 | 13000000 | 0 | -1132141 | 0 | -1132141 | 14132141 | -1132141 |  | -1132141 | 14132141 | 0 | -9
|  | 100790-ulsj-0003 | South Land - Solar | 10-01-19-20-00 | Land Dev Sales-Bulk Non-Residential | 81400000 | 81400000 | 0 | 0 | 0 | 0 | 81400000 | 0 |  | 0 | 81400000 | 0 | 0
|  |  |  | 10-02-19-20-00 | L/D Selling Exp-Closing-Bulk Non-Residential | 3269850 | 3269850 | 0 | 0 | 0 | 0 | 3269850 | 0 |  | 0 | 3269850 | 0 | 0
|  |  |  | 10-03-19-10-00 | L/D Selling Exp-XClosing-Bulk Non-Residential | 407000 | 407000 | 10700 | 24300 | 0 | 35000 | 372000 | 35000 |  | 35000 | 372000 | 0 | 9
|  | Total 100790-ulsj-0003 |  |  |  | 85076850 | 85076850 | 10700 | 24300 | 0 | 35000 | 85041850 | 35000 |  | 35000 | 85041850 | 0 | 0
|  | 100790-ulsj-0004 | Speculative Land | 10-01-19-20-00 | Land Dev Sales-Bulk Non-Residential | 11532400 | 11532400 | 0 | 0 | 0 | 0 | 11532400 | 0 |  | 0 | 11532400 | 0 | 0
|  |  |  | 10-02-19-20-00 | L/D Selling Exp-Closing-Bulk Non-Residential | 288310 | 288310 | 0 | 0 | 0 | 0 | 288310 | 0 |  | 0 | 288310 | 0 | 0
|  |  |  | 10-03-19-10-00 | L/D Selling Exp-XClosing-Bulk Non-Residential | 57662 | 57662 | 0 | 0 | 0 | 0 | 57662 | 0 |  | 0 | 57662 | 0 | 0
|  | Total 100790-ulsj-0004 |  |  |  | 11878372 | 11878372 | 0 | 0 | 0 | 0 | 11878372 | 0 |  | 0 | 11878372 | 0 | 0
|  | 100790-ulsj-0005 | Community 16 | 10-01-19-20-00 | Land Dev Sales-Bulk Non-Residential | 9394050 | 9394050 | 0 | 0 | 0 | 0 | 9394050 | 0 |  | 0 | 9394050 | 0 | 0
|  |  |  | 10-02-19-20-00 | L/D Selling Exp-Closing-Bulk Non-Residential | 234851 | 234851 | 0 | 0 | 0 | 0 | 234851 | 0 |  | 0 | 234851 | 0 | 0
|  |  |  | 10-03-19-10-00 | L/D Selling Exp-XClosing-Bulk Non-Residential | 46970 | 46970 | 0 | 0 | 0 | 0 | 46970 | 0 |  | 0 | 46970 | 0 | 0
|  | Total 100790-ulsj-0005 |  |  |  | 9675871 | 9675871 | 0 | 0 | 0 | 0 | 9675871 | 0 |  | 0 | 9675871 | 0 | 0
|  | 100790-ulsj-0006 | Community 17 | 10-01-19-20-00 | Land Dev Sales-Bulk Non-Residential | 9592400 | 9592400 | 0 | 0 | 0 | 0 | 9592400 | 0 |  | 0 | 9592400 | 0 | 0
|  |  |  | 10-02-19-20-00 | L/D Selling Exp-Closing-Bulk Non-Residential | 239810 | 239810 | 0 | 0 | 0 | 0 | 239810 | 0 |  | 0 | 239810 | 0 | 0
|  |  |  | 10-03-19-10-00 | L/D Selling Exp-XClosing-Bulk Non-Residential | 47962 | 47962 | 0 | 0 | 0 | 0 | 47962 | 0 |  | 0 | 47962 | 0 | 0
|  | Total 100790-ulsj-0006 |  |  |  | 9880172 | 9880172 | 0 | 0 | 0 | 0 | 9880172 | 0 |  | 0 | 9880172 | 0 | 0
|  | 100790-ulsj-0007 | Estrella Water Credits | 25-02-50-30-06 | Incidental Other Revenue | 0 | 0 | 0 | -3819375 | 0 | -3819375 | 3819375 | -3819375 |  | -3819375 | 3819375 | 0 | 0
|  | Total 100790-ulsj-0007 |  |  |  | 0 | 0 | 0 | -3819375 | 0 | -3819375 | 3819375 | -3819375 |  | -3819375 | 3819375 | 0 | 0
|  | 100790-ulsj-0008 | South - 582 acres Land (Lofdahl) | 10-01-19-20-00 | Land Dev Sales-Bulk Non-Residential | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-02-19-20-00 | L/D Selling Exp-Closing-Bulk Non-Residential | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 10-03-19-10-00 | L/D Selling Exp-XClosing-Bulk Non-Residential | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100790-ulsj-0008 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total 100790 | [5 empty] | 177313153 | 177313153 | 10700 | 8956259 | 0 | 8966959 | 168346194 | 8966959 |  | 8966959 | 168346194 | 0 | 5
100890 | NNP Non-Potable Distribution Company LLC | 100890-ldcc-0401 | RV Campus NP Water Tank Exp | 20-02-12-20-06 | Engineering-General | 645701 | 645701 | 0 | 0 | 0 | 0 | 645701 | 0 |  | 0 | 645701 | 0 | 0
|  |  |  | 20-02-23-00-02 | General Contractor-Onsite Development | 1937101 | 1937101 | 0 | 0 | 0 | 0 | 1937101 | 0 |  | 0 | 1937101 | 0 | 0
|  |  |  | 25-02-59-91-03 | Contingency - Development | 286978 | 286978 | 0 | 0 | 0 | 0 | 286978 | 0 |  | 0 | 286978 | 0 | 0
|  | Total 100890-ldcc-0401 |  |  |  | 2869780 | 2869780 | 0 | 0 | 0 | 0 | 2869780 | 0 |  | 0 | 2869780 | 0 | 0
|  | 100890-ldrj-0200 | Non Potable Common Cost Job | 25-02-50-30-06 | Incidental Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total 100890-ldrj-0200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total 100890 | [5 empty] | 2869780 | 2869780 | 0 | 0 | 0 | 0 | 2869780 | 0 |  | 0 | 2869780 | 0 | 0
100999 | Estrella Partners LP - ELIM | 100999-ldci-0959 | Capitalized Interest | 25-02-55-20-01 | Interest Paid-N/P-Promissory | 0 | 0 | 0 | 14600981 | 0 | 14600981 | -14600981 | 14600981 |  | 14600981 | -14600981 | 0 | 0
|  |  |  | 25-02-55-20-06 | Interest Paid-B/P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 25-02-55-40-01 | Loan Fee Paid-N/P-Promissory | 0 | 0 | 0 | 1060720 | 0 | 1060720 | -1060720 | 1060720 |  | 1060720 | -1060720 | 0 | 0
|  | Total 100999-ldci-0959 |  |  |  | 0 | 0 | 0 | 15661701 | 0 | 15661701 | -15661701 | 15661701 |  | 15661701 | -15661701 | 0 | 0
Total 100999 | [5 empty] | 0 | 0 | 0 | 15661701 | 0 | 15661701 | -15661701 | 15661701 |  | 15661701 | -15661701 | 0 | 0
Grand Total | [5 empty] | 342256323 | 356606141 | 41088618 | 132567930 | 0 | 173656552 | 182949588 | 168798782 |  | 168798782 | 187807359 | 4857770 | 47